| Program Name: | CCC/IOU Energy Efficiency Partnership |
| --- | --- |
| Program Number: | SCG3518 |
| Quarter: | Second Quarter 2008 |

- Program description

The California Community Colleges/Investor Owned Utility Energy Efficiency Partnership is a unique, statewide program to achieve immediate and long-term energy savings and peak demand reduction within California’s higher education system. The combined funding of nearly $29M for the 2006-08 program cycle will establish a permanent framework for sustainable, comprehensive energy management at Community College campuses served by California's four Investor Owned Utilities.

The 2006-2008 CCC/IOU Partnership was based on the experiences of the previous partnership cycle.  The management structure was modeled after the 2004-2005 UC/CSU Partnership.  However, the structure was flattened to facilitate the decision making process.   A Management Team was established to coordinate the Program activities and has been meeting on a regular basis since program initiation.

- Administrative activities

- Continued to hold Partnership Management Team meetings every three weeks to conduct the business of the Partnership.  Held bi-weekly Project Team meetings to review and approve new project applications, Outreach Team meetings as needed to focus marketing efforts, and held several Training and Education Team meetings to refocus the program’s training activities.

- The Partnership was represented at Butte College Sustainability Conference in June with Management Team members participating in conference sessions and Outreach activities with Community College attendees from across the state.   Presentations focused on energy savings measures, Monitoring Based Commissioning (MBCx), IT systems, including Server Virtualization and PC Power Management, and Food Service Technology.  Emphasis was also placed on the life-cycle cost savings that are generated form, energy efficiency projects.  The information presented was well received by the attendees and generated significant interest in the program.

- The Partnership coordinated a Food Service Technology workshop at the SCG Energy Resource Center in Downey.  Several southern California CCC campus representatives attended this very informative session.  This was piggy-backed by a MBCx workshop for campuses and potential commissioning agent contractors on the same date

- The Management Team continued with planning activities for the 2009-2011 Partnership program cycle, and finalized a “bottoms-up” approach to developing energy savings goals and incentive budgets utilizing the CCC FUSION Maintenance and Capital Outlay Project Planning Database.  This database contains all planned and funded projects at CCC campuses scheduled for the next five years.  Estimates for energy savings were generated based on projects listed, and was supplemented by campus visits and forecasted savings for non-listed projects such as MBCx, new central plants, and emerging technology projects.  The estimates were refined by the IOUs in preparation for final CPUC filing in late June or early July.

- Marketing activities

- Enhanced Outreach, Marketing and Project Development efforts continued during the second quarter in SCE, PG&E, SDG&E and SCG territories to focus on achieving savings goals.  Project development activities focused on high-probability, quick turnaround projects that could deliver significant savings for the 06-08 program cycle.   Monitoring-Based Commissioning (MBCx), Information Technology (IT), Emerging Technologies (ET) and Food Service Technology (FST) projects have emerged as an outreach focus as these are been identified as an “un-tapped” opportunity for the CCC’s and can be completed in a reasonably short period of time.  In addition to identifying savings for this program cycle, opportunities for longer term projects, especially new construction associated with CCC bond measures, were tracked to help evaluate program potential for the 09-10-11 program cycle the effort at the District and Campus level.

- As described above, the Outreach Team participated in the Butte College Sustainability Conference to expand outreach activities for Information Technology energy projects.

- The Management Team began preparation for the UC/CSU/CCC Sustainability Conference scheduled for July 31 – August 2 of 2008.  The CCC/IOU Partnership will take part in conference sessions and presentations, as part of an exhibitor booth, and in the Best Practices Awards Competition.  This is an important conference as it allows the CCC’s to share best practices and network with peers from the UC and CSU systems.

- Direct implementation activities

- Plans were finalized for collaboration between the Partnership and the IOU Energy Training Centers to deliver an Energy Efficiency Maintenance and Operations Training Pilot Project to be offered to CCC Facilities and M&O Staff.  The training will be based on existing IOU training courses that were selected to reflect the results of a CCC training needs survey completed in 2006 by the Partnership.  The Pilot Project training will be delivered to selected campuses in a combined video-conference and webinar format. Live attendance will not be necessary. This format was chosen to minimize staff time away from work and provide for more flexibility for attendees.  The Pilot Project will focus in SCE territory and tie in one campus in SDG&E territory and two campuses in PG&E territory.  Training will be conducted by SCE training center staff.   The Pilot Project training offering will be delivered in fall of 2008, and will be used as a basis to develop a broader training program for all CCC campuses in the 2009-2011 energy efficiency program cycle.  In addition, possible synergies between Partnership T&E efforts and District curriculum development in the energy and sustainability and “Green Workforce” career development areas have also been explored.

- The Monitoring Based Commissioning (MBCx) pilot program continued to expand in the CCC footprint with several projects approved at campuses.  As discussed above, two MBCx “workshops” were delivered to CCC campuses in the 1st and 2nd Quarter to better disseminate program requirements, answer questions, and encourage participation.  The expansion of MBCx in the CCC Partnership is one strategy used as part of the enhanced project development activities and is expected to produce significant savings for this program cycle and position campuses for projects in 2009-2011.

- Significant effort was expended by Management Team personnel and IOU staff in working with campuses on updating project status to ensure 2008 completion.  Enhanced tracking reports and an “Off-Cycle Project Review” meeting was held every three weeks to facilitate this effort.

- Program performance/program status (describe)

Program is on target

Program is exceeding expectations

Program is falling short of expectations

Significant effort in Outreach and project development activities continued in the second quarter in an effort to achieve program goals.

- Program achievements (non-resource programs only):

- There is a shortfall of approved projects at this point in the cycle.  As discussed above, the Outreach plans and recent enhanced efforts have resulted in more project approvals and gains in working toward achieving the Program saving goals.

- Changes in program emphasis, if any, from previous quarter (new program elements, less or more emphasis on a particular delivery strategy, program elements discontinued, measure discontinued, budget changes, etc.).

- As discussed above, significant effort was expended by Management Team personnel and IOU staff in working with campuses on updating project status to ensure 2008 completion.  Enhanced tracking reports and an “Off-Cycle Project Review” meeting was held every three weeks to facilitate this effort.

- Began discussions of 2009-2011 program cycle elements with the Management Team.

- Discussion of near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation, etc.)

- Continued review and approval of Project Applications as they are submitted by Districts, recognizing the schedule restraints to bring projects in by the end of 2008.

- Continue with enhanced project tracking and forecasting activities to ensure project completion by the end of 2008

- Continue with enhanced Outreach Team efforts in diverse technical areas such as IT, ET, Food Service and MBCx to identify additional Project Applications for submission and provide technical assistance to Districts/Campuses in need.

- Continue to develop a Training & Education program in collaboration with the IOU Energy Training Centers.

- Continue with the development of MBCx pilot program for the Partnership.

- Monitor project progress and maintain Project Tracking Tool in Program web site in order to actually assess and forecast Program performance toward goals.

- Continue with Management Team planning efforts to develop program strategies, elements, and savings and incentive budget estimates for the 2009-2011 Partnership.

- Changes to staffing and staff responsibilities, if any

Addition of an analyst, Elizabeth Nemeth.

- Changes to contracts, if any

No changes.

- Changes to contractors and contractor responsibilities, if any

No changes.

- Number of customer complaints received

No complaints received.

- Revisions to program theory and logic model, if any

No changes.