Program Title: Statewide Residential Home Energy Efficiency Surveys Program

- Program Overview:

- The Home Energy Efficiency Survey program provides customer specific energy efficiency information for single-family residential customers.  The program employs two delivery channels: Mail-In Surveys, which include targeted direct mailings, and the interactive online survey in English, which offers convenient results online to provide customers with valuable information to assist them with understanding, controlling and reducing energy use in their homes.

- Program Summary

- Total program budget =$170,000*

- Expenditures to date = $158,957

*The program budget was revised from the forecast filing in accordance w/ D.03-04-055 Attachment 1”

- Total net demand reduction and energy savings

- Not applicable for this information program

- Total number of customers served during second quarter

|  | - Mail-In Survey | - Hard To Reach Mailing |
| --- | --- | --- |
| - Program Target* | - 6,000 | - 3000 (50% 0f Mail In target ) |
| - Actual | - 196 surveys completed | - Mailings will occur during Q3 & Q4 |

*2003 targets were not set for the second quarter.

- Projected and actual number of units:

- Please refer to the program activity tables shown in the corresponding program workbook.

- Total rebate

- Not applicable to this information program

- Program Implementation Status

- Status of program delivery

In compliance with Decision 03-04-055, Statewide utilities worked jointly to launch the  Home Energy Efficiency Program following Commission approval on April 17th, 2003.

- Customer Enrollment

- The following sample copies of audits were sent to the Commission's Energy Division:

- Mail-in survey - English and Spanish in all four IOU service territories

- Chinese in PG&E, SoCalGas, and SCE service territories, and

- Vietnamese in SDG&E’s service

- Workbook

- Please refer to informational tables shown in the program workbook for details of program expenditures and program activities

- Training

- Customer training is typically not conducted due to the nature of the program.  The energy audits are created in simplified form to help the customer’s complete an energy audit.

- Marketing

| - List Pieces | - Quantity completed during second quarter | - Method of Delivery | - Number Each Method |
| --- | --- | --- | --- |
| - Completed On Line Interactive Survey | - 1,241 | - On line interactive | - 1,241 |
| Mail In surveys | - 196 | - Mail in survey | - 196 |

SoCalGas Web Page

- The SoCalGas website identified below provides a description of the program; lists measures with general specifications and rebate levels; downloadable application forms, and audit surveys.

- www.socalgas.com

- Hard to Reach

- IOU’s will work within the Commissions definition of hard to reach customers as defined in the October 2001 Energy Efficiency Policy Manual, to actively target one or more of the customer segments for mailing.  In compliance with D. 03-04-055, at least 50% of the following utility mail-in survey targets as defined by the Commission, will be sent to Hard To Reach customers:

| Utility | 2003 Mail In survey targets | Hard To Reach mailings |
| --- | --- | --- |
| PG&E | 29,000 | 14,500 |
| SCE | 18,000 | 9000 |
| SCG | 6,000 | 3,000 |
| SDGE | 8,000 | 4,000 |

- Program Accomplishments

Statewide Second Quarter Activities

Statewide utilities worked jointly to plan, coordinate and launch the Statewide Home energy Efficiency program following Commission approval on April 17th, 2003. Statewide activities include:

- Implementation of new statewide pricing structure for mail-in surveys, a statewide survey mailing schedule and standard statewide reporting requirements to improve program delivery.

- Each utility made progress towards the selection of a vendor to develop a utility specific online home energy efficiency survey in Spanish.

- Discussed options for providing non-financial incentives to customers who complete the online Spanish language HEES once available on web sites.

SoCalGas Second Quarter Activities

- Program Manager coordinated discussions on implementing an interactive Spanish on-line audit.   SoCalGas will introduce an interactive on-line Spanish audit in 2003.

- Worked in conjunction with statewide IOU’s to implement a new statewide pricing structure for mail-in surveys, a statewide survey mailing schedule and standard statewide reporting requirements to improve program delivery

- Program Challenges

- None

- Customer Disputes

- None

- Compliance Items

- The following list itemizes the various regulatory compliance items issued by the California Public Utilities Commission directly relating to this program.

D. 03-04-055, Ordering Paragraph 3 states:

No party shall delay program commencement or preparation pending submission of or Commission action on these plans.

Response:

Program commencement and preparation were not delayed pending submission of or Commission action on these plans.

D. 03-04-055, Ordering Paragraph 6 states:

The utilities shall work together to market their statewide programs.  To the extent the utilities offer the same programs, they shall advertise them together.  Program Implementation Plans and quarterly reports shall describe utility efforts to coordinate programs.  Utilities shall focus all PGC-funded marketing for programs in this decision on energy efficiency messages.

Response:

SDG&E will work together with other utilities to market their statewide programs.  To the extent SDG&E offers the same programs SDG&E will advertise them together with the other utilities.  SDG&E’s Program Implementation Plans and quarterly reports describe utility efforts to coordinate programs.  Utilities shall focus all PGC-funded marketing for programs in this decision on energy efficiency messages.

Decision 02-03-056, states

50% of all mailed statewide residential Home Energy Efficiency Surveys shall be sent to hard to reach customers.  IOU’s shall develop and make available a Spanish language version of the survey and a version in the most prevalent Asian language in the IOU’s territory for both mailing and web posting within two months of the launch of their survey programs.

- Response:

- IOU’s actively targeted hard to reach customers via direct mailing efforts, based on each IOU’s unique marketing strategy.  For SDG&E this occurred in early fall 2002.  IOU’s met the Commission’s mandate for having Spanish and Asian language version surveys available for mailing and web posting within two months of the programs launch date, or June 1, 2002.

Decision 03-04-055, states:

We require each ( IOU ) to provide mailed and online surveys in Spanish.  The IOUs should continue to send 50% of mail-in surveys to hard to reach customers.

- Response:

- IOU’s continue to work jointly to implement the Commissions mandate of a Spanish version interactive online survey.  IOU’s are targeting the third quarter 2003, for the addition of this component.  IOU’s continue to send at least 50% of mailed surveys to Hard To Reach customers.

Residential Hard-to-Reach: Those customers who do not have easy access to program information or generally do not participate in energy efficiency programs due to a language, income, housing type, geographic, or home ownership (split incentives) barrier.  These barriers are defined as:

- Language – Primary language spoken is other than English, and/or

- Income – Those customers who fall into the moderate income level (income levels less than 400% of federal poverty guidelines), and/or

- Housing Type – Multi-Family and Mobile Home Tenants, and/or

- Geographic – Residents of areas other than the San Francisco Bay Area, San Diego area, Los Angeles Basin or Sacramento, and/or

- Homeownership – Renters