| Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Name: | Statewide Residential Single Family Home Energy Efficiency Rebate |
| IOU Service Area: | SCG |
| Program Number: | 1220-04 |
| Program Type: | IOU Statewide Program |
| Month | April-05 |

- Program Status

| Budget and Expenditures | Budget | Apr-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $12,145,090 | $566,890 | 5% | $7,607,126 | 63% |  |  | $7,607,126 | 63% | $4,537,964 |
| Admin | $1,432,400 | $48,474 | 3% | $584,342 | 41% |  |  | $584,342 | 41% | $848,058 |
| Marketing | $2,174,790 | $152,989 | 7% | $1,573,164 | 72% |  |  | $1,573,164 | 72% | $601,626 |
| DI | $8,368,900 | $365,427 | 4% | $5,449,620 | 65% |  |  | $5,449,620 | 65% | $2,919,280 |
| EM&V | $169,000 |  |  |  |  |  |  |  |  | $169,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

| Energy Effects | Goals | Apr-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 4,250 | 291 | 7% | 2,109 | 50% |  |  | 2,109 | 50% | 2,140 |
| Annual kWh | 10,766,576 | 928,999 | 9% | 6,739,834 | 63% |  |  | 6,739,834 | 63% | 4,026,742 |
| Lifecyc kWh | 157,409,229 | 12,751,795 | 8% | 91,782,007 | 58% |  |  | 91,782,007 | 58% | 65,627,222 |
| Annual Therms | 4,736,076 | 445,713 | 9% | 3,244,111 | 68% |  |  | 3,244,111 | 68% | 1,491,966 |
| Lifecyc Therms | 63,299,167 | 5,645,623 | 9% | 40,582,395 | 64% |  |  | 40,582,395 | 64% | 22,716,772 |

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Performance Goals | Goals | April -05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Hard to Reach goal is that 23% of rebate applications come from HTR zip codes | 23% | 28% | 121% |  |  |  |  | 28% | 121% |  |

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative  - 
Participated in  monthly calls with CA statewide Single Family team to discuss utility update on 2005 SF rebate program.

    - Marketing

    - Participated in Earth Day activities and Pasadena Home and Garden show.  SF applications and SoCalGas newsletters featuring the 2005 SF rebate program were distributed.

    - An Orange County register article promoting energy-efficiency featured SoCalGas’ 2005 SF rebate program.  The article encouraged customers to use energy wisely and participate in SoCalGas’ rebate program

    - 2005 SF Spanish application was distributed to retailers in highly populated Spanish speaking communities and made available on SoCalGas’ web site.

    - Direct Implementation

      - For Audits and Site Surveys :N/A

      - For Direct Installations, Rebates, Equipment Maintenance and Optimization  -

- Total number of customers sites served 2,474

- Summary of type and number of measures installed or repaired

| Measure Type | Measure Qty |
| --- | --- |
| Appliances | 1,951 |
| Building Shell - Insulation | 814,320 |
| HVAC - Controls | 3,749 |
| HVAC - Heating Systems | 235 |
| Water Heating - Systems | 277 |
| Grand Total | 820,532 |

      - Discrepancies between total month's rebates paid may differ from the total calculated in the workbook due to the following reasons:

(1) There may be a lag in customer rebate payments, particularly those approved for payments towards the end of the month, due to the processing of check payments;

(2) SoCalGas pays an approved customer application either the prescribed rebates/incentives or the cost shown on the customer invoice, whichever is lower;

    - EM&V

- Program Challenges 
None

- Customer Disputes 
None

- Compliance - SoCalGas filed an updated Program Implementation Plan for this program on December 13, 2004 per  Decision 04-12-019, issued on December 2, 2004.

- Coordination Activities
Coordination Activities are detailed in the revised PIP

- Changes to Subcontractors or Staffing – Program Manager Assignment has changed

- Additional Items-None

Supporting Documentation

- Marketing Materials – 
None this month

- Point of Purchase Program Documentation – 
None this month

- Free Measure Distribution Documentation-  
This program does not distribute free measures

- Upstream Incentive Documentation – 
This program is not an upstream incentive program.

- Training Documentation – 
None this month

- Trade Shows and Public Events – 
None this month