| Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Name: | Statewide Residential Multifamily Energy Efficiency Rebates |
| IOU Service Area: | SCG |
| Program Number: | 1246-04 |
| Program Type: | IOU Statewide Program |
| Month | April-04 |

- Program Status

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | April-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $4,624,768 | $140,177 | 3% | $2,806,080 | 61% |  |  | $2,806,080 | 61% | $1,818,688 |
| Admin | $522,750 | $15,870 | 3% | $220,632 | 42% |  |  | $220,632 | 42% | $302,118 |
| Marketing | $455,360 | $15,798 | 3% | $368,787 | 81% |  |  | $368,787 | 81% | $86,573 |
| DI | $3,575,580 | $108,509 | 3% | $2,216,661 | 62% |  |  | $2,216,661 | 62% | $1,358,919 |
| EM&V | $71,078 |  |  |  |  |  |  |  |  | $71,078 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

| Energy Effects | Goals | April-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 791 | 2 | 0% | 113 | 14% |  |  | 113 | 14% | 678 |
| Annual kWh | 13,141,337 | 548,593 | 4% | 10,354,867 | 79% |  |  | 10,354,867 | 79% | 2,786,470 |
| Lifecyc kWh | 162,081,837 | 6,591,640 | 4% | 124,884,111 | 77% |  |  | 124,884,111 | 77% | 37,197,726 |
| Annual Therms | 1,885,379 | 60,789 | 3% | 1,238,055 | 66% |  |  | 1,238,055 | 66% | 647,324 |
| Lifecyc Therms | 21,317,206 | 685,351 | 3% | 14,383,403 | 67% |  |  | 14,383,403 | 67% | 6,933,803 |

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder.

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Performance Goals | Goals | April-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Hard to Reach goal is that 29% of rebate applications come from HTR zip codes | 29% | 30% | 103% |  |  |  |  | 30% | 103% | 0 |

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative

    - Regular monthly administrative activities include but are not limited to the following activities:

- Multiple calls with CA statewide Multifamily team to review budgets and launch of 2005 rebate applications and associated documents.

- SCG continued distribution of MF applications from Program Manager -

- SCG note in its application and website that small appliances, showerheads and aerators were no longer available.

- Attended the two day Statewide meeting to discuss 2006 -2008 program guidelines and strategy.

- Participated in the on-site rebate inspection process at a MF apartment complex to gain understanding of the overall procedure.

- Provided 92 reservations for MF rebate funds

    - Marketing

    - Continued the fourth month of full-page ads promoting SCG MF Energy Efficiency rebates in 4 property owner industry publications.

    - Worked with statewide team to finalize ad for MF Trends Magazine and the Pacific Coast Builder’s Conference Program advertisement.

    - Participated in the Pasadena Home and Garden Show; Distributed applications, brochures and informed customers of SoCalGas Energy Efficiency Programs.

    - Program Manager attended site visit of the Residential Marketing Group at the San Dimas Customer Contact Center to make personal introduction, conduct side by side call observations and answer pertinent questions regarding program status.

    - Direct Implementation

      - For Audits and Site Surveys  - Not Applicable

      - For Direct Installations, Rebates, Equipment Maintenance and Optimization

- Total number of customers sites served, 31

- Summary of type and number of measures installed or repaired.

| Measure Type | Measure Qty |
| --- | --- |
| Appliances | 6 |
| Building Shell – Insulation | 1,400 |
| HVAC - Controls | 1,611 |
| HVAC – Heating Systems | 0 |
| Other | 0 |
| Water Heating - Systems | 26 |
| Water Heating - Controls | 1 |
| Grand Total | 3,044 |

      - Discrepancies between total month's rebates paid may differ from the total calculated in the workbook due to the following reasons:

(1) There may be a lag in customer rebate payments, particularly those approved for payments towards the end of the month, due to the processing of check payments;

(2) SoCalGas pays an approved customer application either the prescribed rebates/incentives or the cost shown on the customer invoice, whichever is lower;

    - EM&V

- Program Challenges 
None

- Customer Disputes 
None

- Compliance Items 
SoCalGas filed an updated Program Implementation Plan for this program on December 13, 2004 per  Decision 04-12-019, issued on December 2, 2004.

- Coordination Activities 
 Coordination Activities are detailed in the revised PIP

- Changes to Subcontractors or Staffing - 
None

- Additional Items - None

Supporting Documentation

- Marketing Materials – 
Full page ad placed with four Apartment publications

- Point of Purchase Program Documentation – 
This program does not have point of purchase activities.

- Free Measure Distribution Documentation- 
This program does not distribute free measures

- Upstream Incentive Documentation – 
This program is not an upstream incentive program.

- Training Documentation – 
There were no training activities this month

- Trade Shows and Public Event

Pasadena Home and Garden Show