| Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Name: | Local Nonresidential Financial Incentives Program |
| IOU Service Area: | SCG |
| Program Number: | 1260-04 |
| Program Type: | IOU Local Program |
| Month | April-05 |

- Program Status

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget  in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | Apr-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $4,936,084 | $117,508 | 2% | $4,299,117 | 87% |  |  | $4,299,117 | 87% | $636,967 |
| Admin | $1,057,645 | $62,055 | 6% | $573,979 | 54% |  |  | $573,979 | 54% | $483,666 |
| Marketing | $228,150 | $3,570 | 2% | $111,269 | 49% |  |  | $111,269 | 49% | $116,881 |
| DI | $3,460,079 | $51,445 | 1% | $3,600,740 | 104% |  |  | $3,600,740 | 104% | -$140,661 |
| EM&V | $190,210 | $438 | 0% | $13,128 | 7% |  |  | $13,128 | 7% | $177,082 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Energy Effects | Goals | Mar-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW |  |  | NA |  | NA |  | NA |  | NA |  |
| Annual kWh |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc kWh |  |  | NA |  | NA |  | NA |  | NA |  |
| Annual Therms | 3,019,954 | 70,603 | 2% | 4,068,722 | 135% |  |  | 4,068,722 | 135% | -1,048,768 |
| Lifecyc Therms | 48,742,088 | 1,133,775 | 2% | 67,006,939 | 137% |  |  | 67,006,939 | 137% | -18,264,851 |

Note: Energy savings have not been updated for April pending final review of savings assumptions.

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

This program does not have performance goals.

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative

Regular monthly administrative activities include but are not limited to the following activities: continued refining of the customer participation process and program design, review of customer participation and market activity, coordination with participating retailers, vendors, and manufacturers and other market participants, contract management, responding to customer inquiries and concerns, planning of future training events, and managing of program budgets and expenditures.

This month, additional activities included:

A Commercial Foodservice Rebate Program Bill insert, with reference to the Food Service Equipment Center, was sent to all C&I Customers during April.

    - Marketing

- On 4/22/05, SoCalGas attended the Orange County Hospitality Industry Breakfast held in Brea California.  A SoCalGas representative reviewed NRFIP program details, and other DSM energy efficiency opportunities.  NRFIP literature and applications were distributed to the approximately 60 attendees.

- SoCalGas conducted two NRFIP and additional DSM Program update training sessions at San Bernardino District on April 13th for approximately 28 Commercial Service Techs, Industrial Service Techs, their reliefs, and supervisors. Approximately eight Account Executives also attended this update session.  An additional update training session was held in Valencia, CA on April 21st, for approximately 12 SoCalGas Northern Region Field Operation Supervisors. Current and future NRFIP and other DSM program changes were discussed, followed by a Q&A session.

- SCG distributed 1,435 Commercial Food Service Rebate applications in April.  There were 514 other pieces of NRFIP collateral distributed directly to customers.  Additional applications and collateral were distributed at additional events, through vendors, and from the internet.

    - Direct Implementation

      - For Audits and Site Surveys  - Not applicable

      - For Direct Installations, Rebates, Equipment Maintenance and Optimization  -

- Total number of customers sites served, 56

- Summary of type and number of measures installed or repaired

| Measure Type | Qty |
| --- | --- |
| Nonresidential - Custom End Use | 44,772 |
| Nonresidential - Food Service & Processing | 6,401 |
| Grand Total | 51,177 |

      - Discrepancies between total month's rebates paid may differ from the total calculated in the workbook  due to the following reasons:

(1) There may be a lag in  customer rebate payments, particularly those approved for payments towards the end of the month, due to the processing of check payments;

(2) SoCalGas pays an approved customer application either the prescribed rebates/incentives or the cost shown on the customer invoice, whichever is lower.

    - EM&V

- Program Challenges 
None

- Customer Disputes 
None

- Compliance Items

SoCalGas filed an updated Program Implementation Plan for this program on December 13, 2004 per Decision 04-12-019, issued on December 2, 2004.

- Coordination Activities

Coordination activities are detailed in the revised PIP.

- Changes to Subcontractors or Staffing

None

- Additional Items

None

Supporting Documentation

- Marketing Materials –

Commercial Foodservice Rebate Program Bill insert

- Point of Purchase Program Documentation –
This program does not have point of purchase activities.

- Free Measure Distribution Documentation – 
This program does not distribute free measures.

- Upstream Incentive Documentation – 
This program is not an upstream incentive program.

- Training Documentation – 
This program does not have training activities.

- Trade Shows and Public Events –

Orange County Hospitality Industry Breakfast held in Brea, California on 4/22/05