| Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Name: | Statewide Residential Single Family Home Energy Efficiency Rebate |
| IOU Service Area: | SCG |
| Program Number: | 1220-04 |
| Program Type: | IOU Statewide Program |
| Month | May-05 |

- Program Status

| Budget and Expenditures | Budget | May-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $12,145,090 | $333,390 | 3% | $7,940,516 | 65% |  |  | $7,940,516 | 65% | $4,204,574 |
| Admin | $1,432,400 | $58,483 | 4% | $642,825 | 45% |  |  | $642,825 | 45% | $789,575 |
| Marketing | $2,174,790 | $37,708 | 2% | $1,610,872 | 74% |  |  | $1,610,872 | 74% | $563,918 |
| DI | $8,368,900 | $237,199 | 3% | $5,686,819 | 68% |  |  | $5,686,819 | 68% | $2,682,081 |
| EM&V | $169,000 |  |  |  |  |  |  |  |  | $169,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

| Energy Effects | Goals | May-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 4,250 | 191 | 4% | 2,300 | 54% |  |  | 2,300 | 54% | 1,950 |
| Annual kWh | 10,766,576 | 319,495 | 3% | 7,059,329 | 66% |  |  | 7,059,329 | 66% | 3,707,247 |
| Lifecyc kWh | 157,409,229 | 5,154,799 | 3% | 96,936,806 | 62% |  |  | 96,936,806 | 62% | 60,472,424 |
| Annual Therms | 4,736,076 | 136,490 | 3% | 3,380,601 | 71% |  |  | 3,380,601 | 71% | 1,355,475 |
| Lifecyc Therms | 63,299,167 | 1,981,477 | 3% | 42,563,872 | 67% |  |  | 42,563,872 | 67% | 20,735,295 |

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Performance Goals | Goals | May -05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Hard to Reach goal is that 23% of rebate applications come from HTR zip codes | 23% | 27% | 117% |  |  |  |  | 28% | 121% |  |

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative  - 
None.

    - Marketing

    - None this month

    - Direct Implementation

      - For Audits and Site Surveys :N/A

      - For Direct Installations, Rebates, Equipment Maintenance and Optimization  -

- Total number of customers sites served

- Summary of type and number of measures installed or repaired

| Measure Type | Measure Qty |
| --- | --- |
| Appliances | 1,684 |
| Building Shell - Insulation | 534,757 |
| HVAC - Controls | 431 |
| HVAC - Heating Systems | 150 |
| Water Heating - Systems | 237 |
| Grand Total | 537,259 |

      - Discrepancies between total month's rebates paid may differ from the total calculated in the workbook due to the following reasons:

(1) There may be a lag in customer rebate payments, particularly those approved for payments towards the end of the month, due to the processing of check payments;

(2) SoCalGas pays an approved customer application either the prescribed rebates/incentives or the cost shown on the customer invoice, whichever is lower;

    - EM&V

- Program Challenges 
None

- Customer Disputes 
None

- Compliance - SoCalGas filed an updated Program Implementation Plan for this program on December 13, 2004 per  Decision 04-12-019, issued on December 2, 2004.

- Coordination Activities
Coordination Activities are detailed in the revised PIP

- Changes to Subcontractors or Staffing – Program Manager Assignment has changed

- Additional Items-None

Supporting Documentation

- Marketing Materials – 
None this month

- Point of Purchase Program Documentation – 
None this month

- Free Measure Distribution Documentation-  
This program does not distribute free measures

- Upstream Incentive Documentation – 
This program is not an upstream incentive program.

- Training Documentation – 
None this month

- Trade Shows and Public Events – 
None this month