| Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Name: | Statewide Crosscutting Education & Training |
| IOU Service Area: | SCG |
| Program Number: | 1258-04 |
| Program Type: | IOU Statewide Program |
| Month | July-05 |

- Program Status

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | Jul-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $3,672,314 | $77,498 | 2% | $2,731,789 | 74% |  |  | $2,731,789 | 74% | $940,525 |
| Admin | $731,664 | $45,953 | 6% | $945,342 | 129% |  |  | $945,342 | 129% | -$213,678 |
| Marketing | $277,000 | $2,436 | 1% | $370,797 | 134% |  |  | $370,797 | 134% | -$93,797 |
| DI | $2,574,650 | $29,109 | 1% | $1,415,650 | 55% |  |  | $1,415,650 | 55% | $1,159,000 |
| EM&V | $89,000 |  |  |  |  |  |  |  |  | $89,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder.

Not applicable for this program.

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder

| Performance Goal | Current Month’s Achievement | Cumulative Achievement | Remainder |
| --- | --- | --- | --- |
| 137 Seminars | 11 | 85 | 52 |
| 40 HTR Seminars | 9 | 66 | 0 |
| 35 Outreach Events | 2 | 25 | 10 |

| Equipment Demonstrations | # of Demonstrations | # of Attendees |
| --- | --- | --- |
| Food Service | 16 | 168 |

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative

Regular monthly administrative activities include production and distribution of collateral, scheduling and holding classes and seminars, participating in community outreach events, planning for future classes and seminars, community and outreach events, managing of program budgets and expenditures and compiling data to prepare CPUC monthly reports.

    - Marketing

| Collateral | Description | Distribution | PDF File Name |
| --- | --- | --- | --- |
| Indoor Comfort News – IHACI Seminar Ad | Full-page advertisement in HVAC industry-focused monthly periodical, created to provide information on seminar content, time, date, location | Insert in publication | August ICN Ad.pdf |
| IHACI – System Design – Parts I & II (flier) (#13768/69 & #13726/27) | Single sheet flier created to provide information on seminar content, time, date, location, and availability for all seminars | 950 produced 750 direct mail (IHACI) 200 manually | 13768 13769 13726 13727 flier.pdf |
| Lamp & Ballast Basics (flier) (#14059) | Single sheet flier created to provide information on seminar content, time, date, location, and availability | 250 produced 250 manually | 14059 flier.pdf |
| Lamp & Ballast Basics (e-mail) (#14059) | Electronic-mail campaign created to provide information on seminar content, time, date, location and availability | 4,611 via e-mail | 14059 email.pdf |
| Gas Engines Testing & Tuning for AQMD Compliance / Modular Boiler Installation for Greater Gas Savings (flier) (#14020 & #14056) | Single sheet flier created to provide information on content, time, date, location, and availability for both seminars | 2,425 produced 2,075 direct mail 350 manually | 14020 14056 flier.pdf |
| Insulated Concrete Walls: Energy Efficiency Meets Sustainability (flier) (#13877) | Single sheet flier created to provide information on seminar content, time, date, location, and availability | 250 produced 250 manually | 13877 flier.pdf |
| Insulated Concrete Walls: Energy Efficiency Meets Sustainability (e-mail) (#13877) | Electronic-mail campaign created to provide information on seminar content, time, date, location and availability | 4,711 via e-mail | 13877 email.pdf |
| Insulated Concrete Walls: Energy Efficiency Meets Sustainability (e-mail) (#13877) | Electronic-mail campaign created to provide information on seminar content, time, date, location and availability (Second e-mail blast) | 4,726 via e-mail | 13877 email.pdf |
| European Influences on American Regional Cuisine (flier) (#12803) | Single sheet flier created to provide information on seminar content, time, date, location, and availability | 350 produced 350 manually | 12803 flier.pdf |
| European Influences on American Regional Cuisine (e-mail) (#12803) | Electronic-mail campaign created to provide information on seminar content, time, date, location and availability | 2,734 via e-mail | 12803 email.pdf |
| Food Regulations 101: Part III (flier) (#13032) | Single sheet flier created to provide information on seminar content, time, date, location, and availability | 300 produced 300 manually | 13032 flier.pdf |
| Food Regulations 101: Part III (e-mail) (#13032) | Electronic-mail campaign created to provide information on seminar content, time, date, location and availability | 2,734 via e-mail | 13032 email.pdf |
| (JEC) Smart Solutions for Future Energy Savings (flier) (#12804) | Single sheet flier created to provide information on seminar content, time, date, location, and availability | 2,075 produced 1,725 direct mail 350 manually | 12804 flier.pdf |
| (JEC) Smart Solutions for Future Energy Savings (e-mail) (#12804) | Electronic-mail campaign created to provide information on seminar content, time, date, location and availability | 2,734 via e-mail | 12804 email.pdf |

    - Direct Implementation

The following classes were offered to train and inform the market actors in energy efficient methods and technologies:

| Date | Class Description | Attendees |
| --- | --- | --- |
| 07/11/05 | # 13032 – FSEC Downey, CA Food Regulations 101 Part 3 This is the third class in a four-part Food Regulations series. Local, state, tribal, and federal regulators use the FDA Food Code as a model to develop or update their own food safety rules and to be consistent with national food regulatory policy. The code also serves as a reference of best practices for the retail and food service industries on how to prevent food borne illness. This class will cover water, plumbing, waste physical facilities, poisonous or toxic materials, and public health guidelines as well as energy-efficient practices for dealing with the various compliance areas. | 28 |
| 07/12/05 | # 13768– Chatsworth, CA System Design (Part 1 Duct Design) The majority of residential and commercial HVAC systems are design-build (designed by the contractor, not a mechanical engineer). Learn how to size linesets, ductwork, etc. Proper systems design leads to energy efficiency and proper system installations, followed by satisfied customers. | 61 |
| 07/14/05 | # 13769– Chatsworth, CA System Design (Part 2 Components) The majority of residential and commercial HVAC systems are design-build (designed by the contractor, not a mechanical engineer). Learn how to size linesets, ductwork, etc. Proper systems design leads to energy efficiency and proper system installations, followed by satisfied customers. | 54 |
| 07/14/05 | # 12804 – FSEC Downey, CA Smart Solutions for Future Energy Savings (JEC @SoCalGas) Today’s state-of-the-art technology offers myriad opportunities for food service professionals to achieve significant energy savings in their day-to-day operations, as well as laying the foundation for additional energy savings in the future. In addition to equipment, consideration will be given to work procedures and processes, which can be adjusted and adapted to reduce the use of energy. | 8 |
| 07/19/05 | # 14059 – ERC Downey, CA Lamp & Ballast Basics A half-day, basic-level interactive workshop created for anyone who is new to the field of lighting and who needs to be familiar with energy-saving lamp and ballast technologies, their operation, characteristics and performance. Instructor Kathleen Peake will address major topics including: incandescent/halogen, compact/linear fluorescent, and HID lamp technologies, lumen maintenance, efficacy, lamp life, hazardous waste and ballast disposal, starting scenarios, wiring schemes, sound rating, harmonics, dimming and much more. | 41 |
| 07/19/05 | # 13726– ERC Downey, CA System Design (Part 1 Duct Design) The majority of residential and commercial HVAC systems are design-build (designed by the contractor, not a mechanical engineer). Learn how to size linesets, ductwork, etc. Proper systems design leads to energy efficiency and proper system installations, followed by satisfied customers. | 100 |
| 07/20/05 | # 14185 – Corona, CA Hands-On Duct Testing Training As a proactive response to the needs of HVAC professionals, The Gas Company offers hands-on seminars to teach contractors, installers and service technicians how to self-test their work prior to undergoing third party verification for energy-efficient change-outs. These comprehensive one-night classes include an overview of rules and regulations for residential and nonresidential HVAC system change-outs, hands-on duct leakage test demonstrations, and relevant information on how to locate a HERS rater, what forms must be completed for the building department, and more. | 24 |
| 07/21/05 | # 13727– ERC Downey, CA System Design (Part 2 Components) The majority of residential and commercial HVAC systems are design-build (designed by the contractor, not a mechanical engineer). Learn how to size linesets, ductwork, etc. Proper systems design leads to energy efficiency and proper system installations, followed by satisfied customers. | 74 |
| 07/21/05 | # 14020 – ERC Downey, CA Gas Engines: Testing and Tuning for AQMD Compliance This seminar will discuss the significant issues of testing and tuning gas engines, and will include air-fuel ratio controllers, 3-way catalytic reduction, flue gas testing and tuning for efficiency, and AQMD compliance issues. Designed for water superintendents, co-generation or gas engine operators, public works directors, pump station operators, and engineers, this class also provides information on The Gas Company's rebate and incentive programs for equipment upgrades or replacements you may be considering. | 33 |
| 07/22/05 | # 13877 – ERC Downey, CA Insulated Concrete Walls: Energy Efficiency Meets Sustainability Designing and building with Insulated Concrete Forms (ICFs) is on the rise across the nation. Many are finding success with this technology due-to high performance energy efficiency and the building envelope contribution to sustainability. Speakers will highlight residential, commercial, institutional and educational facility applications. Other topics include design considerations, construction process and build-ability, and ICF's potential point additions to U.S. Green Building Council's LEED® rating system. | 60 |
| 07/27/05 | # 14056 – ERC Downey, CA Modular Boiler Installation for Greater Gas Savings This boiler seminar will focus on three key areas of efficiency: defining the type of efficiency to be measured, techniques for accurate efficiency measurement, and strategies for maximizing in-service efficiency through better on-demand performance. Solutions for meeting AFUE (Annual Fuel Utilization Efficiency), LEED, California State, and Gas Company requirements will be highlighted. | 8 |
| 07/27/05 | # 14186 – Sylmar, CA Hands-On Duct Testing Training As a proactive response to the needs of HVAC professionals, The Gas Company offers hands-on seminars to teach contractors, installers and service technicians how to self-test their work prior to undergoing third party verification for energy-efficient change-outs. These comprehensive one-night classes include an overview of rules and regulations for residential and nonresidential HVAC system change-outs, hands-on duct leakage test demonstrations, and relevant information on how to locate a HERS rater, what forms must be completed for the building department, and more. | 24 |

Outreach Events:

| Date | Organization | Event Description | Location |
| --- | --- | --- | --- |
| 06/10/05– 7/4/2005 | Del Mar Fair | Larry Bennett and Bonnie Moreno supported the SDG&E cooking demonstrations and distributed upcoming seminar flyers. | Del Mar, CA |
| 07/28/05– 07/29/05 | American Culinary Federation | Chef Jill Bosich, attended the annual ACF Convention/Conference, where she participated in discussions and workshops and stressed the importance of energy efficiency in professional food service operations. | San Antonio, TX |

      - Audits and Site Surveys  -

- Not applicable to this program

      - Direct Installations, Rebates, Equipment Maintenance and Optimization  -

- Not applicable to this program

      - Spending Variance

No applicable to this program.

      - EM&V

- Program Challenges 
None

- Customer Disputes 
None

- Compliance Items 
Revised program proposal and workbook filed on April 12, 2004 per the CPUC decision.

- Coordination Activities
Seminars and workshops focusing on commercial and residential new construction co-sponsored with SCG’s “Savings By Design” commercial new construction incentive program, Residential New Construction, and Building Operators Certification (BOC) program. Supporting the development of training and education of the UC/CSU/IOU Partnership program, South Bay Cities Council of Governments and the City of Ventura Resource Centers, and the California Energy Commission’s Best Practices education workshops.

- Changes to Subcontractors or Staffing
None.

- Additional Items 
None

Supporting Documentation

- Marketing Materials –

See 1.2.2

- Point of Purchase Program Documentation –

This program does not have point of purchase activities.

- Free Measure Distribution Documentation –

This program does not distribute free measures.

- Upstream Incentive Documentation –

This program is not an upstream incentive program.

- Training Documentation –

See 1.2.3

- Trade Shows and Public Events –

See 1.2.3