| Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Name: | Local Nonresidential Financial Incentives Program |
| IOU Service Area: | SCG |
| Program Number: | 1260-04 |
| Program Type: | IOU Local Program |
| Month | July-05 |

- Program Status

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget  in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | Jul-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $4,936,084 | -$78,715 | -2% | $3,777,996 | 77% |  |  | $3,777,996 | 77% | $1,158,088 |
| Admin | $1,057,645 | -$20,007 | -2% | $658,685 | 62% |  |  | $658,685 | 62% | $398,960 |
| Marketing | $228,150 | $153 | 0% | $122,406 | 54% |  |  | $122,406 | 54% | $105,744 |
| DI | $3,460,079 | -$91,066 | -3% | $2,950,153 | 85% |  |  | $2,950,153 | 85% | $509,927 |
| EM&V | $190,210 | $32,205 | 17% | $46,752 | 25% |  |  | $46,752 | 25% | $143,458 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Energy Effects | Goals | Jul-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW |  |  | NA |  | NA |  | NA |  | NA |  |
| Annual kWh |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc kWh |  |  | NA |  | NA |  | NA |  | NA |  |
| Annual Therms | 3,019,954 | -128,816 | -4% | 3,071,331 | 102% |  |  | 3,071,331 | 102% | -51,377 |
| Lifecyc Therms | 48,742,088 | -4,397,024 | -9% | 52,187,007 | 107% |  |  | 52,187,007 | 107% | -3,444,919 |

Note: Energy savings have not been updated for April pending final review of savings assumptions.

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

This program does not have performance goals.

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative

Regular monthly administrative activities include but are not limited to the following activities: continued refining of the customer participation process and program design, review of customer participation and market activity, coordination with participating retailers, vendors, and manufacturers and other market participants, contract management, responding to customer inquiries and concerns, planning of future training events, and managing of program budgets and expenditures.

This month, additional activities included:

- SCG met with Representatives of SDG&E, PG&E, and Fisher-Nickel to discuss the testing and development of work papers for food service equipment.  This will allow various food service equipment measures to be included in the PY2006 Energy Efficient Rebate Program.  Testing and work paper development may eventually lead to the inclusion of food service types of equipment in the Express Efficiency Rebate Program in PY2007-2008.

- SCG is currently researching and developing possible new measures for the Non-residential Financial Incentives Program.  Current items being reviewed are ozone technologies for the commercial and industrial laundry industries; new food service equipment; boiler system controls; and boiler water treatment measures.

- SCG provided a presentation on the status of the PY2004-05 DSM Programs, and information on the 2006-2008 DSM program filing for the SoCalGas Pacific Coast FOS 1 meeting held at the ERC in Downey on July 13th.  Approximately 15 C&I field supervisors attended.

    - Marketing

- SCG distributed 606 Commercial Food Service Rebate applications in June.  There were 229 other pieces of NRFIP collateral distributed directly to customers.  Additional applications and collateral were distributed at additional events, through vendors, and from the internet.

    - Direct Implementation

      - For Audits and Site Surveys  - Not applicable

      - For Direct Installations, Rebates, Equipment Maintenance and Optimization  -

- Total number of customers sites served

- Summary of type and number of measures installed or repaired

| Measure Type | Qty |
| --- | --- |
| Nonresidential - Custom End Use | 5 |
| Nonresidential - Food Service & Processing | 20 |
| Grand Total | 25 |

      - Discrepancies between total month's rebates paid may differ from the total calculated in the workbook  due to the following reasons:

(1) There may be a lag in  customer rebate payments, particularly those approved for payments towards the end of the month, due to the processing of check payments;

(2) SoCalGas pays an approved customer application either the prescribed rebates/incentives or the cost shown on the customer invoice, whichever is lower.

    - EM&V

- Program Challenges 
None

- Customer Disputes 
None

- Compliance Items

SoCalGas filed an updated Program Implementation Plan for this program on December 13, 2004 per Decision 04-12-019, issued on December 2, 2004.

- Coordination Activities

Coordination activities are detailed in the revised PIP.

- Changes to Subcontractors or Staffing

None

- Additional Items

None

Supporting Documentation

- Marketing Materials –

None

- Point of Purchase Program Documentation –
This program does not have point of purchase activities.

- Free Measure Distribution Documentation – 
This program does not distribute free measures.

- Upstream Incentive Documentation – 
This program is not an upstream incentive program.

- Training Documentation – 
This program does not have training activities.

- Trade Shows and Public Events –

None