| Program Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Title: | Ventura County Regional Energy Alliance – PGC |
| Program Number: | 1493-04 |
| Month: | July 2005 |

- Program Status

The Ventura County Regional Energy Alliance (VCREA), in partnership with Southern California Edison (SCE) and the Southern California Gas Company (SCG) proposes to build on the VCREA progress to date to further develop its core capabilities, to complete the development of its Energy Resource Center capability, and to implement a targeted Public Sector Program for public agencies throughout the Ventura County region.  This effort will utilize the strengths of the VCREA and its utility partners to jointly overcome identified participation barriers, better serve local needs and hard-to-reach customers, and increase participation in energy efficiency programs.

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | Jul-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $380,294 | -$124 | 0% | $7,528 | 2% |  |  | $7,528 | 2% | $372,766 |
| Admin | $43,148 | -$124 | 0% | $7,528 | 17% |  |  | $7,528 | 17% | $35,620 |
| Marketing | $5,290 |  |  |  |  |  |  |  |  | $5,290 |
| DI | $314,546 |  |  |  |  |  |  |  |  | $314,546 |
| EM&V | $17,310 |  |  |  |  |  |  |  |  | $17,310 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  Due to a lag in the time between when the partnership expends funds and when SCG is invoiced for its share of those expenditures, the reported monthly expenditures of the partnership may differ from the expenditures recorded in SCG’s accounting system.  Expenditures include some of SCE expenses.

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Energy Effects | Goals | Jul-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW |  |  | NA |  | NA |  | NA |  | NA |  |
| Annual kWh |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc kWh |  |  | NA |  | NA |  | NA |  | NA |  |
| Annual Therms | 141,772 |  |  |  |  |  |  |  |  | 141,772 |
| Lifecyc Therms | 2,126,586 |  |  |  |  |  |  |  |  | 2,126,586 |

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Performance Goals | Goal | July-05 | % of Goal | Cumulative | % of Goals | Committed | % of Goal | Cumulative & Committed | % of Goal | Goal Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Conduct at least 4 training sessions for the public sector | 4 | 1 | 25% | 4 | 100% | n/a | n/a | 4 | 100% | 0 |
| Conduct at least 6 sessions for businesses | 6 | 0 | 33% | 5 | 83% | n/a | n/a | 5 | 17% | 1 |
| Conduct at least 4 events for residential customers. | 4 | 0 | 0% | 5 | 125% | n/a | n/a | 5 | 125% | 0 |
| Promote VCEEC resources and energy efficiency information at 20 community events or more. | 20 | 0 | 0% | 17 | 80% | n/a | n/a | 17 | 80% | 3 |
| Respond to every customer inquiry within 48 hours. |  | met | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |
| Achieve an 80 percent overall customer satisfaction level of Excellent (based on follow-up surveys) of (Evaluation Levels: Poor, Below Average, Average, Good, and Excellent). |  | Good and Excellent | met | Good and Excellent | met | n/a | n/a | Good and Excellent | met |  |
| Reduce Energy Consumption in Major facilities of VCREA member agencies by 8 % |  | 0 | 0% | 0 | 0% | n/a | n/a | 0 | 0% |  |
| Reduce peak demand in major facilities of VCREA member agencies by 5% or more |  | 0 | 0% | 0 | 0% | n/a | n/a | 0 | 0% |  |

  - Activities/Accomplishments

    - Administrative -

Routine administrative activities to coordinate and manage the program continue.

    - Marketing -

- Prepared and released e-fliers and direct mailing to promote August 23 and 24th Energy Efficiency Training for water pump operations. (Attachment A).

- Released the July/August edition of the Energy Leader Newsletter for distribution the first week of July.  (Attachment B)

- Released one page of news in VCEDA bi-monthly newsletter distributed mid-month throughout the county with reported readership of 200,000. (Attachment C)

- VCREA staff met again with representatives of Ventura County Economic Development Association (VCEDA) as part of their monthly meeting to develop details associated with the annual Business Opportunities Conference planned for October 14, 2005.  Representatives of the partnership will be present as speakers and participants.

- Local Rotary Clubs have invited the VCREA to speak on the organization and the VCERC partnership programs.  A July 13th PowerPoint presentation was given to 48 members of the Westlake/Thousand Oaks Rotary Club.

- Staff met with several local representatives of energy related businesses such as lighting suppliers, energy systems operators, and insulation services providers who are interested in connecting to the resource center and partnership efforts.

    - Direct Implementation –

Training

- July 7, 2005 Energy Efficiency Best Practices for Public Policy Training was conducted by a team of consultants that included John Deakin, Kurt Kammerer, and VCREA project manager, David Inger.  The training was preceded by a VCERC open house for training participants and other guests.  A total of 27 participants, including planners, city officials, and architects attended the evening training that presented the issues and best practices surrounding development of local energy efficiency policies that support broader public policies and community planning efforts.   A compact disk of training supplements was distributed to participants.  (Attachment D containing flyer and agenda)

Community Events Participation

- None to report

A summary of plans and accomplishments for all training and community events is include in the Program Spreadsheet. (Attachment E)

      - Audits, Site Surveys and Partnerships –

A monthly update of the identified energy efficiency retrofit projects, costs, energy savings and incentives to date is included as Master Project List. (Attachment H)

Plans and Policy

VCREA coordination with public agency and private sector representatives of the Tri-Counties (VTA, SB, SLO) planning association culminated in the successful July 7th training event and VCERC open house. The session provided participants and VCREA member agencies with policy guidelines and resources that will assist in the implementation of local energy efficiency policies.  The training session has led to greater networking among the agencies and a desire to be more engaged in energy efficiency. The compact disk that was presented was also shared and provided to the VCREA board at their July 21st quarterly meeting to further inform policy makers of the energy issues and allow each member to take the documents to their individual agencies for incorporation into specific organizational policy.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Projects and Incentives

VCREA continues to support local public agency efforts to complete energy efficiency projects.  The following are the highlight for the month of July:

- The City of Ventura has completed a lighting replacement project at the Downtown Santa Clara Street Parking Structure (Attachment F)

- The City of Ventura has completed a  lighting replacement project at the Beachfront/Promenade Parking Structure (Attachment G)

- Three additional lighting projects for the City of Ventura are underway at the Police/Fire Headquarters, Sanjon Road Maintenance Complex and City Hall.

- Purchase orders for lighting projects at the Municipal Service Center and Wastewater Treatment Plant in the City of Thousand Oaks are being processed.  Work will commence during the month of September.

- The City of Ventura is reviewing bid submittals for HVAC upgrades.  Contract award is expected during the month of August.

A monthly update of the identified energy efficiency retrofit projects, costs, energy savings and incentives to date is included as Master Project List. (Attachment H)

A monthly update of the identified energy efficiency retrofit projects, costs, energy savings and incentives to date is included as Master Project List. (Attachment J).

      - Calculated and Actual Payment Reconciliation - None

      - EM&V

No activity this month.

- Program Challenges
None

- Customer Disputes
None

- Compliance Items
None

- Coordination Activities

VCREA participated in various meetings, coordinative phone calls and e-mail exchanges with SCE and SCG to discuss incentive issues and up-dates intended for the Program Implementation Plan to support gas savings through the LivingWise School Program for sixth graders.

Several VCREA Board members and staff were guests at the SCE regional meeting that included a presentation by Bob Foster regarding SCE services, programs and challenges.

VCREA staff and Navigant CaLEEP project consultants met July 8th to continue work on the program which is intended to help leverage the growing regional interest in energy efficiency associated with new construction and “green” building design.  A stakeholders meeting will be held in August to further the program goals.

The KEMA BEST Program has been well received in the region, now reaching over 468 small businesses, primarily offering direct installation lighting services.

VCREA has also been contacted by representatives of the Enhanced Automation Initiative that provides financial incentive for energy efficiency for large business customers.   These programs allow VCERC to provide more resource information to local businesses.

- Changes to Subcontractors or Staffing

None

- Additional Items

Supporting Documentation

- Marketing Materials

Attached

- Point of Purchase Program Documentation
None

- Free Measure Distribution Documentation
None

- Upstream Incentive Documentation
None

- Training Documentation

| Table E - Training Documentation for July |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Brief Description of Training | Delivery Method | Materials List | Attendees |  | Training |  |
|  |  |  | Type | Number | Date | Location |
| EE Public Policy Training | Workshop |  | Public | 27 | 7/7/05 | Ventura |

- Trade Show and Public Events

| Table F.1 - Trade Show and Public Events for July |  |  |  |
| --- | --- | --- | --- |
| Event Description | Number of Participants | Event Location | Date |
| None |  |  |  |

| Table F.2 – Trade Show and Public Events, Planned for August |  |  |
| --- | --- | --- |
| Event Description | Event |  |
|  | Location | Date |
| Ventura County Fair | Ventura | 8/3 – 8/14/05 |