| Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Name: | Statewide Residential Multifamily Energy Efficiency Rebates |
| IOU Service Area: | SCG |
| Program Number: | 1246-04 |
| Program Type: | IOU Statewide Program |
| Month | September-04 |

- Program Status

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | Sep-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $4,624,768 | $264,941 | 6% | $4,057,887 | 88% |  |  | $4,057,887 | 88% | $566,881 |
| Admin | $522,750 | $1,093 | 0% | $297,008 | 57% |  |  | $297,008 | 57% | $225,742 |
| Marketing | $455,360 | $21,047 | 5% | $485,751 | 107% |  |  | $485,751 | 107% | -$30,391 |
| DI | $3,575,580 | $242,801 | 7% | $3,275,128 | 92% |  |  | $3,275,128 | 92% | $300,452 |
| EM&V | $71,078 |  |  |  |  |  |  |  |  | $71,078 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

| Energy Effects | Goals | Sep-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 791 |  |  | 117 | 15% |  |  | 117 | 15% | 674 |
| Annual kWh | 13,141,337 | 1,065,024 | 8% | 13,862,508 | 105% |  |  | 13,862,508 | 105% | -721,170 |
| Lifecyc kWh | 162,081,837 | 12,780,122 | 8% | 166,988,372 | 103% |  |  | 166,988,372 | 103% | -4,906,535 |
| Annual Therms | 1,885,379 | 138,437 | 7% | 1,687,033 | 89% |  |  | 1,687,033 | 89% | 198,346 |
| Lifecyc Therms | 21,317,206 | 1,691,355 | 8% | 19,413,180 | 91% |  |  | 19,413,180 | 91% | 1,904,026 |

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder.

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Performance Goals | Goals | September-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Hard to Reach goal is that 29% of rebate applications come from HTR zip codes | 29% | 30% | 103% |  |  |  |  | 30% | 103% | 0 |

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative

- The Multifamily Rebate Program remained closed in August

- Provided information to 54 customers / contractors who inquired about program and / or rebate status.

    - Marketing

- Notification sent out to 351 retailers in SCG’s service territory announcing the re-opening of the 2005 SF rebate program.

- New applications to be re-printed and distributed early October.

- Participated in the 2005 Energy Star Partners Conference in Saratoga Springs, NY.  Met with Energy Star manufacturers and retailers to discuss potential coop opportunities for 2006.

- Met with Viewtech Financial Services to discuss opportunities to provide online rebates for SCG in 2006.

    - Direct Implementation

      - For Audits and Site Surveys  - Not Applicable

      - For Direct Installations, Rebates, Equipment Maintenance and Optimization

- Total number of customers sites served

- Summary of type and number of measures installed or repaired.

| Measure Type | Measure Qty |
| --- | --- |
| Appliances | 22 |
| HVAC - Controls | 3,134 |
| Water Heating - Systems | 51 |
| Water Heating - Controls | 24 |
| Grand Total | 3,231 |

      - Discrepancies between total month's rebates paid may differ from the total calculated in the workbook due to the following reasons:

(1) There may be a lag in customer rebate payments, particularly those approved for payments towards the end of the month, due to the processing of check payments;

(2) SoCalGas pays an approved customer application either the prescribed rebates/incentives or the cost shown on the customer invoice, whichever is lower;

    - EM&V

- Program Challenges 
None

- Customer Disputes 
None

- Compliance Items 
SoCalGas filed an updated Program Implementation Plan for this program on December 13, 2004 per  Decision 04-12-019, issued on December 2, 2004.

- Coordination Activities 
 Coordination Activities are detailed in the revised PIP

- Changes to Subcontractors or Staffing - 
None

- Additional Items - None

Supporting Documentation

- Marketing Materials – 
None in August

- Point of Purchase Program Documentation – 
This program does not have point of purchase activities.

- Free Measure Distribution Documentation- 
This program does not distribute free measures

- Upstream Incentive Documentation – 
This program is not an upstream incentive program.

- Training Documentation – 
There were no training activities this month

- Trade Shows and Public Event

None in August