| Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Name: | Statewide Nonresidential Express Efficiency |
| IOU Service Area: | SCG |
| Program Number: | 1251-04 |
| Program Type: | IOU Statewide Program |
| Month | September-05 |

- Program Status

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget  in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | Sep-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $8,448,858 | -$974 | 0% | $6,692,022 | 79% |  |  | $6,692,022 | 79% | $1,756,836 |
| Admin | $932,720 | $24,073 | 3% | $782,837 | 84% |  |  | $782,837 | 84% | $149,883 |
| Marketing | $2,594,625 | $79,236 | 3% | $1,326,087 | 51% |  |  | $1,326,087 | 51% | $1,268,538 |
| DI | $4,740,513 | -$104,283 | -2% | $4,582,778 | 97% |  |  | $4,582,778 | 97% | $157,735 |
| EM&V | $181,000 |  |  | $320 | 0% |  |  | $320 | 0% | $180,680 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Energy Effects | Goals | Sep-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW |  |  | NA |  | NA |  | NA |  | NA |  |
| Annual kWh | 34,531 |  |  | 108,930 | 315% |  |  | 108,930 | 315% | -74,399 |
| Lifecyc kWh | 379,843 |  |  | 1,198,233 | 315% |  |  | 1,198,233 | 315% | -818,389 |
| Annual Therms | 6,214,018 | 430,908 | 7% | 5,431,826 | 87% |  |  | 5,431,826 | 87% | 782,192 |
| Lifecyc Therms | 79,538,480 | 5,073,494 | 6% | 63,193,441 | 79% |  |  | 63,193,441 | 79% | 16,345,040 |

Note: Energy savings have not been updated for April pending final review of savings assumptions.

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Performance Goals | Goals | Sept 05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Hard to Reach | 43% | 49% | 113% | 70% | 162% | 0 | 0 | 113% | 162% |  |

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative

Regular monthly administrative activities include but are not limited to the following activities: continued refining of the customer participation process and program design, review of customer participation and market activity, coordination with participating retailers, vendors, and manufacturers and other market participants, contract management, responding to customer inquiries and concerns, planning of future training events, and managing of program budgets and expenditures.

This month, additional activities included:

- C&I Customer Programs Staff participated in the CEC Industrial Workshop held at the ERC on Sept. 29th.  The meeting was also attended by members of the California Energy Commission and So Cal Edison.  The purpose of this meeting was to help uncover additional EE opportunities within the industrial sector.

- SCG participated in a Statewide Express Efficiency phone conference on Sept. 28th.  The purpose of this meeting was to address the needs of the statewide agricultural customers..

- SCG EE staff attended the SCG Industrial Service Tech Conference held at the ERC on Sept. 13th and 14th, and delivered DSM program updates to the approximately 50 attending field technicians.

- SCG EE staff provided Express Efficiency and other DSM program training to six new Commercial Service Technicians completing their training at SCG’s Pico Rivera training facility on Sept. 19th.

    - Marketing

- SCG attended the PWS Coin Laundry Show on Sept. 17th, in the City of Industry. SCG developed a flyer highlighting Express Efficiency measures and other DSM opportunities, which were distributed with PWS’ mass mailing advertising to 3,800 customers.  Express Efficiency and other DSM program literature and applications were distributed to the approximately 600 attendees.

- SCG provided energy efficiency collateral including Express Efficiency rebate applications, brochures, and other DSM program literature, for the Housing Authority - Bakersfield outreach event held on September 22.

- On September 29th SCG participated in the annual Access L.A City Hall event.  Approximately 50 business owners stopped at the SCG table, where they were informed of Express Efficiency and other DSM programs.

- SCG had a booth at the North American Foodservice Equipment Manufacturers(NAFEM) convention on Sept. 22nd -25th.  SCG provided Statewide Express Efficiency  and other DSM Program information, applications and brochures to the thousands of food service representatives and equipment manufacturers in attendance.

- Developed an Express Efficiency bill insert for delivery in all October C&I customer bills.

- A total of six executive VIP breakfasts are scheduled between 10/11 and 10/26.  Rick Morrow, SCG VP, and the DSM Energy Efficiency program staff will provide executive level presentations providing business leaders/owners with information on The Gas Company's energy efficiency programs and tools to assist them in planning their business strategy for managing increased energy costs.  The Express Efficiency presentation will focus on the many benefits of energy efficiency, including reduced costs, cleaner air and competitive advantages.  The Gas Company will emphasize that energy efficiency is "here to stay," and the company can help its business customers develop a successful long-term EE strategy.  Business leaders will be  briefed on EE programs that will be  available to non-core customers in 2006, significant EE initiatives for C&I, and more flexible incentives for long-term EE planning.

- SCG distributed 262 Express Efficiency Rebate applications in Sept.  There were 48 other pieces of Express Efficiency collateral distributed directly to customers by field personnel.  Additional applications and collateral were distributed at additional events, through vendors, and from the internet

    - Direct Implementation

      - For Audits and Site Surveys  - Not applicable

      - For Direct Installations, Rebates, Equipment Maintenance and Optimization  -

- Total number of customers sites served.

- Summary of type and number of measures installed or repaired

| Measure Type | Measure Qty |
| --- | --- |
| Appliances | 0 |
| Building Shell - Insulation | 0 |
| Nonresidential - Custom End Use | 0 |
| Water Heating - Systems | 0 |
| Grand Total | 0 |

      - Discrepancies between total month's rebates paid may differ from the total calculated in the workbook  due to the following reasons:

(1) There may be a lag in  customer rebate payments, particularly those approved for payments towards the end of the month, due to the processing of check payments;

(2) SoCalGas pays an approved customer application either the prescribed rebates/incentives or the cost shown on the customer invoice, whichever is lower;

    - EM&V

- Program Challenges 
None

- Customer Disputes 
None

- Compliance Items

SoCalGas filed an updated Program Implementation Plan for this program on December 13, 2004 per Decision 04-12-019, issued on December 2, 2004.

- Coordination Activities

Coordination activities are detailed in the revised PIP.

- Changes to Subcontractors or Staffing

None

- Additional Items

None

Supporting Documentation

- Marketing Materials –

None this month.

- Point of Purchase Program Documentation –
This program does not have point of purchase activities.

- Free Measure Distribution Documentation – 
This program does not distribute free measures.

- Upstream Incentive Documentation – 
This program is not an upstream incentive program.

- Training Documentation – 
None this month.

- Trade Shows and Public Events –

- PWS Coin Laundry Show on Sept. 17th, in the City of Industry

- Housing Authority - Bakersfield outreach event Sept. 22nd, Bakersfield

- Access L.A City Hall September 29th, downtown LA

- North American Foodservice Equipment Manufacturers (NAFEM) show at the Anaheim Convention Center on Sept. 22nd-25th