| Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Name: | Local Nonresidential Financial Incentives Program |
| IOU Service Area: | SCG |
| Program Number: | 1260-04 |
| Program Type: | IOU Local Program |
| Month | November-05 |

- Program Status

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget  in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | Nov-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $4,936,084 | $380,872 | 8% | $4,708,248 | 95% |  |  | $4,708,248 | 95% | $227,836 |
| Admin | $1,057,645 | $108,567 | 10% | $818,780 | 77% |  |  | $818,780 | 77% | $238,865 |
| Marketing | $228,150 |  |  | $155,944 | 68% |  |  | $155,944 | 68% | $72,206 |
| DI | $3,460,079 | $261,283 | 8% | $3,674,645 | 106% |  |  | $3,674,645 | 106% | -$214,566 |
| EM&V | $190,210 | $11,022 | 6% | $58,879 | 31% |  |  | $58,879 | 31% | $131,331 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Energy Effects | Goals | Nov-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW |  |  | NA |  | NA |  | NA |  | NA |  |
| Annual kWh |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc kWh |  |  | NA |  | NA |  | NA |  | NA |  |
| Annual Therms | 3,019,954 | 315,786 | 10% | 3,776,377 | 125% |  |  | 3,776,377 | 125% | -756,423 |
| Lifecyc Therms | 48,742,088 | 4,377,161 | 9% | 63,088,564 | 129% |  |  | 63,088,564 | 129% | -14,346,476 |

Note: Energy savings have not been updated for April pending final review of savings assumptions.

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

This program does not have performance goals.

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative

Regular monthly administrative activities include but are not limited to the following activities: continued refining of the customer participation process and program design, review of customer participation and market activity, coordination with participating retailers, vendors, and manufacturers and other market participants, contract management, responding to customer inquiries and concerns, planning of future training events, and managing of program budgets and expenditures.

This month, additional activities included:

- The transfer of $400,000 from the SCG Statewide Express Efficiency Program to the SCG Non Residential Financial Incentive Program (NRFIP) was approved in November.  The transfer of funds was approved to reopen NRFIP which had depleted it’s available funding.  Based on the additional funding level and additional therm savings goal approved for the 2005 Express Efficiency Program during the Winter 2005 filing, the SCG NRFIP program will assume an additional 656,000 in therm savings associated with the $400,000 in incentive funding.  The SCG Express Efficiency Program will have it’s overall goal reduced by 656,000 therms.

    - Marketing

- SCG attended the "Greening Event" (Environmental Event) at the Museum of Tolerance on November 10, 2005 in the City of Los Angeles. Approximately, 100 customers attended the event .  SCG provided an information table where customers received energy efficiency information such as Natural Gas Prices Update, Express NRFIP Applications, other DSM Program literature, and a list of  the 2006-2008 energy efficiency programs.

- SCG attended the IHACI Show on November 16, 2005, at the Pasadena Convention Center in the City of Pasadena.  Approximately 2500 contractors attended the show and approximately.  SCG provided a booth where customers received information on Education & Training at the Energy Resource Center in Downey,  NRFIP Applications, and other DSM information and collateral material were distributed to the contractors.

- SCG met with eight (8) Director of Engineers at the Anaheim Hilton on November 18, 2005 in the City of Anaheim.  NRFIP Program, Natural Gas Prices and other DSM programs such as Savings by Design, were discussed with the attendees.

- SCG distributed 134 Commercial Food Service Rebate applications in Sept.  There were 130 other pieces of NRFIP collateral distributed directly to customers by field personnel.  Additional applications and collateral were distributed at additional events, through vendors, and from the internet

    - Direct Implementation

      - For Audits and Site Surveys  - Not applicable

      - For Direct Installations, Rebates, Equipment Maintenance and Optimization  -

- Total number of customers sites served

- Summary of type and number of measures installed or repaired

| Measure Type | Qty |
| --- | --- |
| Nonresidential - Custom End Use | 109,712 |
| Nonresidential - Food Service & Processing | 34,618 |
| Grand Total | 140,112 |

      - Discrepancies between total month's rebates paid may differ from the total calculated in the workbook  due to the following reasons:

(1) There may be a lag in  customer rebate payments, particularly those approved for payments towards the end of the month, due to the processing of check payments;

(2) SoCalGas pays an approved customer application either the prescribed rebates/incentives or the cost shown on the customer invoice, whichever is lower.

    - EM&V

- Program Challenges 
None

- Customer Disputes 
None

- Compliance Items

SoCalGas filed an updated Program Implementation Plan for this program on December 13, 2004 per Decision 04-12-019, issued on December 2, 2004.

- Coordination Activities

Coordination activities are detailed in the revised PIP.

- Changes to Subcontractors or Staffing

None

- Additional Items

None

Supporting Documentation

- Marketing Materials –

- Business News “email blast” sent to subscribed customers in November

- 2005 Energy Efficiency Rebates and Services for Businesses – Program Sheets

- High Gas Rate letter sent to all C&I customers Nov. 3rd.Point of Purchase Program Documentation –
This program does not have point of purchase activities.

- Free Measure Distribution Documentation – 
This program does not distribute free measures.

- Upstream Incentive Documentation – 
This program is not an upstream incentive program.

- Training Documentation – 
This program does not have training activities.

- Trade Shows and Public Events –

- "Greening Event" (Environmental Event) at the Museum of Tolerance on November 10, 2005 in the City of Los Angeles

- IHACI Show on November 16, 2005, at the Pasadena Convention Center in the City of Pasadena.

- Director of Engineers Meeting at the Anaheim Hilton on November 18, 2005 in the City of Anaheim