| Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Name: | Statewide Residential Single Family Home Energy Efficiency Rebate |
| IOU Service Area: | SCG |
| Program Number: | 1220-04 |
| Program Type: | IOU Statewide Program |
| Month | February-05 |

- Program Status

| Budget and Expenditures | Budget | Feb-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $12,145,090 | $255,779 | 2% | $4,924,627 | 41% |  |  | $4,924,627 | 41% | $7,220,463 |
| Admin | $1,432,400 | $33,659 | 2% | $447,567 | 31% |  |  | $447,567 | 31% | $984,833 |
| Marketing | $2,174,790 | $71,586 | 3% | $378,470 | 17% |  |  | $378,470 | 17% | $1,796,320 |
| DI | $8,368,900 | $150,534 | 2% | $4,098,590 | 49% |  |  | $4,098,590 | 49% | $4,270,310 |
| EM&V | $169,000 |  |  |  |  |  |  |  |  | $169,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

| Energy Effects | Goals | Feb-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 4,250 | 76 | 2% | 1,056 | 25% |  |  | 1,056 | 25% | 3,193 |
| Annual kWh | 10,766,576 | 159,487 | 1% | 4,307,204 | 40% |  |  | 4,307,204 | 40% | 6,459,372 |
| Lifecyc kWh | 157,409,229 | 2,389,211 | 2% | 55,754,184 | 35% |  |  | 55,754,184 | 35% | 101,655,045 |
| Annual Therms | 4,736,076 | 69,800 | 1% | 2,151,783 | 45% |  |  | 2,151,783 | 45% | 2,584,293 |
| Lifecyc Therms | 63,299,167 | 942,731 | 1% | 25,865,186 | 41% |  |  | 25,865,186 | 41% | 37,433,981 |

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Performance Goals | Goals | February -05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Hard to Reach goal is that 23% of rebate applications come from HTR zip codes | 23% | 28% | 121% |  |  |  |  | 28% | 121% |  |

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative  - 
Participated in three monthly calls with CA statewide Single Family team to discuss the revision of the customer application for 2005.

    - Marketing

    - SCG February/March newsletter article sent out to all SCG customers promoting SCG’s 2005 SF Rebate program.

    - Hispanic advertising campaign launched in February promoting the 2005 SCG SF Rebate program to all Spanish speaking customers.

    - Twenty second web commercials launched on KCBS and KCAL’s web site promoting SCG’s SF Rebate program.  Web commercials are scheduled to run for 6 weeks.

    - Participated in Energy Star collaborative meetings with various manufacturers of energy efficient Energy Star appliances.

    - Direct Implementation

      - For Audits and Site Surveys :N/A

      - For Direct Installations, Rebates, Equipment Maintenance and Optimization  -

- Total number of customers sites served, 172

- Summary of type and number of measures installed or repaired

| Measure Type | Measure Qty |
| --- | --- |
| Appliances | 1,459 |
| Building Shell - Insulation | 208,093 |
| HVAC - Controls | 179 |
| HVAC - Heating Systems | 82 |
| Water Heating - Systems | 103 |
| Grand Total | 209,916 |

      - Discrepancies between total month's rebates paid may differ from the total calculated in the workbook due to the following reasons:

(1) There may be a lag in customer rebate payments, particularly those approved for payments towards the end of the month, due to the processing of check payments;

(2) SoCalGas pays an approved customer application either the prescribed rebates/incentives or the cost shown on the customer invoice, whichever is lower;

    - EM&V

- Program Challenges 
None

- Customer Disputes 
None

- Compliance - SoCalGas filed an updated Program Implementation Plan for this program on December 13, 2004 per  Decision 04-12-019, issued on December 2, 2004.

- Coordination Activities
Coordination Activities are detailed in the revised PIP

- Changes to Subcontractors or Staffing – Program Manager Assignment has changed

- Additional Items-None

Supporting Documentation

- Marketing Materials – 
None this month

- Point of Purchase Program Documentation – 
None this month

- Free Measure Distribution Documentation-  
This program does not distribute free measures

- Upstream Incentive Documentation – 
This program is not an upstream incentive program.

- Training Documentation – 
None this month

- Trade Shows and Public Events – 
None this month