| Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Name: | Statewide Residential Single Family Home Energy Efficiency Rebate |
| IOU Service Area: | SCG |
| Program Number: | 1220-04 |
| Program Type: | IOU Statewide Program |
| Month | March-05 |

- Program Status

| Budget and Expenditures | Budget | Mar-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $12,145,090 | $2,103,809 | 17% | $7,040,236 | 58% |  |  | $7,040,236 | 58% | $5,104,854 |
| Admin | $1,432,400 | $76,501 | 5% | $535,868 | 37% |  |  | $535,868 | 37% | $896,532 |
| Marketing | $2,174,790 | $1,041,705 | 48% | $1,420,175 | 65% |  |  | $1,420,175 | 65% | $754,615 |
| DI | $8,368,900 | $985,603 | 12% | $5,084,193 | 61% |  |  | $5,084,193 | 61% | $3,284,707 |
| EM&V | $169,000 |  |  |  |  |  |  |  |  | $169,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

| Energy Effects | Goals | Mar-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 4,250 | 762 | 18% | 1,818 | 43% |  |  | 1,818 | 43% | 2,431 |
| Annual kWh | 10,766,576 | 1,503,631 | 14% | 5,810,835 | 54% |  |  | 5,810,835 | 54% | 4,955,741 |
| Lifecyc kWh | 157,409,229 | 23,276,028 | 15% | 79,030,212 | 50% |  |  | 79,030,212 | 50% | 78,379,017 |
| Annual Therms | 4,736,076 | 646,615 | 14% | 2,798,397 | 59% |  |  | 2,798,397 | 59% | 1,937,679 |
| Lifecyc Therms | 63,299,167 | 9,071,586 | 14% | 34,936,772 | 55% |  |  | 34,936,772 | 55% | 28,362,395 |

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Performance Goals | Goals | March -05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Hard to Reach goal is that 23% of rebate applications come from HTR zip codes | 23% | 28% | 121% |  |  |  |  | 28% | 121% |  |

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative  - 
Participated in three monthly calls with CA statewide Single Family team to discuss the revision of the customer application for 2005.

    - Marketing

    - Third party retail management consultant completed visits to 351 large and small retail establishments distributing over 35,000 SF rebate applications.

    - .

    - Continued participation in Energy Star collaborative meetings with various manufacturers of energy efficient Energy Star appliances.

    - Direct Implementation

      - For Audits and Site Surveys :N/A

      - For Direct Installations, Rebates, Equipment Maintenance and Optimization  -

- Total number of customers sites served

- Summary of type and number of measures installed or repaired

| Measure Type | Measure Qty |
| --- | --- |
| Appliances | 6,001 |
| Building Shell - Insulation | 2,091,487 |
| HVAC - Controls | 3,326 |
| HVAC - Heating Systems | 792 |
| Water Heating - Systems | 1,602 |
| Grand Total | 2,103,208 |

      - Discrepancies between total month's rebates paid may differ from the total calculated in the workbook due to the following reasons:

(1) There may be a lag in customer rebate payments, particularly those approved for payments towards the end of the month, due to the processing of check payments;

(2) SoCalGas pays an approved customer application either the prescribed rebates/incentives or the cost shown on the customer invoice, whichever is lower;

    - EM&V

- Program Challenges 
None

- Customer Disputes 
None

- Compliance - SoCalGas filed an updated Program Implementation Plan for this program on December 13, 2004 per  Decision 04-12-019, issued on December 2, 2004.

- Coordination Activities
Coordination Activities are detailed in the revised PIP

- Changes to Subcontractors or Staffing – Program Manager Assignment has changed

- Additional Items-None

Supporting Documentation

- Marketing Materials – 
None this month

- Point of Purchase Program Documentation – 
None this month

- Free Measure Distribution Documentation-  
This program does not distribute free measures

- Upstream Incentive Documentation – 
This program is not an upstream incentive program.

- Training Documentation – 
None this month

- Trade Shows and Public Events – 
None this month