| Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Name: | Statewide Residential New Construction California Energy Star New Homes |
| IOU Service Area: | SCG |
| Program Number: | 1244-04 |
| Program Type: | IOU Statewide Program |
| Month | February-05 |

- Program Status

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | Feb-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $3,988,606 | $73,643 | 2% | $2,130,040 | 53% |  |  | $2,130,040 | 53% | $1,858,566 |
| Admin | $357,000 | $12,981 | 4% | $209,875 | 59% |  |  | $209,875 | 59% | $147,125 |
| Marketing | $91,000 | $14,970 | 16% | $106,510 | 117% |  |  | $106,510 | 117% | -$15,510 |
| DI | $3,412,000 | $45,692 | 1% | $1,813,655 | 53% |  |  | $1,813,655 | 53% | $1,598,345 |
| EM&V | $128,606 |  |  |  |  |  |  |  |  | $128,606 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder

| Energy Effects | Goals | Feb-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 4,595 |  |  | 3,323 | 72% |  |  | 3,323 | 72% | 1,272 |
| Annual kWh | 3,338,463 |  |  | 2,414,634 | 72% |  |  | 2,414,634 | 72% | 923,829 |
| Lifecyc kWh | 60,092,341 |  |  | 43,463,419 | 72% |  |  | 43,463,419 | 72% | 16,628,921 |
| Annual Therms | 271,352 |  |  | 220,338 | 81% |  |  | 220,338 | 81% | 51,014 |
| Lifecyc Therms | 4,884,336 |  |  | 3,966,085 | 81% |  |  | 3,966,085 | 81% | 918,251 |

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

| MEASURE / ACTIVITY NAME | UNIT DEFINITION | FINANCIAL INCENTIVE PER UNIT | UNIT GOALS | TOTAL RECORDED UNITS |
| --- | --- | --- | --- | --- |
| Single Family Inland 15% Above AB970 | Home | $500.00 | 900 | 548 |
| Multifamily 15% Above AB970 | Home | $150.00 | 6,000 | 7177 |
| Single Family Coastal 15% Above AB970 | Home | $400.00 | 0 | 0 |
| Single Family Inland 20% Above AB970 | Home | $700.00 | 500 | 0 |

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative

Regular monthly administrative activities include but are not limited to the following activities: continued refining of the customer participation process and program design, review of customer participation and market activity, coordination with participating retailers, vendors, and manufacturers and other market participants, contract management, responding to customer inquiries and concerns, planning of future training events, and managing of program budgets and expenditures.

    - Marketing

Marketing outreach continued via direct contact with builders, architects and energy analysts.

    - Direct Implementation

The following courses were offered during February.

MicroPas Residential Energy Compliance
This seminar is designed to provide detailed training on use of the California Energy Commission approved MicroPas program for use with the residential energy standards. Emphasis will be placed on energy code requirements and obtaining accurate compliance results as well as plan checking compliance.
February 3, 2005County of Los Angeles Department of Public Works, Alhambra, 22 attendees representing 9 firms.

- Introduction to ACCA Manual J: Residential Load Calculation and Equipment Selection
This class instructs in methods to calculate the residential load and the infiltration load utilizing the ACCA Manual J. Instruction is given in the use of the Manual J workbook and worksheets as well as using manufacturer’s cooling capacity sheets to select equipment.  Instruction is also given in calculating the required CFM based on cooling load. This class is required before attending the Introduction to ACCA Manual D: Residential Duct Design course.
February 1, 2005, Southern California Gas Company, Chatsworth, 22 attendees representing 18 firms.

- Introduction to ACCA Manual D: Residential Duct Design
This class focuses on designing residential duct systems according to ACCA Manual D specifications using the ACCA Manual D and duct calculator. The course covers determining the system static pressure and available static pressure, calculating the total equivalent length of duct runs and friction rate and the sizing of ducts. The course also demonstrates the Wrightsoft Manual D software program
February 2, 2005, Southern California Gas Company, Chatsworth, 21 attendees representing 19 firms.

- 2005 Energy Standards Update: High Performance Ducts
This course is oriented toward builders, HVAC contractors and engineers and reviews current and proposed changes to the Residential Energy Efficiency Standards. Class topics include: high performance glazing and radiant barrier roof sheathing, duct testing and the Home Energy Rating System (HERS) verification process. Hydronic systems are reviewed including sizing and installation, water heater sizing, cooling and heating coil sizing and air flow designs for heating and cooling.
February 3, 2005, Southern California Gas Company, Chatsworth, 22 attendees representing 9 firms.

      - Audits and Site Surveys

Not applicable.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization

Not applicable.

      - Discrepancies between total month's rebates paid may differ from the total calculated in the workbook due to the following reasons:

(1) There may be a lag in  customer rebate payments, particularly those approved for payments towards the end of the month, due to the processing of check payments;

(2) SDG&E  pays an approved customer application either the prescribed rebates/incentives or the cost shown on the customer invoice, whichever is lower.

    - EM&V

- Program Challenges 
None.

- Customer Disputes 
None.

- Compliance Items 
None.

- Coordination Activities
Coordination activities are described in the PIP.

- Changes to Subcontractors or Staffing 
None.

- Additional Items

None this month.

Supporting Documentation

- Marketing Materials – 
There were no new marketing materials this month.

- Point of Purchase Program Documentation –
This program does not have point of purchase activities.

- Free Measure Distribution Documentation – 
This program does not distribute free measures.

- Upstream Incentive Documentation – 
This program is not an upstream incentive program.

- Training Documentation – 
No new materials were distributed at training sessions in December.

- Trade Shows and Public Events – 
None this month.