| Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Name: | Statewide Nonresidential Express Efficiency |
| IOU Service Area: | SCG |
| Program Number: | 1251-04 |
| Program Type: | IOU Statewide Program |
| Month | January-05 |

- Program Status

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget  in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | Jan-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $8,448,858 | $585,864 | 7% | $3,784,156 | 45% |  |  | $3,784,156 | 45% | $4,664,702 |
| Admin | $932,720 | $12,866 | 1% | $323,927 | 35% |  |  | $323,927 | 35% | $608,793 |
| Marketing | $2,594,625 | $41,064 | 2% | $844,160 | 33% |  |  | $844,160 | 33% | $1,750,465 |
| DI | $4,740,513 | $531,934 | 11% | $2,616,069 | 55% |  |  | $2,616,069 | 55% | $2,124,444 |
| EM&V | $181,000 |  |  |  |  |  |  |  |  | $181,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Energy Effects | Goals | Jan-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW |  |  | NA |  | NA |  | NA |  | NA |  |
| Annual kWh | 34,531 | 252,392 | 731% | 1,403,536 | 4065% |  |  | 1,403,536 | 4065% | -1,369,005 |
| Lifecyc kWh | 379,843 | 2,776,308 | 731% | 15,438,900 | 4065% |  |  | 15,438,900 | 4065% | -15,059,056 |
| Annual Therms | 6,214,018 | 1,358,576 | 22% | 7,075,310 | 114% |  |  | 7,075,310 | 114% | -861,293 |
| Lifecyc Therms | 79,538,480 | 14,828,741 | 19% | 78,595,546 | 99% |  |  | 78,595,546 | 99% | 942,934 |

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Performance Goals | Goals | Jan-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Hard to Reach | 43% | 20% | 47% | 28% | 69% | 0 | 0 | 28% | 69% | 15% |

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative

Regular monthly administrative activities include but are not limited to the following activities: continued refining of the customer participation process and program design, review of customer participation and market activity, coordination with participating retailers, vendors, and manufacturers and other market participants, contract management, responding to customer inquiries and concerns, planning of future training events, and managing of program budgets and expenditures.

This month, additional activities included:

- SCG finalized the 2005 Statewide Express Efficiency Rebate Application.  A downloadable version was made available to the field and was posted online for customers on January 14th.  Printed versions will be available in the near future.

- Work continued on finalizing the PY2005 EE program planning, EE marketing outreach planning, and the EE communication plan.

    - Marketing

- Three DSM update training meetings were held for Pacific Region, Orange Coast Region, Northern Region, and the Industrial C&I Services groups during January.  Forty-six Account Executives and their Managers were provided Express Efficiency and other DSM PY2005 program updates and information.

- SCG finalized four new DSM program brochures.  These include a Commercial Food Service Brochure, Laundry brochure, Pool Heater brochure, and a new tri-fold generic brochure simplifying the rebate and incentive procedures for the various programs .  These brochures should be available in February.

- An Express Efficiency and additional DSM rebate/incentive program bill insert was finalized for insertion in February C&I customer bills.

- SCG provided a DSM program presentation, and also sat on a panel of utility and municipality representatives knowledgeable in energy efficiency programs for the Association of Energy Engineers, Thursday, January 13th, at the Energy Resource Center in Downey, California.  There were approximately 65 attendees.  Express Efficiency and additional DSM literature, applications, and program material were distributed.

- SCG attended the “ Century Laundry” coin operated laundry equipment warehouse Grand Opening in Orange, CA on January, 29th.  Express Efficiency and additional DSM literature and applications were distributed to the approximately 40 customers in attendance.

- SCG attended the  “Sterling Equipment” coin operated laundry equipment show in Stanton, CA on January 29th  .  Express Efficiency and additional DSM literature and applications were distributed to the approximately 100 customers in attendance.

- SCG distributed 270 Express Efficiency Rebate applications and 41 other pieces of marketing collateral directly to their customers.  Additional applications and collateral were distributed at events, through vendors, and from the internet.

    - Direct Implementation

      - For Audits and Site Surveys  - Not applicable

      - For Direct Installations, Rebates, Equipment Maintenance and Optimization  -

- Total number of customers sites served, 654.

- Summary of type and number of measures installed or repaired

| Measure Type | Measure Qty |
| --- | --- |
| Appliances | 209 |
| Building Shell - Insulation | 648,180 |
| HVAC - Controls | 804 |
| Nonresidential - Custom End Use | 855,612 |
| Water Heating - Systems | 40,911 |
| Grand Total | 1,545,716 |

      - Discrepancies between total month's rebates paid may differ from the total calculated in the workbook  due to the following reasons:

(1) There may be a lag in  customer rebate payments, particularly those approved for payments towards the end of the month, due to the processing of check payments;

(2) SoCalGas pays an approved customer application either the prescribed rebates/incentives or the cost shown on the customer invoice, whichever is lower;

    - EM&V

- Program Challenges 
None

- Customer Disputes 
None

- Compliance Items

SoCalGas filed an updated Program Implementation Plan for this program on December 13, 2004 per Decision 04-12-019, issued on December 2, 2004.

- Coordination Activities

Coordination activities are detailed in the revised PIP.

- Changes to Subcontractors or Staffing

None

- Additional Items

None

Supporting Documentation

- Marketing Materials –

2005 Express Efficiency Rebate Application Form – program application that lists the measures and rebate amounts

- Point of Purchase Program Documentation –
This program does not have point of purchase activities.

- Free Measure Distribution Documentation – 
This program does not distribute free measures.

- Upstream Incentive Documentation – 
This program is not an upstream incentive program.

- Training Documentation – 
None this month.

- Trade Shows and Public Events –

- Association of Energy Engineers, Thursday, January 13th, at the Energy Resource Center in Downey, California.

- Century Laundry coin operated laundry equipment warehouse Grand Opening in Orange, CA on January, 29th.

- Sterling Equipment coin operated laundry equipment show in Stanton, CA on January 29th.