| Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Name: | Statewide Nonresidential Express Efficiency |
| IOU Service Area: | SCG |
| Program Number: | 1251-04 |
| Program Type: | IOU Statewide Program |
| Month | February-05 |

- Program Status

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget  in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | Feb-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $8,448,858 | $295,006 | 3% | $4,079,162 | 48% |  |  | $4,079,162 | 48% | $4,369,696 |
| Admin | $932,720 | $25,598 | 3% | $349,525 | 37% |  |  | $349,525 | 37% | $583,195 |
| Marketing | $2,594,625 | $59,773 | 2% | $903,933 | 35% |  |  | $903,933 | 35% | $1,690,692 |
| DI | $4,740,513 | $209,635 | 4% | $2,825,704 | 60% |  |  | $2,825,704 | 60% | $1,914,809 |
| EM&V | $181,000 |  |  |  |  |  |  |  |  | $181,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Energy Effects | Goals | Feb-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW |  |  | NA |  | NA |  | NA |  | NA |  |
| Annual kWh | 34,531 | 64,668 | 187% | 1,468,204 | 4252% |  |  | 1,468,204 | 4252% | -1,433,673 |
| Lifecyc kWh | 379,843 | 711,343 | 187% | 16,150,242 | 4252% |  |  | 16,150,242 | 4252% | -15,770,399 |
| Annual Therms | 6,214,018 | 384,785 | 6% | 7,460,095 | 120% |  |  | 7,460,095 | 120% | -1,246,078 |
| Lifecyc Therms | 79,538,480 | 3,747,818 | 5% | 82,343,363 | 104% |  |  | 82,343,363 | 104% | -2,804,883 |

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Performance Goals | Goals | Feb-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Hard to Reach | 43% | 13% | 30% | 27% | 63% | 0 | 0 | 27% | 63% | 16% |

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative

Regular monthly administrative activities include but are not limited to the following activities: continued refining of the customer participation process and program design, review of customer participation and market activity, coordination with participating retailers, vendors, and manufacturers and other market participants, contract management, responding to customer inquiries and concerns, planning of future training events, and managing of program budgets and expenditures.

This month, additional activities included:

- A DSM rebate/incentive program bill insert went into all February Commercial and Industrial customer bills.

- Printed versions of the PY2005 Express Efficiency Rebate Applications were distributed to the field in February.

- Chinese and Korean versions of the Express Efficiency Rebate applications were finalized in February, and are being reviewed for release.

- Four new DSM brochures were printed and distributed to the field in February.  These are: Commercial Food Service Brochure, Laundry brochure, Pool Heater brochure, and a new tri-fold generic brochure simplifying the rebate and incentive procedures for the various programs.

    - Marketing

- SCG provided Express Efficiency and other DSM program update training for the Inland Region C&I Services group February 7th.  Ten Account Executives and their Manager were provided PY2005 program updates and information.  This completed C&I Services initial training on the PY2005 programs.

- SCG provided Express Efficiency and other DSM program training for 37 Pacific Coast Region Commercial Service Techs, Industrial Service Techs, and supervisors at two sessions held at the Energy Resource Center in Downey on February 23rd.  NRFIP and other DSM program training was also provided for six new Commercial Service Techs during their final week of training at Pico Rivera on Feb. 14th.

- SCG had a booth at the Metal Finishers Association of Southern California’s annual supplier show case in Montebello, on Feb. 8th.  Express Efficiency and other DSM program brochures and applications were distributed to the approximately 250 attendees.

- SCG held a Vendor Mixer at the Energy Resource Center in Downey on February 17th.  Account Executives provided Express Efficiency and other DSM program training for the thirty Commercial and Industrial Vendors that were in attendance.  Program brochures, literature, and applications were distributed.

- SCG attended the Southern California Minority Business Development Council’s 36th annual Minority Business Opportunity Day (MBOD) on February 24th at the Pacific Palms Conference Resort in Industry Hills. Express Efficiency and other DSM Program literature and applications were distributed to the 500 attendees.

    - Direct Implementation

      - For Audits and Site Surveys  - Not applicable

      - For Direct Installations, Rebates, Equipment Maintenance and Optimization  -

- Total number of customers sites served, 654.

- Summary of type and number of measures installed or repaired

| Measure Type | Measure Qty |
| --- | --- |
| Appliances | 131 |
| Building Shell - Insulation | 321232 |
| Water Heating - Systems | 3848 |
| Nonresidential - Custom End Use | 10220 |
| HVAC - Controls | 206 |
| Grand Total | 335637 |

      - Discrepancies between total month's rebates paid may differ from the total calculated in the workbook  due to the following reasons:

(1) There may be a lag in  customer rebate payments, particularly those approved for payments towards the end of the month, due to the processing of check payments;

(2) SoCalGas pays an approved customer application either the prescribed rebates/incentives or the cost shown on the customer invoice, whichever is lower;

    - EM&V

- Program Challenges 
None

- Customer Disputes 
None

- Compliance Items

SoCalGas filed an updated Program Implementation Plan for this program on December 13, 2004 per Decision 04-12-019, issued on December 2, 2004.

- Coordination Activities

Coordination activities are detailed in the revised PIP.

- Changes to Subcontractors or Staffing

None

- Additional Items

None

Supporting Documentation

- Marketing Materials –

“Save with Rebates/Incentives on Energy-Efficient Laundry Equipment for Your Business” brochure

“New Rebate for 2005!  Commercial Pool Heaters”  brochure

“Rebate and Incentive Programs for Business Customers” brochure

“Cash Rebates on Commercial Food Service Equipment” brochure (includes programmable set-back thermostat rebate information for Express Efficiency Program”

“Rebate and Incentive Bill Insert” for Feb

Korean Express Efficiency Rebate application forms

Chinese Express Efficiency Rebate application forms

- Point of Purchase Program Documentation –
This program does not have point of purchase activities.

- Free Measure Distribution Documentation – 
This program does not distribute free measures.

- Upstream Incentive Documentation – 
This program is not an upstream incentive program.

- Training Documentation – 
None this month.

- Trade Shows and Public Events –

- Metal Finishers Association of Southern California’s annual supplier show case.  Montebello, CA, on Feb. 8th.

- C&I Vendor Mixer at the Energy Resource Center in Downey on February 17th.

- Southern California Minority Business Development Council’s 36th annual Minority Business Opportunity Day (MBOD) on February 24th at the Pacific Palms Conference Resort in Industry Hills