| Program Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Title: | Statewide Crosscutting Emerging Technologies |
| Program Number: | 1254-04 |
| Program Type: | IOU Statewide Program |
| Month: | January - 05 |

- Program Status

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget  in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | Jan-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $1,561,500 | $19,961 | 1% | $409,783 | 26% |  |  | $409,783 | 26% | $1,151,717 |
| Admin | $320,000 | $5,559 | 2% | $74,538 | 23% |  |  | $74,538 | 23% | $245,462 |
| Marketing | $128,000 |  |  | $50,971 | 40% |  |  | $50,971 | 40% | $77,029 |
| DI | $1,058,000 | $14,402 | 1% | $284,275 | 27% |  |  | $284,275 | 27% | $773,725 |
| EM&V | $55,500 |  |  |  |  |  |  |  |  | $55,500 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder.

Not applicable to this program.

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Other Performance Goals | Current Month’s Achievement | Cumulative Achievement | Commitments | Remainder |
| --- | --- | --- | --- | --- |
| ETCC Collaborative – 4 meetings per year | 1 | 4 | N/A | 0 |
| Project Initiation – 6 per year | 0 | 8 |  | 0 |
| ETCC database update – 1 per year | 1 | 1 |  | 0 |

  - Describe program activities and accomplishments during the month for each of the following types of activities:

  - Administrative

Regular monthly administrative activities include but are not limited to the following activities: continued refining of the program participation process and program design; review of new technologies and market activity; coordination with participating customers, vendors, and manufacturers; contract management; responding to inquiries; planning of future technology demonstrations and assessments; and managing of program budgets and expenditures.

    - Marketing

- Ongoing efforts to connect with early adopter customers through our Account Executives continue regularly to develop new prospects for demonstrations.

    - Direct Implementation

Continued support occurred for all new and ongoing performance monitoring and demonstration projects.  Those with significant activity this month included:

- The brick manufacturer (industrial CHP demonstration w/heat recovery to a kiln) has made repairs to the kiln. The Bowman microturbine system has been tested and one of the three units has a control problem. Repairs are being arranged. The kiln is expected to be relit in March or early April. Data will be gathered following resumption of brick firing.

- Installation of a heat recovered engine chiller system at a university campus is proceeding as scheduled.

- A firm involved in food processing has installed two of the AutoFlame boiler control systems. Data collection and assessment activities have begun.

Continued the process to acquire new demonstrations / assessments:

The eight assessments counted for 2004-05 thus far include: Industrial CHP assessment at a brick manufacturer, a beverage company refrigeration unit, a BCHP system at a credit union, a heat recovered engine driven air compressor system at a manufacturer of plastic containers, a thermal/solar boiler system analysis at a city pool, a new application of the FIR burner at a toxic waste processing facility, an engine-driven chiller at one of the UC’s, and a boiler control system at a food processor.

Others pending includes: a pair of condensing boilers at a commercial laundry business, and efficiency controls improvement for boilers with Alzeta burners.

Additional demonstrations/assessments that are currently being planned and negotiated include:

- An energy saving process improvement at a beverage can manufacturer involving a novel conveyor system.

      - Site Surveys

Not applicable to this program.

      - Installations and System Optimization

Not applicable to this program.

      - Discussion of Expenditure Variance

Not applicable.

    - EM&V activities

- Program Challenges
None

- Customer Disputes
None

- Compliance Items
None

- Coordination Activities

None

- Changes to Subcontractors or Staffing
None

- Additional items 
None

Supporting Documentation

- Marketing Materials – 
There were no new marketing materials this month.

- Point of Purchase Program Documentation –
This program does not have point of purchase activities.

- Free Measure Distribution Documentation – 
This program does not distribute free measures.

- Upstream Incentive Documentation – 
This program is not an upstream incentive program.

- Training Documentation – 
This program does not have training activities.

Trade Shows and Public Events –
No activity this month.