| Program Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Title: | Statewide Crosscutting Emerging Technologies |
| Program Number: | 1254-04 |
| Program Type: | IOU Statewide Program |
| Month: | December 2004 |

- Program Status

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget  in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | Dec-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $1,561,500 | $22,699 | 1% | $389,822 | 25% |  |  | $389,822 | 25% | $1,171,678 |
| Admin | $320,000 | $3,501 | 1% | $68,979 | 22% |  |  | $68,979 | 22% | $251,021 |
| Marketing | $128,000 | $10,126 | 8% | $50,971 | 40% |  |  | $50,971 | 40% | $77,029 |
| DI | $1,058,000 | $9,072 | 1% | $269,873 | 26% |  |  | $269,873 | 26% | $788,127 |
| EM&V | $55,500 |  |  |  |  |  |  |  |  | $55,500 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder.

Not applicable to this program.

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Other Performance Goals | Current Month’s Achievement | Cumulative Achievement | Commitments | Remainder |
| --- | --- | --- | --- | --- |
| ETCC Collaborative – 4 meetings per year | 1 | 4 | N/A | 0 |
| Project Initiation – 6 per year | 0 | 8 |  | 0 |
| ETCC database update – 1 per year | 1 | 1 |  | 0 |

  - Describe program activities and accomplishments during the month for each of the following types of activities:

  - Administrative

Regular monthly administrative activities include but are not limited to the following activities: continued refining of the program participation process and program design; review of new technologies and market activity; coordination with participating customers, vendors, and manufacturers; contract management; responding to inquiries; planning of future technology demonstrations and assessments; and managing of program budgets and expenditures.

By the end of the month a coordinated effort with SCE resulted in an update of the ETCC database.

    - Marketing

- Ongoing efforts to connect with early adopter customers through our Account Executives continues regularly to develop new prospects for demonstrations.

- Expenditures shown on Tab 1A of the workbook for December under “advertisement/media promotions” include approx. $10,000 in SCG annual dues paid to Portland Energy Conservation Inc. to function as administrator of CA Commissioning  Collaborative supported by all the IOU’s and the CEC among others.

    - Direct Implementation

General Note: The program has a goal of initiating at least 12 assessments during the two-year cycle (2004-05). Due to the uncertainties inherent in Emerging Technologies deployment projects (often due to changing business circumstances with customers, and the almost random nature of the occurrence of potentially interesting project opportunities), more than the targeted number of 12 will be attempted, and more than 6 in year one if good selections are found.

Continued support occurred for all new and ongoing performance monitoring and demonstration projects.  Those with significant activity this month included:

- The brick manufacturer (industrial CHP demonstration w/heat recovery to a kiln) has made repairs to the kiln. Connections to the SCE system have finally been arranged. The Bowman microturbine system is likely now to be commissioned in the 1st Q or early 2nd Q of 2005.

- Installation of a heat recovered engine chiller system at a university campus is proceeding as scheduled.

- A firm involved in food processing has purchased two of the AutoFlame boiler control systems. We have negotiated with them an agreement to assess them.

- Revisits to two customer sites with FIR (forced internal recirculation) low NOx burners in new and retrofit fire tube boilers are now scheduled for early 2005 to confirm performance.

Continued the process to acquire new demonstrations / assessments:

The eight assessments counted for 2004-05 thus far include: Industrial CHP assessment at a brick manufacturer, a beverage company refrigeration unit, a BCHP system at a credit union, a heat recovered engine driven air compressor system at a manufacturer of plastic containers, a thermal/solar boiler system analysis at a city pool, a new application of the FIR burner at a toxic waste processing facility, an engine-driven chiller at one of the UC’s, and a boiler control system at a food processor.

Additional demonstrations/assessments that are currently being planned and negotiated include:

- An energy-saving process improvement at an aluminum heat treatment facility.

- A condensing boiler for application in commercial coin-operated laundries.

- An energy saving process improvement at a beverage can manufacturer involving a novel conveyor system.

As of Dec. 31, each of these prospects is considered very likely.

      - Site Surveys

Not applicable to this program.

      - Installations and System Optimization

Not applicable to this program.

      - Discussion of Expenditure Variance

Not applicable.

    - EM&V activities

- Program Challenges
None

- Customer Disputes
None

- Compliance Items
None

- Coordination Activities

- The 4th ETCC meeting was held on Dec. 6-7 at the SCE CTAC facility and a new approach to planning PY 2006-08 was initiated.

- Changes to Subcontractors or Staffing
None

- Additional items 
None

Supporting Documentation

- Marketing Materials – 
There were no new marketing materials this month.

- Point of Purchase Program Documentation –
This program does not have point of purchase activities.

- Free Measure Distribution Documentation – 
This program does not distribute free measures.

- Upstream Incentive Documentation – 
This program is not an upstream incentive program.

- Training Documentation – 
This program does not have training activities.

Trade Shows and Public Events –
No activity this month.