| Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Name: | Local Nonresidential Financial Incentives Program |
| IOU Service Area: | SCG |
| Program Number: | 1260-04 |
| Program Type: | IOU Local Program |
| Month | January-05 |

- Program Status

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget  in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | Jan-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $4,936,084 | $186,374 | 4% | $3,205,191 | 65% |  |  | $3,205,191 | 65% | $1,730,893 |
| Admin | $1,057,645 | $45,953 | 4% | $431,234 | 41% |  |  | $431,234 | 41% | $626,411 |
| Marketing | $228,150 | $1,683 | 1% | $76,893 | 34% |  |  | $76,893 | 34% | $151,257 |
| DI | $3,460,079 | $138,375 | 4% | $2,696,701 | 78% |  |  | $2,696,701 | 78% | $763,378 |
| EM&V | $190,210 | $363 | 0% | $363 | 0% |  |  | $363 | 0% | $189,847 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Energy Effects | Goals | Jan-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW |  |  | NA |  | NA |  | NA |  | NA |  |
| Annual kWh |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc kWh |  |  | NA |  | NA |  | NA |  | NA |  |
| Annual Therms | 3,019,954 | 140,286 | 5% | 3,065,628 | 102% |  |  | 3,065,628 | 102% | -45,674 |
| Lifecyc Therms | 48,742,088 | 2,155,041 | 4% | 54,180,618 | 111% |  |  | 54,180,618 | 111% | -5,438,530 |

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

This program does not have performance goals.

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative

Regular monthly administrative activities include but are not limited to the following activities: continued refining of the customer participation process and program design, review of customer participation and market activity, coordination with participating retailers, vendors, and manufacturers and other market participants, contract management, responding to customer inquiries and concerns, planning of future training events, and managing of program budgets and expenditures.

This month, additional activities included:

- SCG finalized the 2005 Commercial Food Service Rebate Application.  A downloadable version was made available to the field and was posted online for customers on January 14, 2005.  Printed versions will be available in the near future.  Non Residential Equipment Replacement/Non Residential Energy Conservation forms were also updated and made available to the field online.

- Work continued on finalizing the PY2005 EE  program planning, EE marketing outreach planning, and the EE communication plan.

    - Marketing

- Three DSM update training meetings were held for Pacific Region, Orange Coast Region, Northern Region, and the Industrial C&I Services groups during January 05.  Forty-six Account Executives and their Managers were provided NRFIP and other DSM PY2005 program updates and information.

- SCG finalized four new DSM program brochures.  These include a Commercial Food Service Brochure, Laundry brochure, Pool Heater brochure, and a new tri-fold generic brochure simplifying the rebate and incentive procedures for the various programs .  These brochures should be available in February.

- An NRFIP and additional DSM rebate/incentive program bill insert was finalized for insertion in February C&I customer bills.

- SCG provided a DSM program presentation, and also sat on a panel of utility and municipality representatives knowledgeable in energy efficiency programs for the Association of Energy Engineers, Thursday, January 13th, at the Energy Resource Center in Downey, California.  There were approximately 65 attendees.  NRFIP and additional DSM literature, applications, and program material were distributed.

- SCG attended the “ Century Laundry” coin operated laundry equipment warehouse Grand Opening in Orange, CA on January, 29th.  NRFIP and additional DSM literature and applications were distributed to the approximately 40 customers in attendance.

- SCG attended the  “Sterling Equipment” coin operated laundry equipment show in Stanton, CA on January 29th  .  NRFIP and additional DSM literature and applications were distributed to the approximately 100 customers in attendance.

- SCG distributed 218 NRFIP Commercial Food Service Rebate applications and 71 other pieces of marketing collateral directly to customers.  Additional applications and collateral were distributed through vendors and from the internet.

    - Direct Implementation

      - For Audits and Site Surveys  - Not applicable

      - For Direct Installations, Rebates, Equipment Maintenance and Optimization  -

- Total number of customers sites served, 56

- Summary of type and number of measures installed or repaired

| Measure Type | Qty |
| --- | --- |
| HVAC - Heating Systems | (49,303) |
| Nonresidential - Custom End Use | 125,503 |
| Nonresidential - Food Service & Processing | 20,193 |
| Nonresidential - Pumping Systems | (7,184) |
| Grand Total | 89,209 |

      - Discrepancies between total month's rebates paid may differ from the total calculated in the workbook  due to the following reasons:

(1) There may be a lag in  customer rebate payments, particularly those approved for payments towards the end of the month, due to the processing of check payments;

(2) SoCalGas pays an approved customer application either the prescribed rebates/incentives or the cost shown on the customer invoice, whichever is lower.

    - EM&V

- Program Challenges 
None

- Customer Disputes 
None

- Compliance Items

SoCalGas filed an updated Program Implementation Plan for this program on December 13, 2004 per Decision 04-12-019, issued on December 2, 2004.

- Coordination Activities

Coordination activities are detailed in the revised PIP.

- Changes to Subcontractors or Staffing

None

- Additional Items

None

Supporting Documentation

- Marketing Materials –

Commercial Food Service Rebate Application form – program application that lists eligible food service measures and rebate amounts.

- Point of Purchase Program Documentation –
This program does not have point of purchase activities.

- Free Measure Distribution Documentation – 
This program does not distribute free measures.

- Upstream Incentive Documentation – 
This program is not an upstream incentive program.

- Training Documentation – 
This program does not have training activities.

- Trade Shows and Public Events –

- Association of Energy Engineers, Thursday, January 13th, at the Energy Resource Center in Downey, California.

- Century Laundry coin operated laundry equipment warehouse Grand Opening in Orange, CA on January, 29th.

- Sterling Equipment coin operated laundry equipment show in Stanton, CA on January 29th.