| Program Name: | SoCalGas On-Bill Financing |
| --- | --- |
| Program Number: | SCG3514 |
| Quarter: | Second Quarter 2006 |

- Program description

The SoCalGas On-Bill Financing program is a local program designed to facilitate the purchase and installation of qualified energy efficiency measures by customers who might otherwise not be able to act given capital constraints and administrative and time burdens to participation.

- Administrative activities

- Various internal presentations to provide an overview of the 2006-2008 On-Bill Financing Program and the support the program provides to energy efficiency rebate/incentive programs.

- Participated in discussions and meetings with the Statewide IOUs to discuss our approaches for Financing programs for the 2006-2008 program cycle.

- Marketing activities

- Sought select customers to participate in program as "beta" sites for testing purposes.

- Direct implementation activities

- Finalizing Business Requirements for Phase II that will fully automate the billing system for processing monthly loan charges.

- Program performance/program status

Program is on target

Program is exceeding expectations

Program is falling short of expectations

Explain

Milestone 1 stated that SCG would have a manual billing system in place and loans available to customers by end of first quarter 2006.  At the end of the first quarter, the manual billing system was in place.  Loans will be available to customers pending the decision from the Department of Corporations regarding SoCalGas’ status as a lender.

- Program achievements (non-resource programs only):

- Provided training to regional sales groups on the benefits for SoCalGas customers to have On Bill Financing as an option for participation

- Manual billing system implemented

- Changes in program emphasis, if any, from previous quarter (new program elements, less or more emphasis on a particular delivery strategy, program elements discontinued, measure discontinued, budget changes, etc.).

- None.

- Discussion of near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation, etc.)

- Recruit contractors to participate in the OBF Contractor Network.

- Direct mailing campaign to pre-selected customers.

- Work with Partnership programs to recruit potential OBF customers.

- Changes to staffing and staff responsibilities, if any

- None

- Changes to contracts

- None

- Changes to contractors and contractor responsibilities, if any

- None

- Number of customer complaints received

- None

- Revisions to program theory and logic model, if any

Provided in February 1, 2006 concept paper.

- None