| Program Name: | Portfolio of the Future |
| --- | --- |
| Program Number: | SCG3530 |
| Quarter: | Third Quarter 2007 |

- Program description

The Portfolio of the Future Program is comprised of multiple diverse activities designed to help SoCalGas identify and evaluate promising emerging natural gas efficiency technologies.  The Portfolio Program starts with a comprehensive scan of technologies and an evaluation of their readiness for commercialization.  The inventory of technology opportunities is then prioritized in accordance with criteria established with SoCalGas.  From this ranked inventory, a portfolio of studies and activities, including pilot demonstration projects and testing of new business models, is implemented.  The overarching goal of this program is to advance development of promising technologies for possible inclusion in SoCalGas’ energy efficiency programs.

- Administrative activities

- Conducted project management and accounting activities, including monthly budget variance reports, work planning, staffing and scheduling.

- Performed monthly billing and reporting, including updating Sempra Utilities’ DBE (Diverse Business Enterprises) compliance reporting database.

- Maintained the SMART system and reclassified travel charges from inception of contract to Administration in accordance with Chart of Accounts; entered corrected historical information into SMART system.

- Marketing activities

- None

- Direct implementation activities

- Continued to pursue partnerships to implement pilots.

- Continued refining work plans for top measures selected for pilot studies.

- Continued providing requested materials to EM&V contractor.

- Researched and pursued potential technologies and manufacturers for participation in energy efficiency demonstration projects.

Pilot A – SpyrcorTM

- Continued coordination with manufacturer and key members of SoCalGas’ industrial energy efficiency and emerging technology programs to identify potential customers interested in hosting a demonstration of the SpyroCorTM Radiant Heat Transfer System.

- Commenced discussions and coordination with SpinWorks, the manufacturer of SpyroCorTM, and a SoCalGas customer to facilitate the demonstration; discussed demonstration project with SoCalGas, SpyroCorTM and customer; secured commitment from customer to install and test system.

- Reviewed options for measuring emissions.

Pilot B – Laundry Wastewater Recycle

- Completed market research to confirm/identify key barriers to wider scale adoption of the technology measures; analyzed market survey results.

- Developed competitive technology summary and selection criteria.

- Developed PowerPoint presentation comparing technologies, discussing market assessment results, and proposing next steps; met with representatives of SoCalGas to discuss results to-date.

- Interviewed manufacturer of efficient dryer retrofit heat exchanger for potential inclusion as DSM technology.

Pilot C – Commercial Dishwashers

- Designed market study, including the generation of a survey questionnaire and site list; obtained SoCalGas customer information to identify candidate survey participants.

- Developed and pre-tested survey instrument to determine response rates and interview incentives, and refined questions based on industry feedback.

- Completed surveys for two food service establishment segments:  fast food and schools.

- Developed surveys for casual concept restaurants, independent restaurants and prisons.

Pilot D – Solar Water Heaters

- Developed plan for reviewing market in Southern California.

- Conducted secondary research to support market profiling and reviewing state and utility programs/models for successfully addressing key market barriers.

- Commenced compiling market profile.

Pilot E – Steam Traps

- Continued working with Armstrong, one of the two leading steam trap manufacturers, and its representative in Southern California, the Guy Warden Co., to plan for a field demonstration of the savings potential of this technology in California.

- Obtained available data on steam trap failure rates and monitoring system experience, and discussed most appropriate sites and clients for a pilot program.

- Began segmenting the market opportunity for the SteamEye system, with the objective of estimating potential market penetration and energy savings in SoCalGas territory.

- Worked with Armstrong to develop a spreadsheet-based model for analyzing energy savings and financial attractiveness of the SteamEye system under different scenarios.

- Initiated development of a plan for a field demonstration of the SteamEye steam trap monitoring system at a Coco-Cola bottling plant in Southern California.

Pilot F – Cold Water (Enzymatic) Detergents

- Worked with leading cold water detergent manufacturer and potential market research and monitoring subcontractors to refine pilot study approach; commenced working out product placement logistics.

- Identified potential DBE subcontractors to conduct key elements of research; developed, issued and evaluated responses to RFPs for market research and monitoring services subcontractors (MBE/WBE).

- Drafted initial questionnaire for recruited study participants (pending study refinements).

- Developed refined estimates of impacts under different temperature change-out assumptions.

- Conducted multiple discussions with SoCalGas and Proctor & Gamble regarding potential cost sharing for pilot (project start delayed, awaiting resolution of co-funding issues).

- Pilot G – Combustion Sensors and ControlsReviewing the breadth of types of sensors & controls, primarily in the industrial sector.  Some low-cost commercial/residential options are also emerging.

- Also researching costs, savings and commercial readiness of various options.

- Program performance/program status

Program is on target

Program is exceeding expectations

Program is falling short of expectations

- Program achievements (non-resource programs only):

- All six approved pilot programs have commenced and are producing information.

- Changes in program emphasis, if any, from previous quarter (new program elements, less or more emphasis on a particular delivery strategy, program elements discontinued, measure discontinued, budget changes, etc.).

- None.

- Discussion of near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation, etc.)

- Continue to conduct approved market surveys, technology demonstrations and pilot projects.

- Conduct additional research and assessment of other candidate technologies for pilot testing and obtain approval from SoCalGas to develop detailed project concepts, partnerships and work plans.

- Continue to secure partners and subcontractors.

- Develop & launch market awareness building program, including presence on the Portfolio’s sister program's website (the California Sustainability Alliance).

- Changes to staffing and staff responsibilities, if any

- None

- Changes to contracts

- None

- Changes to contractors and contractor responsibilities, if any

- None

- Number of customer complaints received

- None

- Revisions to program theory and logic model, if any, provided in February 1, 2006 concept paper.

- None