| Program Name: | Bakersfield Kern County Energy Watch |
| --- | --- |
| Program Number: | SCG 3523 |
| Quarter: | First Quarter 2008 |

- Program description

The Bakersfield and Kern County Energy Watch (BKCEW) has built on the success of the 2004-2005 partnership.  This partnership is a unique cooperative effort of Pacific Gas and Electric Company (PG&E), Southern California Edison (SCE) and Southern California Gas Company (SCG).  Partnership offerings are available to residents, businesses and municipalities of the City of Bakersfield and Kern County.  The Partnership is reducing energy use by providing energy efficiency information and direct installation of energy-efficient equipment to homeowners and small businesses in targeted areas, while continuing to retrofit municipal properties.  The 2006-2008 BKCEW has been enhanced by a new component that offers training to city building inspectors.

- Administrative activities

- The Program Manager met with the City Managers of Shafter, Taft and Arvin and the Public Works Director of the City of Wasco to discuss the Energy Watch Partnership and potential municipal facility retrofit projects.

- Monthly partnership meetings were held with City, County, investor-owned utility (IOU) and Staples Marketing representatives to discuss the partnership progress.

- Meetings were held with the IOU’s, Staples Marketing and County representatives to discuss the current program goals and the 2009 – 2011 program.

- Marketing activities

- Scheduling has begun for Energy Watch radio spots that will begin in May.

- The Energy Watch program was promoted at a Bakersfield Jam basketball game in March.

- With the move of additional funds to Staples Marketing for the Direct Install element, canvassing to the Small Business and Homebuyer customers has begun to ramp up.

- Direct implementation activities

The small business and residential direct install components are successfully meeting goals.  Staples Marketing received additional funding to continue the Small Business and Homebuyer programs.

- Program performance/program status

Program is on target

Program is exceeding expectations

X  Program is falling short of expectations (explain)

Although the partnership is falling short of its goals through the first quarter we expect to be on target by the end of 2008.  The reason for the current shortfall is that it has taken longer than projected to complete the installation of both City and County municipal projects and to move additional funding to the Direct Install program.

- Program achievements (non-resource programs only)

The following training classes were held in the first quarter.

- Residential New Construction

- Energy Management for Commercial and Small Businesses

- Changes in program emphasis, if any, from previous quarter (new program elements, less or more emphasis on a particular delivery strategy, program elements discontinued, measure discontinued, budget changes).

- Continued emphasis will be placed on working with the smaller cities throughout the County to inform them of the Energy Watch program and to assist these cities with retrofitting their municipal facilities.

- Discuss near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation).

- By working with the smaller cities, it is anticipated that several retrofit projects will be captured this year to assist the partnership in achieving their goals.

- Changes to staffing and staff responsibilities, if any

None

- Changes to contracts, if any

Additional funding for the small business and homebuyer direct install components has been provided to Staples Marketing.

- Changes to contractors and contractor responsibilities, if any

None

- Number of customer complaints received

None

- Revisions to program theory and logic model, if any

None