| Program Name: | School Targeted Living Wise |
| --- | --- |
| Program Number: | SCG3534 |
| Quarter: | First Quarter 2008 |

- Program description

The School Targeted LivingWise Program is a residential savings/education program delivered through 6th grade classes. LivingWise combines classroom learning and home retrofit/audit projects completed by students and parents.

- Administrative activities

- Renewal discussions underway, with an onsite meeting between SCG, SCE and RAP on February 27.

- Marketing activities

Schools

Outreach activities featured a combination of fax, email and telephone activities continued to pre-approved eligible schools.

Water agencies

Discussions for water agency funding have been underway with numerous potential water sponsors, including:

California American Water Company

California Water Services

Central Basin Municipal Water District

City of Alhambra

City of Downey

City of Oxnard

City of Torrance

Golden State Water, Region 1

Metropolitan Water District of Southern California (MWD)

Metropolitan Water District of Orange County (MWDOC)

Mission Springs Water District

Newhall County Water District

San Bernardino Valley Municipal Water District

Suburban Water Company

Vista Irrigation District

Ventura Regional Sanitation District
West Basin Municipal Water District

Western Municipal Water District

The following agencies agreed to fund the project:

California Water Service Company,

City of Downey

City of Torrance

Golden State Water Company Ojai District and

Mission Springs Water District

Suburban Water Company

The following agencies declined participation for the current school year.

California American Water Company

Central Basin Municipal Water District

Indian Wells/Ridgecrest

Western Municipal Water District

- Direct implementation activities

Outreach efforts targeted pre-approved schools in Q1. A combination of fax, email and telephone activities were aimed at generating rapid enrollment to maximize program participation and savings results.  119 teachers were enrolled, representing 6,262 additional households. Materials for 8,175 households were shipped during the quarter

- Program performance/program status

Program is on target

X  Program is exceeding expectations

Program is falling short of expectations

- Program achievements (non-resource programs only):

- N/A – program is a resource program

- Changes in program emphasis, if any, from previous quarter (new program elements, less or more emphasis on a particular delivery strategy, program elements discontinued, measure discontinued, budget changes, etc.).

- None.

- Discussion of near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation, etc.)

- Enrollment efforts in Q1 2008 are approaching the overall 65,000 hh program goal, and are now expected to meet this total in Q2.

- . Marketing efforts toward water agencies will identify Fall 2008 funding as soon as possible so SCG and SCE budget decisions can be made in a timely fashion.

- Changes to staffing and staff responsibilities, if any

- None

- Changes to contracts

- None.

- Changes to contractors and contractor responsibilities, if any

- None

- Number of customer complaints received

- None

- Revisions to program theory and logic model, if any

# Provided in February 1, 2006 concept paper.

- None

No other changes to report for this quarter.