QUESTION OCE4-1:

A cost break down of the failed tools at Well #1: WEZU C2C

RESPONSE OCE4-1:

The cost break down for the lost in hole bottomhole assembly costs for the WEZU C2C well are listed below.  The "Lost In Hole" or LIH charge for the Sperry equipment (Items 1, 2 and 3) is the actual uninsured tool cost to replace the lost item and the "Deductible" amount is the actual tool cost after insurance. SoCalGas obtained the Lost In Hole Limited Liability Insurance for the Sperry equipment at the beginning of the project which insures the Sperry equipment in the event their tools are lost in the well during the well drilling process.  As such, the actual cost SoCalGas paid to replace the lost Sperry equipment is the "Deductible" amount listed in Items 1, 2 and 3 below.  The remaining bottomhole drill string equipment lost in the well (Items 4 and 5) was provided by other vendors and was replaced at actual cost LIH because no LIH Limited Liability Insurance was available for that equipment.

1.  Sperry GEO Pilot:  LIH: $1,172,080 / Deductible: $703,248

2.  Sperry 6-3/4" Performance Motor:  LIH: $167,440 / Deductible: $100,464

3.  Sperry 8" Performance Motor:  LIH: $193,200 / Deductible: $115,920

Subtotal Sperry Charges (Items 1-3):   LIH: $1,532,720 / Deductible: $919,632

4.  Hole Opening Bottomhole Assembly; LIH: $184,286

5.  Miscellaneous Lost/Damaged Drill String Components (stabilizer, subs, drill collars, drill pipe, etc.): LIH: $ 96,082

Subtotal Other Non-Sperry Equipment Charges (Items 4-5):  LIH: $273,286

Grand Total of WEZU C2C Lost In Hole Tool Charges (Sperry Deductible Subtotal + Non-Sperry LIH Subtotal): $1.2 million

QUESTION OCE4-2:

The agreement, which states how the negotiations was handled between Halliburton and SoCalGas, over the failed tools. This will also include how the cost was shared.

RESPONSE OCE4-2:

Below is the email that outlines the agreed Sperry settlement related to the disputed Lost In Hole/Deductible charges for the Sperry GEOPilot listed in Response #1, Item 1 above.  Sperry agreed to a $280,000 invoice credit and an additional $250,000 future service credit in order to share the cost of the lost GEOPilot tool in the well.

# From: Mansdorfer, Jim [mailto:JMansdorfer@semprautilities.com] 
Sent: Monday, August 01, 2011 1:58 PM
To: James Melrose
Subject: RE: WEZU C2C Lost In Hole Resolution

James, to confirm our discussion:

SoCalGas will wire transfer the $703,248 for the LIH charge for the Geo-Pilot as soon as possible, hopefully by COB tomorrow. Halliburton will issue a new service invoice with a reduction (credit) of $280,000, which SoCalGas will pay as soon as possible after receiving the new invoice. Halliburton will also provide a future credit on future services of $250,000 with same terms as below, except the time period is extended to end of 2013.

Thank you for working with us on this, and I hope to continue the good relationship that I have enjoyed with Halliburton for the 30 years I have been with SoCalGas.

Jim Mansdorfer P.E.
Storage Engineering Manager 
SoCalGas Storage

QUESTION OCE4-3:

How the AFDUC was calculated in the original and current estimate and the interest rate that was used to calculate the current estimate.

RESPONSE OCE4-3:

Honor Rancho (Unbundled Storage Program)

|  | Table 1 (Original Estimates) | Table 2 (Current Estimates) | Difference (Table 2 vs. Table 1) |
| --- | --- | --- | --- |
| AFUDC | $456,181 | $2,113,883 | $1,657,702 |
| Gross Expenditures | $48,980,157 | $60,143,237 | $11,163,080 |
| Less: Cushion Gas | (11,535,183) | (6,500,000) | 5,035,183 |
| Less: AFUDC | (456,181) | (2,113,883) | (1,657,702) |
| Capital Expenditures | $36,988,793 | $51,529,354 | $14,540,561 |

AFUDC represents the financing costs of Honor Rancho capital expenses during the construction work-in-progress (CWIP) period.  The AFUDC amounts in the original estimate (Table 1) and the current estimate (Table 2) were calculated on a consistent basis.  The AFUDC rates applied in the project were determined in accordance with methodology described in the Code of Federal Regulations.   These rates were applied monthly to CWIP balances to calculate AFUDC amounts.  AFUDC calculations ended when the project was completed and all capital expenses were transferred into service.

The difference in AFUDC between the original estimate (Table 1) and the current estimate (Table 2) was caused by a combination of the following:

- Change in the capital expenditure

AFUDC is calculated by applying the AFUDC rates to the average CWIP amounts on a monthly basis.  As the updated project spending increased over the level estimated in the original filing, the average CWIP amounts also increased, increasing AFUDC slightly.

- Change in the in-service dates

In the original estimate, project expenditures were expected to start going into service at the beginning of 2010, and project completion was expected in early 2011.  The current estimate reflects a delayed schedule in the spending and in-service dates.  The project started going into service at the end of 2010, and the project was completed towards the middle of 2012.  The delayed schedule resulted in a longer CWIP period, which caused an increase in the AFUDC amounts.

- Slightly higher AFUDC rates

The AFUDC rates applied in the original estimate were based on the second quarter 2009 AFUDC rate of 8.26%.  The current estimate reflects the actual AFUDC rates from 2009 through 2012; the rate was briefly above 9% in 2012.

QUESTION OCE4-4:

I suggested a more updated estimate for Cushion Gas from the $4.50 used in November 2011.

RESPONSE OCE4-4:

# Attached is an updated gas price forecast as of October 25, 2012.

QUESTION OCE4-5:

A detailed cost breakdown of each expense item shown on Tables 1& 2 of your Testimony.  Please provide the inception and completion dates for the Honor Rancho Expansion Project.

RESPONSE OCE4-5:

Responding to Question 5 will require the generation of detailed line item reports from SAP for each value in Table 2.  Since Table 1 was an estimate, there is little if any additional information beyond what has already been provided in the work papers and the CPCN filing.

QUESTION OCE4-6:

SoCalGas stated in testimony on page 13 that, “A total of three various drilling assemblies were lost in the hole during the process of preparing and sidetracking the last 800 feet of the production hole section after the initial production casing hole section was completed”, since this occurred with the 2nd contractor, please describe how the cost for these lost tools were shared or handled?

RESPONSE OCE4-6:

The cost for the directional tools (MWD/Mud motors only) that were lost in the WEZU C7 well were covered by Lost In Hole insurance provided by Baker Hughes-INTEQ.  This insurance was handled in a similar manner as described in Question OCE4-1.  The directional tools were insured and the deductible amount was paid by SoCalGas.