QUESTION 21.1

Please update the table that SoCalGas and SDG&E provided to SCGC in Response 20.2 to reflect the data presented in the SoCalGas and SDG&E PSEP Status Report for January 2014 dated February 21, 2014 and posted on SoCalGas website on February 28, 2014.

RESPONSE 21.1

|  |  | Direct Costs* | Workpaper Identified Direct Costs ** | Variance |
| --- | --- | --- | --- | --- |
| Utility | Pipeline | Capital | O&M | Capital | O&M *** |  |
| SCG | 2000 | $ 13,603,392 | $ 55,225,360 | $ - | $ 77,980,300 | $ (9,151,548) |
|  | 2001 East | $ - | $ 169,500 | $ - | $ 8,210,850 | $ (8,041,350) |
|  | 2001 West | $ - | $ 18,314,949 | $ - | $ 47,941,100 | $ (29,626,151) |
|  | 1005 | $ 993,270 | $ - | $ - | $ 3,030,750 | $ (2,037,480) |
|  | 2003 | $ - | $ 1,455,057 | $ - | $ 18,770,600 | $ (17,315,543) |
|  | 407 | $ - | $ 2,712,000 | $ - | $ 5,125,850 | $ (2,413,850) |
|  | 406 | $ - | $ 2,324,410 | $ - | $ 12,148,100 | $ (9,823,690) |
|  | 235 West | $ - | $ 1,687,236 | $ - | $ 10,799,550 | $ (9,112,314) |
|  | 1013 | $ 900,045 | $ - | $ - | $ 2,679,350 | $ (1,779,305) |
|  | 1015 | $ 1,197,370 | $ - | $ 43,251,300 | $ - | $ (42,053,930) |
|  | 1004 | $ - | $ 6,963,512 | $ - | $ 7,087,400 | $ (123,888) |
|  | 404 | $ - | $ 9,191,315 | $ - | $ 14,011,550 | $ (4,820,235) |
|  | 44-137 | $ - | $ 4,596,162 | $ 4,340,700 | $ - | $ 255,462 |
|  | 1014 | $ 460,311 | $ - | $ 271,600 | $ - | $ 188,711 |
|  | 43-121 | $ 24,853,527 | $ - | $ 18,328,600 | $ - | $ 6,524,927 |
|  | 33-120 | $ 7,847,918 | $ - | $ 7,529,100 | $ - | $ 318,818 |
|  | 45-120 | $ 17,674,511 | $ - | $ 17,883,800 | $ - | $ (209,289) |
|  | 32-21 | $ 37,847,845 | $ - | $ 38,423,000 | $ - | $ (575,155) |
|  | 41-6000-2 | $ 5,427,371 | $ - | $ 77,995,400 | $ - | $ (72,568,029) |
|  | 36-9-09 North | $ 63,273,401 | $ 7,514,500 | $ 46,351,800 | $ - | $ 24,436,101 |
|  | 37-18-K | $ 11,862,505 | $ - | $ 13,203,900 | $ - | $ (1,341,395) |
|  | 1011 | $ - | $ 791,000 | $ 15,726,500 | $ - | $ (14,935,500) |
|  | 36-37 | $ 786,480 | $ - | $ 464,100 | $ - | $ 322,380 |
|  | 42-66-1 | $ 487,855 | $ - | $ 287,900 | $ - | $ 199,955 |
|  | 42-66-2 | $ 395,088 | $ - | $ 233,000 | $ - | $ 162,088 |
|  | 37-18 | $ 22,612,548 | $ - | $ 16,676,000 | $ - | $ 5,936,548 |
|  | 37-18-F | $ 11,185,210 | $ - | $ 8,248,700 | $ - | $ 2,936,510 |
|  | 30-18 | $ 17,332,772 | $ - | $ 17,051,600 | $ - | $ 281,172 |
|  | 44-654 | $ 800,271 | $ - | $ 164,000 | $ - | $ 636,271 |
|  | 31-09 | $ 274,590 | $ - | $ 33,765,500 | $ - | $ (33,490,910) |
|  | 37-07 | $ 16,650,161 | $ - | $ 12,278,900 | $ - | $ 4,371,261 |
|  | 45-163 | $ 6,111,356 | $ - | $ 3,605,600 | $ - | $ 2,505,756 |
|  | 41-19 | $ 491,381 | $ - | $ 289,900 | $ - | $ 201,481 |
|  | 1171LT1BP2 | $ 523,772 | $ - | $ 309,100 | $ - | $ 214,672 |
|  | 33-121 | $ 2,383,967 | $ - | $ 1,406,500 | $ 463,700 | $ 513,767 |
|  | 41-6001-2 | $ 266,183 | $ - | $ 157,100 | $ - | $ 109,083 |
|  | 36-1032 | $ 3,317,454 | $ - | $ 6,142,500 | $ 355,400 | $ (3,180,446) |
|  | 35-20-A | $ 2,533,008 | $ - | $ 5,360,200 | $ - | $ (2,827,192) |
|  | 41-30-A | $ 169,500 | $ - | $ 1,068,800 | $ - | $ (899,300) |
|  | 41-30 | $ 593,250 | $ - | $ 18,649,000 | $ - | $ (18,055,750) |
|  | 38-200 | $ 1,332,016 | $ - | $ 785,900 | $ - | $ 546,116 |
|  | 45-120XO1 | $ 317,304 | $ - | $ 187,200 | $ - | $ 130,104 |
|  | 38-501 | $ 7,297,178 | $ - | $ 5,381,400 | $ - | $ 1,915,778 |
|  | 41-80 | $ 6,615,585 | $ - | $ 3,903,000 | $ - | $ 2,712,585 |
|  | 36-1002 | $ 1,232,858 | $ - | $ 727,400 | $ - | $ 505,458 |
|  | 44-687 | $ 1,287,946 | $ - | $ 759,900 | $ - | $ 528,046 |
|  | 38-512 | $ 7,630,551 | $ - | $ 9,501,900 | $ - | $ (1,871,349) |
|  | 44-1008 | $ 6,786,238 | $ - | $ - | $ 1,406,500 | $ 5,379,738 |
|  | 41-181 | $ 254,945 | $ - | $ 150,500 | $ - | $ 104,445 |
|  | 35-20-N | $ 297,252 | $ - | $ 175,400 | $ - | $ 121,852 |
|  | 38-539 | $ 41,964,024 | $ - | $ 30,947,000 | $ - | $ 11,017,024 |
|  | 36-9-21 | $ 2,143,344 | $ - | $ 1,264,600 | $ - | $ 878,744 |
|  | 44-720 | $ 4,307,198 | $ - | $ 2,541,200 | $ - | $ 1,765,998 |
|  | 41-201 | $ 128,579 | $ - | $ - | $ - | $ 128,579 |
|  | 41-116 | $ 294,828 | $ - | $ 174,000 | $ - | $ 120,828 |
|  | 41-116BP1 | $ 257,589 | $ - | $ 152,000 | $ - | $ 105,589 |
|  | 38-523 | $ 8,221,428 | $ - | $ 6,063,000 | $ - | $ 2,158,428 |
|  | 41-6045 | $ 264,200 | $ - | $ 155,900 | $ - | $ 108,300 |
|  | Storage | $ - | $ 2,712,000 | $ - | $ 1,200,000 | $ 1,512,000 |
|  | 41-6000-2 (1) | $ 13,560,000 |  | $ 77,995,400 |  | $ (64,435,400) |
|  | 1171LT1BP2 (1) | $ 524,320 |  | $ 309,100 |  | $ 215,220 |
|  | 41-6001-2 (1) | $ 266,680 |  | $ 157,100 |  | $ 109,580 |
|  | 2000-0.18-XO2 (2) | $ 342,000 |  | $ 227,800 |  | $ 114,200 |
|  | 2000-0.18-BO (2) | $ 271,350 |  | $ 180,900 |  | $ 90,450 |
|  | 2000-0.18-XO1 (2) | $ 260,400 |  | $ 173,600 |  | $ 86,800 |
| SCG TTL |  | $ 378,714,123 | $ 113,657,001 | $ 551,378,300 | $ 211,211,000 | $ (270,218,176) |
| SDGE | 49-28 | $ 24,259,382 | $ - | $ 17,863,100 | $ - | $ 6,396,282 |
|  | 49-17 | $ 27,137,628 | $ - | $ 20,013,000 | $ - | $ 7,124,628 |
|  | 49-25 | $ 11,391,051 | $ - | $ 8,400,500 | $ - | $ 2,990,551 |
|  | 49-32 | $ 811,329 | $ - | $ 478,700 | $ - | $ 332,629 |
|  | 49-16 | $ 6,780,000 | $ - | $ 36,912,500 | $ - | $ (30,132,500) |
|  | 49-11 | $ - | $ 2,082,341 | $ 1,742,800 | $ - | $ 339,541 |
|  | 1600 | $ 11,006,200 | $ 5,516,208 | $ 9,744,633 | $ 4,320,000 | $ 2,457,775 |
|  | 49-26 | $ 13,038,347 | $ - | $ 9,591,200 | $ - | $ 3,447,147 |
|  | 49-20 | $ - | $ 127,690 | $ - | $ - | $ 127,690 |
|  | 49-14 | $ 9,669,799 | $ - | $ 7,131,200 | $ - | $ 2,538,599 |
|  | 49-15 | $ 27,580,064 | $ 600,015 | $ 20,339,300 | $ 260,000 | $ 7,580,779 |
|  | 49-22 | $ - | $ 113,000 | $ - | $ - | $ 113,000 |
|  | 49-13 | $ 16,779,849 | $ - | $ 12,374,600 | $ - | $ 4,405,249 |
| SDGE TTL |  | $ 148,453,648 | $ 8,439,255 | $ 144,591,533 | $ 4,580,000 | $ 7,721,370 |
| Sum of SCG & SDG&E |  | $ 527,167,771 | $ 122,096,255 | $ 695,969,833 | $ 215,791,000 | $ (262,496,806) |

* Current estimates are preliminary.  Estimates will be refined as project planning and engineering is completed.

** This does not include the supplemental costs.

*** For pipelines where ILI runs will be performed, those costs were also included in this column.

(1) The source of these costs is the December 2013 cashflow. The other project costs listed are from the DATA REQUEST SCGC-TCAP-PSEP-17.

(2) The source of these costs is the January 2014 cashflow. The other project costs listed are from the DATA REQUEST SCGC-TCAP-PSEP-17.