| Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Name: | Statewide Residential Home Energy Efficiency Survey |
| IOU Service Area: | SCG |
| Program Number: | 1247-04 |
| Program Type: | IOU Statewide Program |
| Month | April 05 |

- Program Status

  - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | Apr-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $628,000 | $2,033 | 0% | $377,066 | 60% |  |  | $377,066 | 60% | $250,934 |
| Admin | $158,752 | $1,969 | 1% | $64,350 | 41% |  |  | $64,350 | 41% | $94,402 |
| Marketing |  | $64 | NA | $152,922 | NA |  | NA | $152,922 | NA | -$152,922 |
| DI | $389,248 |  |  | $159,794 | 41% |  |  | $159,794 | 41% | $229,454 |
| EM&V | $80,000 |  |  |  |  |  |  |  |  | $80,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder.

Not applicable for this program.

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

Not applicable for this program.

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative
Regular monthly administrative activities include but are not limited to the following activities:  continued re-fining of the customer participation process and program design, review of customer participation and market activity, coordination with other programs, survey vendor and other market participants, contract management, responding to customer inquiries and concerns, planning of future training events, and managing of program budgets and expenditures

Updated English measures and updated measures for Spanish, Chinese, Vietnamese.  Translated Korean survey and in the process of reviewing for printing at end of 2nd quarter of 2005.  The Korean survey was created  to expand customer participation

    - Marketing –

          - Mailed out 29,479 English surveys

          - Mail approximately 200 surveys to Hard to Reach Chinese Vietnamese customers.

          - Email campaign to 1,700 customers promoting the online audit.

          - Promoted the English, Spanish and Chinese online audit in the bill newsletter

          - Participated in Pasadena Home show and distributed material regarding audit surveys to approximately 100 people.

    - Direct Implementation

      - For Audits and Site Surveys:

          - 61   On line surveys were completed in March.

          - 48   SCG In-home audits were completed in March.

          - 4,061  Mail in surveys were completed in  March

      - For Direct Installations, Rebates, Equipment Maintenance and Optimization  - Not Applicable

      - If total month’s rebates paid or direct install costs differ from total calculated in report workbook, provide discussion of difference – Not Applicable

    - EM&V

- Program Challenges 
 None

- Customer Disputes 
None

- Compliance Items 
SoCalGas filed an updated Program Implementation Plan for this program on April 12,  2004.

- Coordination Activities
Coordination Activities are detailed in the revised PIP.

- Changes to Subcontractors or Staffing -
None
Additional Items 
None

Supporting Documentation

- Marketing Materials – 
None this month

- Point of Purchase Program Documentation – 
This program does not have point of purchase activities.

- Free Measure Distribution Documentation – 
This program does not distribute free measures

- Upstream Incentive Documentation – 
This program is not an upstream incentive program.

- Training Documentation – 
This program typically does not conduct training sessions.

- Trade Shows and Public Events – 
None this month