| Program Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Title: | South Bay Cities Energy Efficiency Resource Center – PGC |
| Program Number: | 1404-04 |
| Month: | June 2005 |

- Program Status

The South Bay Energy Efficiency Resource Center (SBEERC) is a partnership with the South Bay Cities Council of Governments (SBCCOG), Southern California Edison (SCE) and Southern California Gas Co. (SCG).  The South Bay Energy Efficiency Resource Center will expand on current regional energy efficiency activities through the development of a community-based resource for energy information, training and materials to assist the member agencies, businesses and citizens to best utilize the resources available to them through the wide variety of statewide and local energy efficiency programs.  To accomplish this, this partnership will form an Energy Efficiency Resource Center, which will serve the region’s constituents as the central clearinghouse for energy efficiency information and resources.  The SBEERC will establish a small, yet capable Resource Center that will significantly increase the availability of information and resources to the citizens of South Bay region.

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | Jun-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $793,490 | $335 | 0% | $41,086 | 5% | $14,828 | 2% | $55,915 | 7% | $752,404 |
| Admin | $132,026 | $335 | 0% | $13,189 | 10% | $14,828 | 11% | $28,018 | 21% | $118,837 |
| Marketing | $23,000 |  |  | $2,023 | 9% |  |  | $2,023 | 9% | $20,977 |
| DI | $604,675 |  |  | $25,874 | 4% |  |  | $25,874 | 4% | $578,801 |
| EM&V | $33,789 |  |  |  |  |  |  |  |  | $33,789 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

Due to a lag in the time between when the partnership expends funds and when SCG is invoiced for its share of those expenditures, the reported monthly expenditures of the partnership may differ from the expenditures recorded in SCG’s accounting system.

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder.

Not applicable to this program.

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Performance Goals | Goals | June-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Conduct at least 4 training sessions for the public sector | 4 | 0 | 0% | 5 | 100% | 0 | 0% | 5 | 125% | 0 |
| Conduct at least 12 sessions for businesses | 12 | 1 | 8% | 7 | 58% | 0 | 0% | 7 | 50% | 7 |
| Conduct at least 4 events for residential customers. | 4 | 5 | 125% | 22 | 525% | 0 | 0% | 22 | 425% | 0 |
| Promote SBEERC resources and energy efficiency information at 12 community events or more. | 12 | 2 | 16% | 26 | 216% | 0 | 0% | 26 | 216% | 0 |
| Respond to every customer inquiry within 48 hours. |  | 10 | n/a | 37 | n/a | 0 | n/a | 37 | n/a |  |
| Achieve an 80 percent overall customer satisfaction level of Excellent (based on follow-up surveys) of (Evaluation Levels: Poor, Below Average, Average, Good, and Excellent). |  | Excellent | met | Excellent | met | Excellent | met | Excellent | met |  |

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative -

- SBESC continues to work with SBCCOG Board and Steering Committee as well as Utility Partners to keep the program on track.

- Team signed lease and moved into new office facilities at 3868 Carson Street, Torrance.

- Team participated in meetings, conference calls and other communication with Partners regarding the existing program and planning for future program.

- Contacted SCE partners to procure additional CFL’s to be handed out at community events.

- A new Environmental Deputy was hired during the reporting period

    - Marketing –

SBESC:

- Prepared full page ad for special Graduation edition of The Daily Breeze, June 9, circulation 222,008 households

- Prepared flyer for July 21 special workshops for religious facilities, and sent out personalized invitations to 175 local houses of worship.

- Prepared flyer for each of the four mobile home park trainings and delivered them a week ahead of the training date trainings.

- Prepared articles for SBESC E-Newsletter and SBCCOG newsletter.  Published SBESC E-newsletter June 29.

- Met with Congresswoman Jane Harman’s Field Deputy at SBESC.

- Continue to process requests from telephone callers and visitors to the center in a timely manner.

    - Direct Implementation

Training

- SBESC delivered energy efficiency workshops for residential customers during the reporting period as follows:

  - June 6   - Southwood Homeowners Association, Torrance, CA

  - June 8   - Knolls Mobile Home Park, Torrance, CA

  - June 21 - SK Mobile Home Park, Torrance, CA

  - June 23 - San Rafael Mobile Home Park, Harbor City, CA

  - June 30 - Skyline Mobile Home Park, Torrance, CA

- The following business training was also delivered:

  - June 22 - Business –Hotel Training, Torrance, CA

Follow-up for training event included thank you letters and participation certificates. Most of the attendees rated the event good to excellent.

Energy Efficiency Action Plan

The plan is currently being worked on and a first draft will be completed in time to be incorporated in current program.

      - Audits, Site Surveys and Partnerships - None

      - Direct Installations, Rebates, Equipment Maintenance and Optimization – Not applicable

      - Calculated and Actual Payment Reconciliation - None

    - EM&V

Nothing this month.

- Program Challenges
None

- Customer Disputes
None

- Compliance Items
None

- Coordination Activities

- SBCCOG is participating in the Navigant CaLEEP Pilot Program.  Navigant will complete energy efficiency planning for South Bay Cities.

- Changes to Subcontractors or Staffing
None

- Additional Items
None

Supporting Documentation

- Marketing Materials

- Point of Purchase Program Documentation
None

- Free Measure Distribution Documentation
None

- Upstream Incentive Documentation
None

- Training Documentation

| Table E.1 – Training Documentation |
| --- |
| Brief Description of Training | Delivery Method | Materials List | Attendees | Training |
|  |  |  | Type | Number | Date | Location |
| Residential EE Training | Workshop | EE Info | Residents | 13 | Various | Various |
| Hotel Training | Workshop | EE Info | Business | 2 | 6/22/05 | Torrance |

| Table E.2 – Training Events Held |
| --- |
| Event Description | Event |
|  | Location | Date |
| Residential EE Training | Torrance | 6/6/05 |
| Residential EE Training | Torrance | 6/08/05 |
| Residential EE Training | Torrance | 6/21/05 |
| Residential EE Training | Harbor City | 6/23/05 |
| Residential EE Training | Torrance | 6/30/05 |

- Trade Show and Public Events

| Table F.2 - Trade Show and Public Events, Planned |
| --- |
| Event Description | Event |
|  | Location | Date |
| Royal Western Mobile Home Park | Gardena | 7/6/05 |
| Palos Verdes Chamber of Commerce | Palos Verdes | 7/12/05 |
| Torrance Chamber of Commerce | Torrance | 7/13/05 |
| Lawndale Kiwanis | Lawndale | 7/13/05 |
| Starlight Mobile Home Park | Torrance | 7/20/05 |
| EE in Churches Training event | Torrance | 7/21/05 |
| Tri-League of Women Voters | Torrance | 7/28/05 |