| Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Name: | Statewide Crosscutting Codes and Standards |
| IOU Service Area: | SCG |
| Program Number: | 1259-04 |
| Program Type: | IOU Statewide Program |
| Month: | July - 2005 |

- Program Status

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | Jul-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $325,526 | $12,276 | 4% | $166,903 | 51% |  |  | $166,903 | 51% | $158,623 |
| Admin | $80,014 | $2,800 | 3% | $34,728 | 43% |  |  | $34,728 | 43% | $45,286 |
| Marketing |  | $9,476 | NA | $111,289 | NA |  | NA | $111,289 | NA | -$111,289 |
| DI | $219,986 |  |  | $20,886 | 9% |  |  | $20,886 | 9% | $199,100 |
| EM&V | $25,526 |  |  |  |  |  |  |  |  | $25,526 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder.

Not applicable

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Performance Goal | Current Month’s Achievement | Cumulative Achievement | Commitments | Remainder |
| --- | --- | --- | --- | --- |
| Report on 4 CASE studies | 0 CASE study reported | 4 CASE studies | 0 CASE studies | 0 CASE studies |

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative activities:

The Codes and Standards Statewide Crosscutting IOU Team held teleconference meetings July12 & 20, 2005 to discuss Statewide Utility Concurrence regarding the development of a detailed plan for the 2006-2008 Codes and Standards Program.  The plan included a target list of case studies, projected timelines for adoption by the CEC.

July 15, 2005 the Statewide Crosscutting Team met at the SCE CTAC to discuss and evaluate the economical benefits of Demand Response in Title 24 for the 2008 Building Energy Efficiency Standards.  The group discussed what was necessary to develop a standard and measure its effectiveness.

July 18, 2005 attended CEC workshop on proposed revisions to regulations for Lamps and Metal Halide Luminaires.  The workshop focus was to obtain comments regarding potential revision the Appliance Efficiency Regulation for various appliances.

July 19, 2005 attended CEC workshop conducted for Energy Efficiency Improvements in Existing Building.  The workshop focused on options to develop a plan to reduce peak load consumption as required by AB549.

    - Marketing

Not applicable.

    - Direct Implementation

July 28, 2005 met with consultants and contractor to evaluate progression of the Noritz Water Heater Combination Hydronic System test.  After discussion the group made small but necessary changes to overall scope of the CASE study.

      - Audits and Site Surveys

Not applicable.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization

Not applicable.

      - Spending Variance

Not applicable.

    - EM&V

- Program Challenges 
None.

- Customer Disputes 
None.

- Compliance Items 
None.

- Coordination Activities
Coordination activities are detailed in the PIP.

- Changes to Subcontractors or Staffing 
None.

- Additional Items
In reviewing the workbook we have determined that the majority of the marketing charges should have been charged to another program and not to Codes and Standards. We will need to make the correction through a journal entry which will not be reflected until the August report.

Supporting Documentation

- Marketing Materials – 
Not applicable.

- Point of Purchase Program Documentation –
This program does not have point of purchase activities.

- Free Measure Distribution Documentation – 
This program does not distribute free measures.

- Upstream Incentive Documentation – 
This program is not an upstream incentive program.

- Training Documentation – 
No new training materials were developed this month.

- Trade Shows and Public Events – 
This program does not have trade shows or public events.