| Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Name: | Statewide Residential Single Family Home Energy Efficiency Rebate |
| IOU Service Area: | SCG |
| Program Number: | 1220-04 |
| Program Type: | IOU Statewide Program |
| Month | August-05 |

- Program Status

| Budget and Expenditures | Budget | Aug-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $12,145,090 | $611,747 | 5% | $9,106,467 | 75% |  |  | $9,106,467 | 75% | $3,038,623 |
| Admin | $1,432,400 | $185,900 | 13% | $948,101 | 66% |  |  | $948,101 | 66% | $484,299 |
| Marketing | $2,174,790 | $40,609 | 2% | $1,733,441 | 80% |  |  | $1,733,441 | 80% | $441,349 |
| DI | $8,368,900 | $385,238 | 5% | $6,424,925 | 77% |  |  | $6,424,925 | 77% | $1,943,975 |
| EM&V | $169,000 |  |  |  |  |  |  |  |  | $169,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

| Energy Effects | Goals | Aug-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 4,250 | 190 | 4% | 2,858 | 67% |  |  | 2,858 | 67% | 1,392 |
| Annual kWh | 10,766,576 | 405,851 | 4% | 8,229,100 | 76% |  |  | 8,229,100 | 76% | 2,537,476 |
| Lifecyc kWh | 157,409,229 | 5,998,097 | 4% | 114,310,802 | 73% |  |  | 114,310,802 | 73% | 43,098,427 |
| Annual Therms | 4,736,076 | 201,623 | 4% | 3,958,242 | 84% |  |  | 3,958,242 | 84% | 777,834 |
| Lifecyc Therms | 63,299,167 | 2,626,128 | 4% | 50,143,624 | 79% |  |  | 50,143,624 | 79% | 13,155,544 |

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Performance Goals | Goals | August -05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Hard to Reach goal is that 23% of rebate applications come from HTR zip codes | 23% | 28% | 121% |  |  |  |  | 28% | 121% |  |

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative- 
None.

    - Marketing - none this month.

    - Direct Implementation

      - For Audits and Site Surveys :N/A

      - For Direct Installations, Rebates, Equipment Maintenance and Optimization  -

- Total number of customers sites served

- Summary of type and number of measures installed or repaired

| Measure Type | Measure Qty |
| --- | --- |
| Appliances | 4,487 |
| Building Shell - Insulation | 530,984 |
| HVAC - Controls | 278 |
| HVAC - Heating Systems | 186 |
| Water Heating - Systems | 256 |
| Grand Total | 536,191 |

      - Discrepancies between total month's rebates paid may differ from the total calculated in the workbook due to the following reasons:

(1) There may be a lag in customer rebate payments, particularly those approved for payments towards the end of the month, due to the processing of check payments;

(2) SoCalGas pays an approved customer application either the prescribed rebates/incentives or the cost shown on the customer invoice, whichever is lower;

    - EM&V

- Program Challenges 
None

- Customer Disputes 
None

- Compliance - SoCalGas filed an updated Program Implementation Plan for this program on December 13, 2004 per  Decision 04-12-019, issued on December 2, 2004.

- Coordination Activities
Coordination Activities are detailed in the revised PIP

- Changes to Subcontractors or Staffing – Program Manager Assignment has changed

- Additional Items-None

Supporting Documentation

- Marketing Materials – 
None this month

- Point of Purchase Program Documentation – 
None this month

- Free Measure Distribution Documentation-  
This program does not distribute free measures

- Upstream Incentive Documentation – 
This program is not an upstream incentive program.

- Training Documentation – 
None this month

- Trade Shows and Public Events – 
None this month