| Implementer Name: | Southern California Gas Co |
| --- | --- |
| Program Name: | Bakersfield/Kern Energy Watch 1350-04 |
| IOU Service Area: | SCG |
| Program Number: | 1230-04 |
| Program Type: | IOU Partnership Program |
| Month | August-05 |

- Program Status

Pacific Gas and Electric Company (PG&E), Southern California Edison (SCE), Southern California Gas Company (SoCalGas), the City of Bakersfield (City), the County of Kern (County), and Staples/Hutchinson and Associates, Inc. (Staples/Hutchinson) entered into a partnership to reduce energy use by providing energy efficiency information and direct installation of energy efficient equipment to the City and County’s local community.

Specifically, this partnership will offer direct install services to hard-to-reach customers, home buyers, and small businesses; free energy audits to both residential and nonresidential hard-to-reach customers; marketing and outreach to encourage participation in statewide energy efficiency programs; municipal building energy efficiency retrofits; support for codes and standards enforcement; and local training seminars for residential contractors as well as design/build firms and engineers and architects working on commercial properties.

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | Aug-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $500,000 | $167 | 0% | $1,799 | 0% |  |  | $1,799 | 0% | $498,201 |
| Admin | $60,100 | $167 | 0% | $1,799 | 3% |  |  | $1,799 | 3% | $58,301 |
| Marketing | $439,900 |  |  |  |  |  |  |  |  | $439,900 |
| DI |  |  | NA |  | NA |  | NA |  | NA |  |
| EM&V |  |  | NA |  | NA |  | NA |  | NA |  |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder.

Not applicable to this program.

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative

Administrative activities related to standard program implementation included the monthly partnership coordination meeting of all partners in Bakersfield on August 25, 2005  in Bakersfield; telephone calls, e-mails and meetings between PG&E and Staples Marketing and between PG&E and residential services vendors; telephone calls and e-mails at each utility to coordinate 2005 activities; meetings, telephone calls and e-mails between the City of Bakersfield, County of Kern and PG&E and between the County of Kern and SCE to discuss progress in municipal building retrofits; and between utilities to coordinate marketing activities.

Partners have identified additional potential for installing energy efficiency measures in a number of PG&E and SCE small business customers.  SCE will file a change order with the CPUC for approval to add these small business retrofits. Up to $100,000 in incentives will be transferred from the municipal retrofits to cover the additional small business retrofit opportunities. PG&E may move $200,000 from administrative and marketing, while SCE has identified $100,000 that may be available for small business retrofits.  In addition, SCE has identified retrofits at small county facilities which, if installed using the Energy Watch small business program, could be completed before the end of the year. PG&E will need to do a contract change order with Staples Marketing for the additional work.

    - Marketing

The radio schedule concluded at the end of August.  Currently, $20,000 in marketing/outreach funds remain and are available for further promotion, depending on the outcome of the additional funding for non-residential retrofits.

Representatives of Bakersfield’s Energy Watch staff attended the Hispanic Chamber of Commerce Expo in Bakersfield on August 7th to promote the goals of the Energy Watch program.

Staples Marketing is scheduled to participate in the following outreach activities:

Kern County Fair

Kern County Fairgrounds

September 21-October 2, 2005

Bakersfield Fall Home Show

Kern County Fairgrounds - Booth #269

October 21-23, 2005

    - Direct Implementation

During August, the Education and Training component of the Bakersfield & Kern County Energy Watch program had no training or education efforts to report.  The absence of any scheduled sessions was a conscious decision based on past findings.  Historically July and August have been difficult months to successfully promote workshops largely due to vacations and hot valley weather.

Although the Energy Watch has met its education and training goals, we continue to explore the need for additional seminars and workshops, and respond to the needs of the community by offering courses to meet those needs.  PG&E is continuing to work with So Cal Gas to offer a Electric Safety and Energy Efficiency seminar in the early fall. A Commercial Pool Owners Workshop was held on August 30th in Bakersfield, as part of PG&E’s regular workshop offerings, and was jointly promoted by Energy Watch. As a result, attendance at the Bakersfield workshop, 35 participants, was twice as large as previous sessions.

      - For Audits and Site Surveys  - Not applicable for SCG

      - For Direct Installations, Rebates, Equipment Maintenance and Optimization  -  Not applicable for SCG.

      - Discrepancies between total month's rebates paid may differ from the total calculated in the workbook due to the following reasons: - Not applicable for SCG

    - EM&V -

EcoNorthwest, the consultant conducting the evaluations of seven of PG&E’s partnership programs received Energy Division approval to proceed with implementation of its evaluation plan on October 29, 2004. Survey design is proceeding and the revised EM&V project schedule has been reflected in tab 6 of the workbook.

- Program Challenges 
None

- Customer Disputes 
None

- Compliance Items

PG&E, SCE and SoCalGas filed revised Program Implementation Plans (PIP) and workbooks for this program on June 15, 2004.

- Coordination Activities

Coordination activities are detailed in the revised PIP. In addition, all Energy Watch partners have provided Staples Marketing with supplies of informational materials regarding other energy efficiency programs to be handed out at special events scheduled to promote Energy Watch and statewide energy efficiency programs.

- Changes to Subcontractors or Staffing

None

- Additional Items

None

Supporting Documentation

- Marketing Materials –

There were no new marketing materials this month.

- Point of Purchase Program Documentation –
This program does not have point of purchase activities.

- Free Measure Distribution Documentation –

This program does not have free measure distribution.

- Upstream Incentive Documentation – 
This program does not have upstream incentive documentation.

- Training Documentation –

No classes were held in July.

- Trade Shows and Public Events –

Energy Watch staff attended one activity in August 2005.

| Brief description of the event | Location of the event | Date of event |
| --- | --- | --- |
| Hispanic Chamber of Commerce Expo | Bakersfield | August 7, 2005 |