| Program Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Title: | South Bay Cities Energy Efficiency Resource Center – PGC |
| Program Number: | 1404-04 |
| Month: | August 2005 |

- Program Status

The South Bay Energy Efficiency Resource Center (SBEERC) is a partnership with the South Bay Cities Council of Governments (SBCCOG), Southern California Edison (SCE) and Southern California Gas Co. (SCG).  The South Bay Energy Efficiency Resource Center will expand on current regional energy efficiency activities through the development of a community-based resource for energy information, training and materials to assist the member agencies, businesses and citizens to best utilize the resources available to them through the wide variety of statewide and local energy efficiency programs.  To accomplish this, this partnership will form an Energy Efficiency Resource Center, which will serve the region’s constituents as the central clearinghouse for energy efficiency information and resources.  The SBEERC will establish a small, yet capable Resource Center that will significantly increase the availability of information and resources to the citizens of South Bay region.

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | Aug-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $793,490 | $1,580 | 0% | $42,507 | 5% | $14,828 | 2% | $57,336 | 7% | $750,983 |
| Admin | $132,026 | $1,580 | 1% | $14,610 | 11% | $14,828 | 11% | $29,439 | 22% | $117,416 |
| Marketing | $23,000 |  |  | $2,023 | 9% |  |  | $2,023 | 9% | $20,977 |
| DI | $604,675 |  |  | $25,874 | 4% |  |  | $25,874 | 4% | $578,801 |
| EM&V | $33,789 |  |  |  |  |  |  |  |  | $33,789 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

Due to a lag in the time between when the partnership expends funds and when SCG is invoiced for its share of those expenditures, the reported monthly expenditures of the partnership may differ from the expenditures recorded in SCG’s accounting system.

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder.

Not applicable to this program.

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Performance Goals | Goals | Aug-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Conduct at least 4 training sessions for the public sector | 4 | 0 | 0% | 5 | 125% | 0 | 0% | 5 | 125% | 0 |
| Conduct at least 12 sessions for businesses | 12 | 1 | 8% | 9 | 75% | 0 | 0% | 9 | 75% | 3 |
| Conduct at least 4 events for residential customers. | 4 | 1 | 25% | 25 | 650% | 0 | 0% | 25 | 650% | 0 |
| Promote SBEERC resources and energy efficiency information at 12 community events or more. | 12 | 1 | 8% | 27 | 225% | 0 | 0% | 27 | 225% | 0 |
| Respond to every customer inquiry within 48 hours. |  | 15 | n/a | 84 | n/a | 0 | n/a | 84 | n/a |  |
| Achieve an 80 percent overall customer satisfaction level of Excellent (based on follow-up surveys) of (Evaluation Levels: Poor, Below Average, Average, Good, and Excellent). |  | Excellent | met | Excellent | met | Excellent | met | Excellent | met |  |

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative -

- SBESC continues to work with SBCCOG Board and Steering Committee as well as Utility Partners to keep the program on track.

- Executive staff met with SCE’s Director of Energy Efficiency.

    - Marketing –

SBESC:

- Created and published an advertisement for BusinessInsider Magazine, created and distributed individualized flyer for each of the two training events held in August and created an invitation/flyer to the Torrance Area Chamber of Commerce Mixer/ Ribbon Cutting Grand Opening event that will be held at the center on October 19, 2005.

- Created quarter-page advertisement for the Daily Breeze, and provided information on the workshops scheduled for August 25 and September 8 for the Out & About section of the newspaper.

- Created 24” x 36” poster for use at community and outreach events.

- Program Manager discussed with City of Torrance staff the need for SBESC information to be included in their “Get Green” publication and was assured SBESC will be included in the next run.

- Program Manager prepared SBESC energy article for SBCCOG newsletter and SBESC e-newsletter.

- Distributed flyer for August 25 workshop at an Energy Workshop for Water/Wastewater Agencies on August 22.

- Made presentation on energy efficiency at two the Kiwanis Club on August 2 and the Rotary Club on August 31.

- Program Manager contacted the head of all South Bay Kiwanis clubs and provided information on SBESC.  Information about the center and the availability of speakers on energy efficiency will be passed on to all the unit clubs.

- On August 15 staff met with the Gas Company ERC members to discuss holding ERC training at the SBESC.   The tentative date for the first training is on November 10, 2005.  The event will target restaurants.

- On August 31, Program Manager attended a focus group outreach event regarding a large housing project on Navy reuse site.

- Finalized the details for the center’s grand opening/ribbon cutting gala event to be held on October 19, 2005.

- Continues to work with the community to identify outreach opportunities.

    - Direct Implementation

Training

SBESC delivered energy efficiency workshops for residential customers during the reporting period as follows:

- August 18 – Residential:  Garden West Mobile Home Park

- August 25 – Business:  Energy Efficiency for South Bay Pump Owners and Operators

Follow-up for training event included thank you letters and participation certificates. Most attendees rated the events good to excellent.

Community Event

SBESC exhibited at Congresswoman Jane Harman’s Alternative Energy Expo community event on August 17.

Energy Resource Center

Staff continues to process requests from telephone callers and visitors to the center in a timely manner.

Energy Efficiency Action Plan

A Draft of the Energy Efficiency Action Plan was completed by SBESC consultant and submitted for review.

      - Audits, Site Surveys and Partnerships - None

      - Direct Installations, Rebates, Equipment Maintenance and Optimization – Not applicable

      - Calculated and Actual Payment Reconciliation - None

    - EM&V

Nothing this month.

- Program Challenges
None

- Customer Disputes
None

- Compliance Items
None

- Coordination Activities

SBCCOG is collaborating with American Synergy Corporation, implementer of the direct install HTR Mobile Home Program to facilitate the mobile home park workshops. At these workshops, reservations are made for installation of energy efficiency measures by American Synergy.

- Changes to Subcontractors or Staffing
None

- Additional Items
None

Supporting Documentation

- Marketing Materials

- Point of Purchase Program Documentation
None

- Free Measure Distribution Documentation
None

- Upstream Incentive Documentation
None

- Training Documentation

| Table E.1 – Training Documentation |
| --- |
| Brief Description of Training | Delivery Method | Materials List | Attendees | Training |
|  |  |  | Type | Number | Date | Location |
| Residential EE Training | Workshop | EE Info | Residents | 6 | 8/18/05 | Gardena |
| Pump Owners and Operators Training | Workshop | EE Info | Business | 15 | 8/25/05 | Torrance |

| Table E.2 – Training Events Held |
| --- |
| Event Description | Event |
|  | Location | Date |
| Residential EE Training - Garden West MHP | Gardena | 8/18/05 |
| Business EE Training – Pump Operators | Torrance | 8/25/05 |

- Trade Show and Public Events

| Table F.2 - Trade Show and Public Events, Planned |
| --- |
| Event Description | Event |
|  | Location | Date |
| Residential Workshop – JCI Gardens | Gardena | 9/2/05 |
| Business Workshop for Non Profits | Torrance | 9/8/05 |
| Residential Workshop for all-electric homes | Torrance | 9/15/05 |
| Residential workshop – Japanese Cultural Inst. | Torrance | 9/19/05 |
| Residential Workshop – City of Gardena Seniors | Gardena | 9/19/05 |
| Business Workshop – Title 24 | Torrance | 9/21/05 |