| Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Name: | Statewide Residential New Construction California Energy Star New Homes |
| IOU Service Area: | SCG |
| Program Number: | 1244-04 |
| Program Type: | IOU Statewide Program |
| Month | September – 05 |

- Program Status

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | Sep-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $3,988,606 | $169,648 | 4% | $3,633,011 | 91% |  |  | $3,633,011 | 91% | $355,595 |
| Admin | $357,000 | $8,112 | 2% | $420,193 | 118% |  |  | $420,193 | 118% | -$63,193 |
| Marketing | $91,000 | $5,433 | 6% | $185,719 | 204% |  |  | $185,719 | 204% | -$94,719 |
| DI | $3,412,000 | $156,103 | 5% | $3,027,099 | 89% |  |  | $3,027,099 | 89% | $384,901 |
| EM&V | $128,606 |  |  |  |  |  |  |  |  | $128,606 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder

| Energy Effects | Goals | Sep-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 4,595 | 195 | 4% | 5,303 | 115% |  |  | 5,303 | 115% | -709 |
| Annual kWh | 3,338,463 | 141,465 | 4% | 3,853,670 | 115% |  |  | 3,853,670 | 115% | -515,206 |
| Lifecyc kWh | 60,092,341 | 2,546,366 | 4% | 69,366,053 | 115% |  |  | 69,366,053 | 115% | -9,273,712 |
| Annual Therms | 271,352 | 4,844 | 2% | 336,470 | 124% |  |  | 336,470 | 124% | -65,118 |
| Lifecyc Therms | 4,884,336 | 87,192 | 2% | 6,056,453 | 124% |  |  | 6,056,453 | 124% | -1,172,117 |

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

| MEASURE / ACTIVITY NAME | UNIT DEFINITION | FINANCIAL INCENTIVE PER UNIT | UNIT GOALS | TOTAL RECORDED UNITS |
| --- | --- | --- | --- | --- |
| Single Family Inland 15% Above AB970 | Home | $500.00 | 900 | 1,050 |
| Multifamily 15% Above AB970 | Home | $150.00 | 6,000 | 10,811 |
| Single Family Coastal 15% Above AB970 | Home | $400.00 | 0 | 0 |
| Single Family Inland 20% Above AB970 | Home | $700.00 | 500 | 0 |

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative

Regular monthly administrative activities include but are not limited to the following activities: continued refining of the customer participation process and program design, review of customer participation and market activity, coordination with participating retailers, vendors, and manufacturers and other market participants, contract management, responding to customer inquiries and concerns, planning of future training events, and managing of program budgets and expenditures.

    - Marketing

Marketing outreach continued via direct contact with builders, architects and energy analysts.

    - Direct Implementation

- EnergyPro® Residential Building Energy Analysis
This course covers utilizing EnergyPro® to prepare Residential Title 24, Energy Code documentation. Topics include basic program operation and inputs, the Residential Wizard and changes to Title 24 Energy Code.
September 6, 2005, 12 attendees representing 12 firms.

- Introduction to ACCA Manual D: Residential Duct Design
This class focuses on designing residential duct systems according to ACCA Manual D specifications using the ACCA Manual D and duct calculator. The course covers determining the system static pressure and available static pressure, calculating the total equivalent length of duct runs and friction rate and the sizing of ducts. The course also demonstrates the Wrightsoft Manual D software program
September 14, 2005, 16 attendees representing 14 firms.

- Static Pressure and Air Flow Testing
Participants in this class use a horizontal HVAC system to measure air flow, static pressure and amperage under various system configurations. System variables include filters, coils, variable size return ducts and leakage.
September 22, 2005, 14 attendees representing 14 firms.

- To support the building industry and its associates with timely information and education on energy efficiency a number of special classes have been designed and will be presented throughout the remainder of 2005. These classes will target members of the Southern California Building Industry Association and will present the changes to the California Building Energy Efficiency Standards, effective October 1, 2005. These changes will have a significant impact on residential new construction in California. There has been an increasing demand from the building industry and its associations for this information. To fill this need, Southern California Gas Company has created presentation tailored to the building industry. On September 20 and 22 this course was presenting to the ICC with 45 attendees at each session representing 45 firms. Additional courses were presented on September 15 and 20 representing 20 attendees representing 20 firms and 24 attendees representing 22 firms.

      - Audits and Site Surveys

Not applicable.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization

Not applicable.

      - Discrepancies between total month's rebates paid may differ from the total calculated in the workbook due to the following reasons:

(1) There may be a lag in  customer rebate payments, particularly those approved for payments towards the end of the month, due to the processing of check payments;

(2) SDG&E  pays an approved customer application either the prescribed rebates/incentives or the cost shown on the customer invoice, whichever is lower.

    - EM&V

- Program Challenges 
None.

- Customer Disputes 
None.

- Compliance Items 
None.

- Coordination Activities
Coordination activities are described in the PIP.

- Changes to Subcontractors or Staffing 
None.

- Additional Items

None this month.

Supporting Documentation

- Marketing Materials – 
There were no new marketing materials this month.

- Point of Purchase Program Documentation –
This program does not have point of purchase activities.

- Free Measure Distribution Documentation – 
This program does not distribute free measures.

- Upstream Incentive Documentation – 
This program is not an upstream incentive program.

- Training Documentation – 
No new materials were distributed at training sessions in December.

- Trade Shows and Public Events – 
None this month.