| Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Name: | Statewide Residential New Construction California Energy Star New Homes |
| IOU Service Area: | SCG |
| Program Number: | 1244-04 |
| Program Type: | IOU Statewide Program |
| Month | Jan-05 |

- Program Status

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | Jan-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $3,988,606 | $146,726 | 4% | $2,056,397 | 52% |  |  | $2,056,397 | 52% | $1,932,209 |
| Admin | $357,000 | $58,905 | 17% | $196,894 | 55% |  |  | $196,894 | 55% | $160,106 |
| Marketing | $91,000 | $8,516 | 9% | $91,540 | 101% |  |  | $91,540 | 101% | -$540 |
| DI | $3,412,000 | $79,305 | 2% | $1,767,963 | 52% |  |  | $1,767,963 | 52% | $1,644,037 |
| EM&V | $128,606 |  |  |  |  |  |  |  |  | $128,606 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder

| Energy Effects | Goals | Jan-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 4,595 | 189 | 4% | 3,323 | 72% |  |  | 3,323 | 72% | 1,272 |
| Annual kWh | 3,338,463 | 137,690 | 4% | 2,414,634 | 72% |  |  | 2,414,634 | 72% | 923,829 |
| Lifecyc kWh | 60,092,341 | 2,478,413 | 4% | 43,463,419 | 72% |  |  | 43,463,419 | 72% | 16,628,921 |
| Annual Therms | 271,352 | 11,948 | 4% | 220,338 | 81% |  |  | 220,338 | 81% | 51,014 |
| Lifecyc Therms | 4,884,336 | 215,070 | 4% | 3,966,085 | 81% |  |  | 3,966,085 | 81% | 918,251 |

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

| MEASURE / ACTIVITY NAME | UNIT DEFINITION | FINANCIAL INCENTIVE PER UNIT | UNIT GOALS | TOTAL RECORDED UNITS |
| --- | --- | --- | --- | --- |
| Single Family Inland 15% Above AB970 | Home | $500.00 | 900 | 548 |
| Multifamily 15% Above AB970 | Home | $150.00 | 6,000 | 7177 |
| Single Family Coastal 15% Above AB970 | Home | $400.00 | 0 | 0 |
| Single Family Inland 20% Above AB970 | Home | $700.00 | 500 | 0 |

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative

Regular monthly administrative activities include but are not limited to the following activities: continued refining of the customer participation process and program design, review of customer participation and market activity, coordination with participating retailers, vendors, and manufacturers and other market participants, contract management, responding to customer inquiries and concerns, planning of future training events, and managing of program budgets and expenditures.

This month, additional activities included

Program Managers attended meetings to review and understand CPUC reporting requirements for 2004.

    - Marketing

Marketing outreach continued via direct contact with builders, architects and energy analysts.

    - Direct Implementation

During January 2005 Southern California Gas did not offer training courses.

      - Audits and Site Surveys

Not applicable.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization

Not applicable.

      - Discrepancies between total month's rebates paid may differ from the total calculated in the workbook due to the following reasons:

(1) There may be a lag in  customer rebate payments, particularly those approved for payments towards the end of the month, due to the processing of check payments;

(2) SDG&E  pays an approved customer application either the prescribed rebates/incentives or the cost shown on the customer invoice, whichever is lower.

    - EM&V

- Program Challenges 
None.

- Customer Disputes 
None.

- Compliance Items 
None.

- Coordination Activities
Coordination activities are described in the PIP.

- Changes to Subcontractors or Staffing 
None.

- Additional Items

None this month.

Supporting Documentation

- Marketing Materials – 
There were no new marketing materials this month.

- Point of Purchase Program Documentation –
This program does not have point of purchase activities.

- Free Measure Distribution Documentation – 
This program does not distribute free measures.

- Upstream Incentive Documentation – 
This program is not an upstream incentive program.

- Training Documentation – 
No new materials were distributed at training sessions in December.

- Trade Shows and Public Events – 
None this month.