| Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Name: | Statewide Nonresidential Express Efficiency |
| IOU Service Area: | SCG |
| Program Number: | 1251-04 |
| Program Type: | IOU Statewide Program |
| Month | March-05 |

- Program Status

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget  in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | Mar-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $8,448,858 | $194,275 | 2% | $4,298,783 | 51% |  |  | $4,298,783 | 51% | $4,150,075 |
| Admin | $932,720 | $87,391 | 9% | $462,262 | 50% |  |  | $462,262 | 50% | $470,458 |
| Marketing | $2,594,625 | $56,774 | 2% | $960,707 | 37% |  |  | $960,707 | 37% | $1,633,918 |
| DI | $4,740,513 | $50,110 | 1% | $2,875,814 | 61% |  |  | $2,875,814 | 61% | $1,864,699 |
| EM&V | $181,000 |  |  |  |  |  |  |  |  | $181,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Energy Effects | Goals | Mar-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW |  |  | NA |  | NA |  | NA |  | NA |  |
| Annual kWh | 34,531 | 51,169 | 148% | 1,519,373 | 4400% |  |  | 1,519,373 | 4400% | -1,484,842 |
| Lifecyc kWh | 379,843 | 562,859 | 148% | 16,713,101 | 4400% |  |  | 16,713,101 | 4400% | -16,333,258 |
| Annual Therms | 6,214,018 | 189,803 | 3% | 7,649,898 | 123% |  |  | 7,649,898 | 123% | -1,435,880 |
| Lifecyc Therms | 79,538,480 | 2,190,967 | 3% | 84,534,331 | 106% |  |  | 84,534,331 | 106% | -4,995,851 |

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Performance Goals | Goals | Mar-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Hard to Reach | 43% | 16% | 37% | 37% | 86% | 0 | 0 | 37% | 86% | 6% |

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative

Regular monthly administrative activities include but are not limited to the following activities: continued refining of the customer participation process and program design, review of customer participation and market activity, coordination with participating retailers, vendors, and manufacturers and other market participants, contract management, responding to customer inquiries and concerns, planning of future training events, and managing of program budgets and expenditures.

This month, additional activities included:

- Chinese, Vietnamese, and Korean versions of the Express Efficiency Rebate applications were posted on the SoCalGas website in March.  The Spanish version is being finalized.

    - Marketing

- SCG gave a DSM presentation for the “Air Quality Regulations for Small Boilers” seminar at the Energy Resource Center in Downey CA, on March 24th, which was attended by approximately 100 participants.  Express Efficiency and other DSM programs were highlighted, with a special emphasis on boiler rebates available in the Statewide Express Efficiency rebate program.  Express Efficiency and other DSM literature and applications were made available to the attendees.

- SCG participated in the Non-Residential Energy Efficiency Customer/ESCO/Vendor Workshop at the Hyatt Regency in Irvine on March 24th.  This program was attended by approximately 250 participants.  The event was an opportunity for customers, energy service companies and vendors to discuss energy efficiency project opportunities.  SoCalGas' presentation included information about the Express Efficiency and other DSM programs.  The workshop itself was an opportunity for attendees to discuss the SCG energy efficient programs and obtain a better understanding of the programs methodology.  Express Efficiency and other DSM literature and applications were made available to the attendees.

- SCG provided DSM update training for 29 Pacific Coast Region Commercial Service Techs, Industrial Service Techs, and their supervisors on March 3rd at Anaheim District.

- SCG distributed 431 Express Efficiency Rebate applications in February (not reported in Feb workbook), and 636 in March.  There were 439 other pieces of Express Efficiency collateral distributed directly to customers.  Additional applications and collateral were distributed at additional events, through vendors, and from the internet.

    - Direct Implementation

      - For Audits and Site Surveys  - Not applicable

      - For Direct Installations, Rebates, Equipment Maintenance and Optimization  -

- Total number of customers sites served, 654.

- Summary of type and number of measures installed or repaired

| Measure Type | Measure Qty |
| --- | --- |
| Appliances | 37 |
| Water Heating - Systems | 4,280 |
| Nonresidential - Custom End Use | 5,020 |
| HVAC - Controls | 163 |
| Grand Total | 9,500 |

      - Discrepancies between total month's rebates paid may differ from the total calculated in the workbook  due to the following reasons:

(1) There may be a lag in  customer rebate payments, particularly those approved for payments towards the end of the month, due to the processing of check payments;

(2) SoCalGas pays an approved customer application either the prescribed rebates/incentives or the cost shown on the customer invoice, whichever is lower;

    - EM&V

- Program Challenges 
None

- Customer Disputes 
None

- Compliance Items

SoCalGas filed an updated Program Implementation Plan for this program on December 13, 2004 per Decision 04-12-019, issued on December 2, 2004.

- Coordination Activities

Coordination activities are detailed in the revised PIP.

- Changes to Subcontractors or Staffing

None

- Additional Items

None

Supporting Documentation

- Marketing Materials –

- Korean Express Efficiency Rebate application form

- Chinese Express Efficiency Rebate application form

- Vietnamese Express Efficiency Rebate application form

- Point of Purchase Program Documentation –
This program does not have point of purchase activities.

- Free Measure Distribution Documentation – 
This program does not distribute free measures.

- Upstream Incentive Documentation – 
This program is not an upstream incentive program.

- Training Documentation – 
None this month.

- Trade Shows and Public Events –

- Air Quality Regulations for Small Boilers seminar at the ERC in Downey, CA on March 24th.

- Non-Residential Energy Efficiency Customer/ESCO/Vendor Workshop at the Hyatt Regency in Irvine, CA on March 24th.