| Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Name: | Statewide Crosscutting Codes and Standards |
| IOU Service Area: | SCG |
| Program Number: | 1259-04 |
| Program Type: | IOU Statewide Program |
| Month: | Jan - 2005 |

- Program Status

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | Jan-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $325,526 | $2,101 | 1% | $121,463 | 37% |  |  | $121,463 | 37% | $204,063 |
| Admin | $80,014 | $276 | 0% | $26,220 | 33% |  |  | $26,220 | 33% | $53,794 |
| Marketing |  | $1,825 | NA | $74,357 | NA |  | NA | $74,357 | NA | -$74,357 |
| DI | $219,986 |  |  | $20,886 | 9% |  |  | $20,886 | 9% | $199,100 |
| EM&V | $25,526 |  |  |  |  |  |  |  |  | $25,526 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder.

Not applicable

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Performance Goal | Current Month’s Achievement | Cumulative Achievement | Commitments | Remainder |
| --- | --- | --- | --- | --- |
| Report on 4 CASE studies | 1 CASE study reported | 3 CASE studies | N/A | 1 CASE study to be reported |

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative Codes and Standards Program Manager recorded no extraordinary activities for the month. SAP data was reviewed for possible omissions and /or errors. In addition, budgetary information was reviewed for accuracy.

    - Marketing

Not applicable.

    - Direct Implementation

- New Title 20, Appliance Efficiency Standard 15-Day language was adopted by the CEC Commission on December 15, 2004. This rulemaking has staggered effective dates through the year 2007. None of the appliances included in the rulemaking are regulated by the Federal government

- Staff met during December with the other IOU’s and the CEC in order to continue to pursue mutually beneficial CASE studies for 2004-2005. One (1) additional CASE study was initiated in 2004, bringing the total to three (3) for 2004. The goal is four (4) during the 2004-2005 timeframe. The new CASE study centered on non-residential outdoor lighting.

- Work continued on Assembly Bill 549 to deal with energy-efficiency in existing buildings.  An examination of the of the Synthesis report was conducted.

- In a separate meeting, comments to the Synthesis report were discussed and next action items for the project were planned. A final report is scheduled to be issued to the Legislature on October 1, 2005.

- Training Activities

During December the following classes were offered to train and inform the market actors in energy efficient methods and technology. These courses were offered in conjunction with the California Energy Star New Homes Program.

EnergyPro® Residential Building Energy Analysis
This course covers utilizing EnergyPro® to prepare Residential Title 24, Energy Code documentation. Topics include basic program operation and inputs, the Residential Wizard and changes to Title 24 Energy Code.
December 2, 2004, National University Computer Center, San Bernardino, 13 attendees representing 13 firms.

MicroPas Residential Energy Compliance
This seminar is designed to provide detailed training on use of the California Energy Commission approved MicroPas program for use with the residential energy standards. Emphasis will be placed on energy code requirements and obtaining accurate compliance results as well as plan checking compliance.
December 8, 2004, Southern California Gas Company, Redlands, 6 attendees representing 6 firms.

      - Audits and Site Surveys

Not applicable.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization

Not applicable.

      - Spending Variance

Not applicable.

    - EM&V

- Program Challenges 
None.

- Customer Disputes 
None.

- Compliance Items 
None.

- Coordination Activities
Coordination activities are detailed in the PIP.

- Changes to Subcontractors or Staffing 
None.

- Additional Items
No additional items to report.

Supporting Documentation

- Marketing Materials – 
Not applicable.

- Point of Purchase Program Documentation –
This program does not have point of purchase activities.

- Free Measure Distribution Documentation – 
This program does not distribute free measures.

- Upstream Incentive Documentation – 
This program is not an upstream incentive program.

- Training Documentation – 
No new training materials were developed this month.

- Trade Shows and Public Events – 
This program does not have trade shows or public events.