| Program Name: | CCC/IOU Energy Efficiency Partnership |
| --- | --- |
| Program Number: | SCG3518 |
| Quarter: | Second Quarter 2006 |

- Program description

The California Community Colleges/Investor Owned Utility Energy Efficiency Partnership is a unique, statewide program to achieve immediate and long-term energy savings and peak demand reduction within California’s higher education system. The combined funding of nearly $29M for the 2006-08 program will establish a permanent framework for sustainable, comprehensive energy management at Community College campuses served by California's four Investor Owned Utilities.

The 2006-2008 CCC/IOU Partnership was based on the experiences of the previous partnership cycle.  The management structure was modeled after the 2004-2005 UC/CSU Partnership.  However, the structure was flattened to facilitate the decision making process.   A Management Team was established to coordinate the Program and has been meeting on a regular basis for the last 8 months to plan and begin implementation of the 2006-08 programs.

- Administrative activities

- Developed a Draft Partnership Letter Agreement that outlines roles, responsibilities, commitments, and other terms and conditions between the program Partners.  The Letter Agreement will be executed by the IOUs and the CCC Chancellors’ office.  The Draft Letter Agreement is currently under review by the Chancellor’s Office legal staff and is expected to be adopted soon.

- Adopted a Project Agreement document that will be used as the contractual vehicle between the IOUs and the CCC Districts for the implementation of campus projects.

- Continued with the development of an enhanced program and project tracking website in cooperation with the UC/CSU/IOU Energy Efficiency Partnership.  The BETA release of the web site occurred on June 30, 2006.

- Continued the evolution of the Training & Education program in collaboration with the UC/CSU/IOU Partnership.  Conducted a training needs survey with all 72 CCC Districts to obtain feedback to assist in T&E Program design.

- The Management Team provided input and comments to state Assembly Bill AB 993 regarding a proposal to establish Community College “Pilot” training programs and facilities.

- Established a Retro-Commissioning/Monitoring Based Commissioning (RCx/MBCx) Team to develop an approach to accomplish commissioning projects for the Partnership.

- Marketing activities

- Several Districts and SCG participated in the California Association of School Business Officials (CASBO) conference in San Diego in April 2006, and made a presentation to the conference to introduce the Partnership.

- The Outreach Committee, led by representatives from the Foundation for California Community Colleges (FCCC), focused efforts in the 2nd Quarter on Districts and Campuses in the PG&E service territory.  The FCCC and PG&E combined efforts to identify those Districts/Campuses that needed additional technical assistance to identify projects and prepare Form 2 submittals and to identify the appropriate contacts for Outreach efforts.  PG&E Management Team members worked with their Account Services representatives to facilitate this contact.

- The Outreach Team conducted a CCC Facility Managers statewide “web cast” on May 3, 2006 at several locations statewide to disseminate Program information to Districts.  The Web Cast was well attended by the Community College Districts, as well as several contractors and engineering firms that are participating in energy projects at the campuses.  Presentations on program information were made by all four IOUs, CCC District personnel, and contractors.  The Web Cast was regarded as a success by all in attendance.

- Representatives from all four IOUs, several CCC Districts, and the Program Administration consultant attended the UC/CSU/CCC Sustainability Conference held at UC Santa Barbara June 25 – 27.   The UC/CSU and CCC/IOU Partnerships collaborated for the effort with an exhibit booth manned by several team members from both Partnerships..

- Direct implementation activities

- The Management Team reviewed Form 2 project submittals from Districts and approved for implementation energy efficiency projects totaling 6,398 kW (33% of 3 year goal), 21,537,019 kWh (26% of goal), 90,307 therms (4% of goal) and encumbering $5,415,254 in incentive funds (24% of budget).   All projects reviewed and approved by the Management Team had met IOU due-diligence review criteria based on CPUC filed plans.  Approved projects will go to the implementation stage upon execution of a Project Agreement between the appropriate District and IOU.  Table 2 (attached) is a summary of projects approved through the 2nd Quarter compared to program goals broken down by IOU.  Also attached is Table 1, which is a summary of all Form 2 project proposals received by all Districts.  This table represents the total backlog of Form 2s received.

- Program performance/program status

Program is on target

Program is exceeding expectations

Program is falling short of expectations

Program effort over the reporting period was largely a transition from program design and startup activities into energy project review and approval for implementation.

- Program achievements (non-resource programs only):

- Projects were approved for implementation but are not complete; therefore no verified savings figures to report.  Backlog of proposed projects are summarized by IOU in Table 1 and approved projects representing proposed savings summarized in Table 2.

- Changes in program emphasis, if any, from previous quarter (new program elements, less or more emphasis on a particular delivery strategy, program elements discontinued, measure discontinued, budget changes, etc.).

- No changes

- Discussion of near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation, etc.)

- Execution of the Partnership Letter Agreement between IOUs and CCC Chancellors Office.

- Continued review and approval of project proposals (Form 2) currently submitted and in backlog (see Tables 1 and 2).

- Continue with Outreach Team efforts to identify additional Form 2 projects for submission and provide technical assistance to Districts/Campuses in need.

- Continue to develop a Training & Education plan coordinated with the UC/CSU Partnership.

- Changes to staffing and staff responsibilities, if any

- No changes.

- Changes to contracts, if any

- No changes.

- Changes to contractors and contractor responsibilities, if any

- No changes.

- Number of customer complaints received

- No complaints received.

- Revisions to program theory and logic model, if any

- No changes.