| Program Name: | Statewide Residential Home Energy Efficiency Survey |
| --- | --- |
| Program Number: | SCG3509 |
| Quarter: | Third Quarter 2006 |

- Program description

The Home Energy Efficiency Survey (HEES) program is a statewide residential audit program that provides residential customers the opportunity to participate in a mail-in, online, and in-home energy analysis of their home.  The primary intent of the program is to increase customer awareness of energy efficiency opportunities and prompt participation and greater crossover with the energy efficiency rebate programs.

- Administrative activities (describe)

Routine monthly administrative activities include but are not limited to the following activities:  manage and track current survey program in production, manage and develop new survey program, contract management, respond to customer inquiries and concerns, plan future marketing events, and manage program budgets and expenditures.

Additional administrative activities include:

- Continued refining of the customer participation process and program design, review of customer participation and market activity.

- Coordination with survey vendor, SCG, LADWP, Golden State Water (GSW), 3rd parties, and other market participants to maximize funds in order to reach program goal.

- Contract management for 3rd parties.

- Marketing activities (describe)

- In an effort to limit lag time for launch of 2006 HEES programs, continuing to market on-line and in-home surveys.

- In the 3rd quarter HEES participated in 14 SCG Marketing and Outreach events and successfully produced 226 completed surveys.

- In August and September HEES worked with Statewide Partnership Program and South Bay Energy Savings Center in four events and successfully achieved 119 completed HEES.

- In July, promoted Online HEES via the online banner ad on the ‘bill due’ notification that home banking customers receive.

- In July, San Gabriel Valley Tribune ran an article promoting SCG Residential Customer Programs that includes HEES

- Joint in-home, mail-in, and online survey effort between SCG, SCE and GSW for shared territories.  Joint mail-in survey efforts being made between SCG and LADWP.

- For cost effective strategy, promotions for online and in-home survey were split amongst SCG, SCE and GSW in shared-territories.

- To promote HEES to Hard-to-Reach and non-English speaking SCG-only and SCG and SCE sectors, joint efforts w/3rd parties is in progress.

- Direct implementation activities (describe)

- Current version on the in-home and online survey is in progress.

- SCG is working diligently with vendor, GSW, and SCE to launch the new joint surveys.  Utilities and vendor are conducting thorough online testing to ensure good customer service.

- SCG’s IT successfully finalized the secured transfer file process (SFTP) to post relevant customer data on SCG server for Contractor’s use in preparing customized HEES reports for participating SCG customers.

- Program performance/program status (describe)

Program is following expectations with new HEES to launch in 2006.

In-home HEES is in progress.  Joint effort between SCG and SCE for an in-home survey is successfully increasing response rate and will soon reach targeted expectation.

New online HEES is currently in testing phase and is expected to launch in 2006.

The new mail-in HEES is in the last phase of production and is expected to launch successfully in 2006 with joint efforts by SCE, GSWC, and LADWP.

- Program achievements (non-resource programs only):

- 1,492 SCG in-home surveys completed.

- 587 SCG online surveys completed.

- Changes in program emphasis, if any, from previous quarter (new program elements, less or more emphasis on a particular delivery strategy, program elements discontinued, measure discontinued, budget changes, etc.).

None

- Discussion of near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation, etc.)

In the fourth quarter, there will be the direct implementation of the new HEES along with several marketing and outreach efforts to increase participation.  They include, but are not limited to:

- routine updating on SCG website’s residential page, HEES page, Single Family Rebates page, and Energy Efficiency page to better promote Residential Customer Programs.

- promote current version of online survey with specialty coffee card incentive

- work with 3rd Party Ethnic Outreach Group to promote HEES at events (i.e. Moon Festival)

- provide laptop computers at outreach events to encourage online HEES participation

- launch new online survey which will introduce a joint SCG, SCE, and GSW landing page to provide gas, electric, and water measures

- launch new mail-in survey which will be multi-branded with SCG, SCE, and GSW to provide gas, electric, and water measures

- in Fall, do joint SCG, SCE, and GSW online marketing (i.e. banner ads) to increase online participation

- begin the process of integrating online HEES with SCG MyAccount to increase online participation.

- Changes to staffing and staff responsibilities, if any

None

- Changes to contracts,

None

- Changes to contractors and contractor responsibilities, if any

None

- Number of customer complaints received

None

- Revisions to program theory and logic model, if any

Provided in February 1, 2006 concept paper.

None