| Program Name: | Single Family Energy Efficiency Retrofit program |
| --- | --- |
| Program Number: | SCG3517 |
| Quarter: | Third Quarter 2006 |

- Program description

The Single Family Energy Efficiency Retrofit (SF) program is an existing statewide program designed to help Southern California Gas Company (SoCalGas) residential customers reduce their natural gas energy usage by replacing inefficient appliances with new energy-efficient appliances and weatherizing their homes.  The program contains elements such as traditional customer incentives, point of sale (POS) rebates, customer information and education and marketing and outreach, using trade allies, manufacturers, retailers and distributors to deliver information, measures and rebates.  It offers agreed upon statewide measures with coordinated implementation, and is designed to be able to segregate, and add new measures for tailoring to a specific market opportunity that emerges in the SoCalGas local service area.

- Administrative activities

Routine monthly administration activities include but not limited to the following:  project tracking, review of prospective projects, coordination, contract management, responding to customer inquiries and concerns, planning for future marketing events, and managing of program budgets and expenditures were performed.  In addition:

- Coordinated minor modification and re-printing of the single family rebate applications.

- Coordinated communications to retailers related to updates associated with the single family rebate program.

- Coordinated translation and re-printing of single family application into Spanish.

- Updated processing procedures to reflect changes to the point of sale instant rebate program.

- Participated in meetings with local and chain retailers to recruit new point of sale retailers.

- Coordinated statewide meeting to discuss changes for 2007 program.

- Continued talks with an outside vendor in drafting a scope of work for online rebate application and processing for 2007.  Participated in the review process until a finished product is available for launch.

- Reviewed program information provided to Flex You Power for their web posting.

- Marketing activities

- Aug/Sept issue of the Gas Company newsletter contains an article promoting the 2006 SF rebate program

- Attended the Energy Star Appliance partners meeting in Newport, Rhode Island.  Met with Energy Star appliance partners to encourage them to support the various energy-efficiency programs in California.

- Met with members of Energy Star to discuss possibilities of a targeted Energy Star dishwasher campaign to the Hispanic market and non-dishwasher users in our service territory.

- SoCalGas’ outreach group participated in events such as Expo Tu Casa event, Harvest Festival, Filipino cultural festival and Lowe’s Energy Efficiency month kickoff handing out 2006 SoCalGas single family rebate applications and distributing free aerators.

- Direct implementation activities

- 2006 SF rebate applications and signage were delivered to Home Depot retailers in SoCalGas’ service territory through SoCalGas’ contractor field representative.

- With help from SDG&E, continued to work on a planned joint RFP seeking an outside vendor to provide rebate application processing and online rebate application services.

- Continued recruiting efforts of local retailers to participate in the point of sale instant rebate campaign providing SoCalGas customers with an instant rebate on qualifying clothes washers, dishwashers or natural gas water heaters.

- Program performance/program status

Program is on target

Program is exceeding expectations

Program is falling short of expectations

Explain

26,163 rebate applications have been received through September 30, 2006. 50% of incentive budget has been spent and program is at 26% of therm goal.  Although the second quarter has been slow, the upcoming promotions and point of sale instant rebates should boost participation.

- Program achievements (non-resource programs only):

- None

- Changes in program emphasis, if any, from previous quarter (new program elements, less or more emphasis on a particular delivery strategy, program elements discontinued, measure discontinued, budget changes, etc.).

- Expanded point of sale rebates on high efficiency clothes washers, high efficiency dishwashers and natural gas water heaters offered to local retailers.

- Discussion of near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation, etc.)

- Point of sale participation for retailers selling high efficiency clothes washers, high efficiency dishwashers and natural gas water heaters expected to increase.  SoCalGas is in discussions with big box retailers that may participate.

- Changes to staffing and staff responsibilities, if any

- N/A

- Changes to contracts,

- None, Contact is Joy Yamagata

- Changes to contractors and contractor responsibilities, if any

- None

- Number of customer complaints received

- None

- Revisions to program theory and logic model, if any

Provided in February 1, 2006 concept paper.