| Program Name: | SoCalGas On-Bill Financing |
| --- | --- |
| Program Number: | SCG3514 |
| Quarter: | Fourth Quarter 2006 |

- Program description:

The Southern California Gas Company (SoCalGas) On-Bill Financing (OBF) Program is a local program designed to facilitate the purchase and installation of qualified energy efficiency measures by customers who might otherwise not be able to act given capital constraints and administrative and time burdens to participation.

- Administrative activities:

- Various internal presentations to provide an overview of the 2006-2008 On-Bill Financing Program and the support the program provides to energy efficiency rebate/incentive programs.

- Participated in discussions and meetings with the Statewide IOUs to discuss our approaches for Financing programs for the 2006-2008 program cycle.

- Marketing activities:

Sought select customers to participate in program as "beta" sites for testing purposes.

- Direct implementation activities:

Information Technology began programming Phase II Business Requirements to fully automate the billing system for processing monthly loan charges.  The projected completion date for Phase II is third quarter 2007 as extended per advice letter 3673, dated, November 21, 2006.

- Program performance/program status:

Program is on target

Program is exceeding expectations

Program is falling short of expectations

Explain:

Milestone 1 stated that SoCalGas would have a manual billing system in place and loans available to customers by end of first quarter 2006.  At the end of the first quarter, the manual billing system was in place.

- Program achievements (non-resource programs only):

- Provided training to regional sales groups on the benefits for SoCalGas customers to have On-Bill Financing as an option for participation, and

- Implented, manual billing system.

- Changes in program emphasis, if any, from previous quarter (new program elements, less or more emphasis on a particular delivery strategy, program elements discontinued, measure discontinued, budget changes, etc.):

The Department of Corporations granted SoCalGas’ an ‘exempt’ status as a lender subject to CPUC regulations.  OBF implemented program improvements as outlined in the approval of advice letter number 3673, dated November 21, 2006.  These enhancements included raising the maximum loan amount from $25,000 to $50,000 per meter.  Eliminating one of the customer eligibility requirements: “No more than three over-due notices in the past 12 months,” modified the site requirement for eligibility, and expanded qualified projects to include self-installation.

- Discussion of near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation, etc.):

- Recruit contractors to participate in the OBF Contractor Network,

- Direct mailing campaign to pre-selected customers, and

- Work with Partnership programs to recruit potential OBF customers.

- Changes to staffing and staff responsibilities, if any:

None

- Changes to contracts:

None

- Changes to contractors and contractor responsibilities, if any:

None

- Number of customer complaints received:

None

- Revisions to program theory and logic model, if any:

None