| Program Name: | Mobile/Manufactured Home Innovative Outreach and Measure Program |
| --- | --- |
| Program Number: | SCG3539 |
| Quarter: | Fourth Quarter 2006 |

- Program description

The Mobile/Manufactured Home Innovative Outreach and Measure Program has been designed to provide gas measures on a comprehensive basis to 14,500 mobile home customers in the Southern California Gas Company (SCG) service territory.

- Administrative activities

The 4th Quarter was a solid quarter of production in the Manufactured-Mobile Home Program and the program is gaining traction.

We are continuing to refine the implementation process including outreach, installation, scheduling, customer service, quality control efforts, data entry and reporting. We are also working to build our installation crews to be prepared for the holiday and winter months.

- Marketing activities

Our marketing and outreach personnel have held 33 neighborhood meetings with 1,000 guests in attendance for the quarter, with 4,156 guests visited or contacted program to date.  During these meetings a program overview was presented to possible Mobile Home clients.  Sample of the measures to be performed were demonstrated and potential clients and program participants were able to ask questions.  It was felt that these neighborhood meetings were quite productive.  Many customers are able to schedule their appointments for installation directly from these meetings.

Locations and numbers where a number of the neighborhood meetings were held are included as follows to give you a sampling of the types of meetings held:

| Mobile Home Park City No. Attending Flyers Caravana San Jacinto 55 0 East lake Hemet 50 0 Murrieta Palms Murrieta 30 0 Eden Roc. North Hemet 70 0 Golf Knolls Murrieta 35 0 Foot Hills of Hemet Hemet 150 0 Saddleback MHP Hemet 90 0 Santa Rosa MH Community Hemet 0 350 Echo Hills MH Estates Hemet 0 100 Sierra Dawn Hemet 0 1100 Hill Side Estates Sun City 0 276 Skyline Torrance 45 Gardena Villas Gardena 30 Parkview San Jacinto 35 Other Areas 176 | Month Mobile Home Park City No. Attending Flyers October Caravana San Jacinto 55 0 East lake Hemet 50 0 Murrieta Palms Murrieta 30 0 Eden Roc. North Hemet 70 0 Golf Knolls Murrieta 35 0 Foot Hills of Hemet Hemet 150 0 Saddleback MHP Hemet 90 0 Santa Rosa MH Community Hemet 0 350 Echo Hills MH Estates Hemet 0 100 Sierra Dawn Hemet 0 1100 Hill Side Estates Sun City 0 276 Skyline Torrance 45 Gardena Villas Gardena 30 Parkview San Jacinto 35 Other Areas 176 Total 590 2,002 Total PTD 3,746 2,002 |
| --- | --- |
| San Jacinto Community Center | San Jacinto | 9 | 0 |
| Park View | Orange | 21 | 0 |
| Linda Vista | Hemet | 68 | 0 |
| Seven Hills | Hemet | 80 | 0 |
| Monte Vista | Yucaipa | 19 | 0 |
| Hemacinto | San Jacinto | 15 | 0 |
| Rialto Mill Village | Rialto | 15 | 0 |
| Val Verde | Orange | 5 | 0 |
| Santiago Creek | Orange | 38 | 0 |
| Orange Crest | Orange | 29 | 0 |
| RV & Mobile | Rancho Mirage | 0 | Flyers |
| Palm View Estates | Desert Hot Springs | 0 | Flyers |
| Santiago | Rialto | 0 | Flyers |

- Direct implementation activities

Jobs were scheduled for all of those in attendance at the neighborhood meetings and those that responded to a direct mail campaign

- Program performance/program status

Program is on target

Program is exceeding expectations

Program is falling short of expectations

- Program achievements (non-resource programs only):

Not applicable

- Changes in program emphasis, if any, from previous quarter (new program elements, less or more emphasis on a particular delivery strategy, program elements discontinued, measure discontinued, budget changes, etc.).

- Working to increase production and complete all work, when possible in 2007.  We will then work with the program manager in June/July to explore supplemental funding for 2008 to gain additional energy savings.

- Discussion of near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation, etc.)

- We are working on both a program of providing helpers to crew chief to increase productivity on our production crews.

- We are also working on adding additional technicians and crews to increase production throughout the holiday and winters months.  Not only will these individuals help during these periods, but throughout 2007.

- Changes to staffing and staff responsibilities, if any

None

- Changes to contracts,

None

- Changes to contractors and contractor responsibilities, if any

None

- Number of customer complaints received

There are no ongoing customer disputes.  We had 9 customer complaints during the quarter and all complaints were handled promptly and to the customers’ satisfaction.

We have had many customer compliment cards come in and we have had some customer complaints come in.

The customer complaints had to do with a technician being late or missing an appointment or having troubles with an air conditioner or a hardwire fixture not functioning properly after we left.  In all cases the customer service team from Synergy responded quickly and handled the complaint to the customer’s satisfaction.

- Revisions to program theory and logic model, if any

# Provided in February 1, 2006 concept paper.

None