| Program Name: | County of Los Angeles Partnership |
| --- | --- |
| Program Number: | SCG3527 |
| Quarter: | Second Quarter 2007 |

- Program Description:

The 2006-08 SCE/SCG/County of Los Angeles Energy Efficiency Partnership is a continuation of the successful partnership implemented in 2004-2005.  The partnership team consists of the County of Los Angeles Internal Services Division (LAC/ISD) and the Investor Owned Utilities (IOUs): Southern California Edison (SCE) and Southern California Gas Company (SCG).  The partners will apply the lessons learned from its previous project implementation experience, as well as from other existing, successful partnership programs.  This scope of this program will focus on retro-commissioning and retrofit activities in County facilities, will apply some of the recommendations from the Public Agency Collaboration study and will explore opportunities to expand the partnership to include retrofit and retro-commissioning activities in other county affiliated agencies.  These agencies may include the Los Angeles County Office of Education (LACOE), the Los Angeles Unified School District (LAUSD), and the Los Angeles County Metropolitan Transportation Authority (LACMTA).  The Investor Owned Utilities (IOUs) will collaborate with LA County’s Internal Services Division to continue.

The management structure of this partnership will remain the same with projects managed by a management team which consists of representatives from each party (SCE, SCG, and County of LA). Each program element will be coordinated through specific project teams for Retro-commissioning (RCx) and Retrofit activities.

- Administrative Activities:

- Processed Phase Two Purchase Orders for RCx Activities:

  - Award one of two, EMC Engineers, Inc. The PO# V3057901 includes 2 building groups.  7 Facilities will be Retro-Commissioned as a part of this contract.

  - Award two of two, Engineered Mechanical Services Inc. (EMSI).  The PO# V3057902 includes 3 building groups.

- Working with LA County EE Subcommittees to identify project opportunities.  Recycled water initiatives were also discussed. This will relate to pumping efficiency and ability to capture energy savings for saving water. Still pending CPUC decision.

- Attended LEED-EB sub team meeting - County wanted to determine the feasibility of LEED-EB certification for existing buildings – in process.

- The partnership team will review the county's deferred maintenance list.  This is the County’s wish list to improve the facilities.  ISD has a list for all of the 38 ISD managed departments and a list from Sheriff Department.  Team will work with the Department of Health Services and Public works.  DPW may be a bit difficult since they are somewhat independent from ISD. This project has not been vetted so engineering assistance will be required to identified and evaluate the specific technology associated with the project.

- Currently in contact with M&V team to discuss scope of work to assess the feasibility of SCE to capture energy savings if SCE assists the county in developing a Green procurement strategy.  Partnership want to determine the feasibility to claim savings if County departments purchases a piece energy efficient equipment from the Green list developed by the partnership.

- In addition to RCx projects, the partnership team is actively seeking opportunities for new retrofit projects. The team had compiled information for potential projects such as lighting, motors, variable frequency drives, compressor optimization, and chiller replacements.  Additional engineering assessments shall be conducted to further develop the projects for implementation.

- SCE partnership management, in collaborated with internal SCE organizations, supported LA County Energy Policy task force to develop energy action plan recommendations for potential county wide energy policy.  The task force, consisted of various county departments, SCE, and SCG representatives, was mobilized to draft recommendations for the policy.  The energy policy was adopted by the County Board of Supervisors in February, 2007.   This policy will help the county to have a more cohesive strategy to deal with energy/water efficiency and sustainable practices.  This policy will create opportunities to develop comprehensive projects in support of the county’s policy objectives.  The partnership team will assess the potential opportunities to enhance the program and will propose a change to the program plan, if the energy policy has any substantial impact on existing program implementation and management.  The partnership teams are involved with various sub committees (outreach, energy/water) to assist in the development of the County’s implementation strategies.

- Marketing Activities:

The County’s Internal Service Department will perform the outreach task to increase interest and solicit projects from targeted County departments similar to the PY04-05 program.  Southern California Edison has participated in assisting with the County’s EE policy and will be coordinating projects with other departments within the County.

- Direct Implementation Activities:

Phase One Project Status:

- Alhambra Courthouse:  Planning, Investigation, eQuest, Implementation has been completed.  Remaining EEMs were implemented.  FPT was performed.  Completion of this facility was extended.   Expect completion by mid August 2007.

- West Covina Courthouse:  Planning, Investigation, eQuest, Implementation has been completed.  Completion of this facility was delayed.   Expect completion by early September 2007.

- Torrance Courthouse:  The Planning, Investigation Complete.  Expect completion by end of October 2007.

- Inglewood Juvenile  The Planning, Investigation phases Complete. EQuest report submitted.  EEMs being reviewed for potential implementation.  Expect completion by mid September 2007.

- Inglewood Courthouse:  The Planning and Investigation phases complete.  EQuest Report submitted.  EEMs being reviewed for potential implementation.  Expect completion of this building by end of October 2007.

- Santa Clarita:  The Planning phase report completed.  Expect completion by end of October 2007.

- Pomona South : The Planning and Investigation Reports completed.  Expect completion by end of October 2007.

- Pomona North:  The Planning and Investigation Reports completed.  Expect completion by end of October 2007.

- Norwalk:  The Planning and Investigation Reports completed.  Expect completion by end of October 2007.

- Registrar Recorder:  The Planning and Investigation Reports completed.  Expect completion by end of October 2007.

- Program Performance/Program Status:

 Program is on target

⁬ Program is exceeding expectations

⁬ Program is falling short of expectations

- Program Achievements (non-resource programs only):

Not Applicable

- Changes in program emphasis, if any, from previous quarter (new program elements, less or more emphasis on a particular delivery strategy, program elements discontinued, measure discontinued, budget changes, etc.).

None for Q2’07.  However, as noted above under administrative section, there may be potential opportunities to enhance the partnership program due to the adoption of County of Los Angeles energy policy.  In the event that the policy requires the partnership to collaborate with the County’s overall energy policy efforts, the partnership will identify the opportunities and will propose a modification to the current program plan.

- Discussion of near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation, etc.)

None

- Changes to staffing and staff responsibilities, if any

None

- Changes to contracts, if any

None

- Changes to contractors and contractor responsibilities, if any

- Purchase Order Issued to:  EMC Engineers, Inc. (EMC) for Phase Two RCx work.  EMC will be responsible for Group 1B and 3 of Phase 2 RCx activities that consist of 6 buildings.

- Purchase Order Issued to:  Engineered Mechanical Services, Inc. (EMSI) for Phase Two RCx work.  EMSI will be responsible for Group 1A, 2 and 4 of Phase Two RCx activities that consist of 8 buildings.

- Number of customer complaints received

None

- Revisions to program theory and logic model, if any

None