| Program Name: | Portfolio of the Future |
| --- | --- |
| Program Number: | SCG3530 |
| Quarter: | Second Quarter 2007 |

- Program description

The Portfolio of the Future Program is comprised of multiple diverse activities designed to help SoCalGas identify and evaluate promising emerging natural gas efficiency technologies.  The Portfolio Program starts with a comprehensive scan of technologies and an evaluation of their readiness for commercialization.  The inventory of technology opportunities will then be prioritized in accordance with criteria to be established with SoCalGas.  From this ranked inventory, a portfolio of studies and activities, including pilot demonstration projects and testing of new business models, will be implemented.  The overarching goal of this program is to advance development of promising technologies for possible inclusion in SoCalGas’ energy efficiency programs.

- Administrative activities

- Conducted project management and accounting activities, including monthly budget variance reports, work planning, staffing and scheduling.

- Performed monthly billing and reporting, including updating Sempra Utilities’ DBE (Diverse Business Enterprises) compliance reporting database.

- Modified monthly reporting and invoicing procedures in accordance with discussions with Sempra Utilities’ contract administrator.

- Attended Subcontractor Management and Reporting Tool (SMART) training.

- Marketing activities

- None

- Direct implementation activities

- Continued developing detailed scopes of work and refining work plans for technologies approved by SoCalGas for pilot testing and/or advancement.

- Reviewed proposed pilot work plans and approaches with SoCalGas Emerging Technology and Program Managers.

- Refined computations of estimated energy savings for selected six measures.

- Continued additional technology and market research to refine estimates of potential for additional measures.

- Developed detailed market research plans and survey instruments.

- Commenced assembling partnerships to implement pilots.

- Provided requested materials to EM&V contractor.

Pilot A – Spyrcor

- Provided workpapers to SoCalGas.

- Conducted interviews at facilities that have implemented the SpyroCor technology and confirmed the achievement of energy savings.

- Presently working with SoCalGas to identify potential customer locations.

Pilot B – Laundry Wastewater Recycle

- Identified primary and secondary barriers to wide-scale adoption of the technology measures.

- Engaged a subcontractor to conduct market research.  Subcontractor designed survey instruments and commenced market surveys.

Pilot C – Commercial Dishwashers

- Initiated discussions with potential partners about program goals and roles of participants.

- Conducted kickoff meeting with manufacturers to develop partnerships.

- Developed list of targeted manufacturers and contacts to broaden industry participation.

Pilot D – Solar Water Heaters

- Given current proposals to include solar hot water in the California Solar Initiative, this pilot study is currently on hold.

Pilot E – Steam Traps

- Developed a plan for field demonstration of the potential savings of technology measures and obtained commitment from two leading steam trap monitoring system manufacturers to participate in field demonstrations.

Pilot F – Cold Water (Enzymatic) Detergents

- Conducted discussions with a leading U.S. detergent manufacturer and a leading consumer products company to plan pilot program.

- Drafted market research plan.

Program performance/program status

Program is on target

Program is exceeding expectations

Program is falling short of expectations

- Program achievements (non-resource programs only):

- Commenced 5 of six approved pilot programs.

- Changes in program emphasis, if any, from previous quarter (new program elements, less or more emphasis on a particular delivery strategy, program elements discontinued, measure discontinued, budget changes, etc.).

- None.

- Discussion of near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation, etc.)

- Continue to conduct approved pilot projects.

- Conduct additional research and assessment of other candidate technologies for pilot testing and obtain approval from SoCalGas to develop detailed project concepts, partnerships and work plans.

- Changes to staffing and staff responsibilities, if any

- None

- Changes to contracts

- None

- Changes to contractors and contractor responsibilities, if any

DBE Subcontractors

- Engaged a Women-owned Business Enterprises (WBE) subcontractor, Skumatz Economic Research Associates, Inc. (SERA) to conduct market research.

- Engaged a WBE subcontractor, WordProse, Inc., to assist with copywriting of marketing materials.

- Number of customer complaints received

- None

- Revisions to program theory and logic model, if any, provided in February 1, 2006 concept paper.

- None