| Program Name: | Multi Family Energy Efficiency Retrofit Program |
| --- | --- |
| Program Number: | SCG3510 |
| Quarter: | Third Quarter 2007 |

- Program description:

The Southern California Gas Company (SoCal Gas) Multi Family Energy Efficiency Retrofit (MFEER) Program is a statewide program that targets property owners and managers of multifamily residential dwellings, homeowner’s associations, and mobile home park associations.  The program encourages property owners and managers to install qualifying energy efficiency products in common areas for residential apartments, mobile home parks and condominium complexes.  The program is designed for flexibility; it offers agreed upon statewide measures for coordinated implementation, but is designed to easily adapt to market changes, including adding new measures that may emerge as cost effective opportunities in the SoCalGas local service area.

- Administrative activities:

Routine monthly administration activities include but not limited to the following:  project tracking, review of prospective projects, coordination, contract management, responding to customer inquiries and concerns, planning for future marketing events, and managing of program budgets and expenditures were performed.

In addition, program staff:

- Continued ongoing communication with Processing and Inspection group to ensure correct application of 2007 program procedures.

- Continued participation in weekly Statewide IOU Multifamily Rebate Team conference calls.

- Attended bi-monthly Residential Customer Programs Staff Meetings.

- Coordinated maintenance and updates of SoCalGas’ 2007 Multifamily Rebate webpage.

- Coordinated maintenance and updates of SoCalGas’ 2007 Multifamily Rebate information for Flex Your Power web pages.

- Updated and finalized Multifamily Processing Procedures.

- Assisted with scoring of 3rd Party Proposals for Water Heating Programs.

- Assisted with the Internal Team Review of 3rd Party Proposal for Controllers in Hospitality Industry.

- Attended CRM demonstration meeting for potential users.

- Attended Director’s Quarterly Dialog Sesson, ERC, Downey.

- Marketing activities:

- Applications may be downloaded via the web site or requested via SoCalGas’ Residential Marketing Department, or Program Manager.

- Partnered with Public Affairs Manager to coordinate and distribute SoCalGas’ marketing materials at event hosted by Irvine Apartment Communities.

- Outreach coordinators continued to promote Multifamily Rebate Program at all residential public events and tradeshows in service territory (specific Multifamily events outlined below):

- 09/20/07:  Participated in the Apartment Association of California’s “Passport to Success” Tradeshow, Long Beach, CA

  - Distributed multifamily applications, tri-fold program description brochures and Multifamily Fact Sheet during the tradeshow.

  - Offered free EE Starter Kit promotion (Low Flow Showerheads and Aerator sets) to attendees.

- Launched a second phase Direct Mail Campaign to GME (Master Metered accounts) to promote MF EE Rebate Program and Free EE Starter Kit to multifamily properties.

- Assisted with the coordination of multifamily program launch for the Palm Desert Partnership program, in order to ensure consistency and reduce customer confusion regarding rebate measures and specifications.

- Direct implementation activities:

- Multifamily EE Rebate applications and brochures were delivered to customers in SoCalGas service territory via tradeshow and outreach participation during third quarter.

- Ongoing random inspections of installed rebate measures as required per program specifications.

- Continued Pre-Inspections for SoCalGas Multifamily Rebate Program, with an emphasis on conducting 100% Pre-inspections on Controller devices and 25% of all other measures.

- Attended American Council for an Energy Efficient Economy Conference, Berkeley, CA.

- Statewide IOU Multifamily Rebate Program received “Exemplary Program” award by the American Council for an Energy Efficient Economy (ACEEE).

- Program performance/program status:

Program is on target

Program is exceeding expectations

Program is falling short of expectations

Explain:

Year-to-date, there have been 1206 requests for reservations received for 2006-2008 Multifamily Rebate Program through September 30, 2007.  42% of the incentive goal for 2006-2007 has been paid, and the program has achieved 40% of therm goal.  Currently, the program is falling short of expectations.

- Program achievements (non-resource programs only):

N/A

- Changes in program emphasis, if any, from previous quarter (new program elements, less or more emphasis on a particular delivery strategy, program elements discontinued, measure discontinued, budget changes, etc.):

- Fulfillment on the Multifamily Energy Efficiency Starter kits has been delayed due to internal processing requirements.  Work papers to substantiate therm savings in the Multifamily sector have been requested from engineering and are expected in fourth quarter.   Fulfilment should commence as soon as internal requirements are met.  Large volume requests are expected and should account for increased therm savings.

- Instituted Pre-Inspections for 100% Controllers and 25% of all other measures in MF Program.

- Still awaiting final results on Secondary evaluation on Boiler Controllers by KEMA, Inc. to substantial therm savings for the measure.

- Discussion of near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation, etc.):

Will continue to focus on opportunities to provide Low Flow Showerheads and Aerators in Multifamily Properties:

- Will offer sign-ups for Free EE Starter Kits at all Residential Outreach Events.

- Will offer Free EE Starter Kit on SoCalGas’ MF Webpage (will implement in the fourth quarter 2007).

- Preliminary plans to offer Free EE Starter Kit on Interactive Voice Response Unit for the Customer Call Center is being researched.

Plans to promote MF Rebate Program by participating in upcoming tradeshows:
10/30/07:  Apartment Owners Association Tradeshow
11/26/07:  Apartment Association of Santa Monica Mini Tradeshow

- Changes to staffing and staff responsibilities, if any:

Continued to employ a “Temporary” Data Entry Clerk to assist with the program administration.

- Changes to contracts:

None.

- Changes to contractors and contractor responsibilities, if any:

None.

- Number of customer complaints received:

None.

- Revisions to program theory and logic model, if any:

None.