Program Name:	Mobile/Manufactured Home Innovative Outreach and Measure Program

Program Number:	SCG3539

Quarter:		Third Quarter, 2007

- Program Description
The Mobile/Manufactured Home Innovative Outreach and Measure Program has been designed to provide gas measures on a comprehensive basis to 14,500 mobile home customers in the SCG service territory.

- Administrative Activities
We are pleased to report that the third quarter was our strongest quarter of production for the program and also held our two best individual months, which were July and August, with 110,993 Therms saved during the 3rd quarter.

Throughout the third quarter, we continued to work closely with SCE program managers, and transitionally, to a new SCE contacts to successfully build production levels, while at the same time reviewing all invoices and to look at ways to strengthen the entire acquisition, installation and billing process.

As a result, Synergy is applying a number of excellent checks and balances to assure that the measure forms match the invoices with a high level of data integrity. We have also set up a control sheet to provide a check and balance for each invoice.  These measures will help strengthen the audit trail for the program.

Synergy has applied these processes to the third quarter invoices, and has also gone back through each pervious invoice to apply these improved standards.

We have been working on organizing our systems and structures to consistently work through our finding, scheduling, installation and inspection processes to consistently increase production in an effort to hit program targets 6-12 months ahead of schedule. We have been working on increasing the numbers of technicians in the field, which will provide us with added production capability.

Synergy, along with SCE-SCG continues to work to build both processes and production to maximize cost effective energy savings and the highest degree of customer satisfaction possible.

We are pleased to report an excellent and smooth transition to new Program Manager Davi Ibarra. We appreciate being able to work with him and the fine team at SCE / SCG to continue the success of the Comprehensive Manufactured Mobile Home Program.

- Marketing Activities
Our marketing and outreach staff has worked toward supporting our business plan by personally distributing flyers in several parks to increase interest and attendance at follow-up neighborhood meetings. During the third quarter, our marketing office sent a total of 16,412 direct mail pieces (5,649 in July; 5,596 in August; 5,167 in September) to mobile home residents in the SCG service area. In addition, our marketing and outreach personnel personally distributed flyers to 2,180 mobile home community residents (180 in August; 2,000 in September), plus to an additional 4 community parks (all in July).

Our marketing and outreach personnel have held 21 neighborhood meetings with 478 guests in attendance during the third quarter.  During these meetings a program overview was presented to possible Mobile Home clients. Samples of the measures to be performed were demonstrated and potential clients and program participants were able to ask questions.  It was felt that these neighborhood meetings were quite productive.  Many customers are able to schedule their appointments for installation directly from these meetings.

Locations and numbers where neighborhood meetings were held are included as follows:

| Month | Mobile Home Park | City | Number Attending |
| --- | --- | --- | --- |
| July | San Vicente | Santa Barbara | 40 |
|  | Blue Sky | Santa Barbara | 10 |
|  | Littleton’s | San Bernardino | 30 |
|  | Bananza | Yucaipa | 5 |
|  | Walnut Grove | Walnut | 30 |
|  | Rancho MHP | Goleta | 15 |
|  | Rancho Granada | Carpentra | 10 |
|  | Country Highland | Beaumont | 20 |
| Total July | 8 |  | 160 |
| Total PTD | 145 |  | 3,579 |

| Month | Mobile Home Park | City | Number Attending |
| --- | --- | --- | --- |
| August | Parque MHP | Rialto | 13 |
|  | Country Club Village | Camarillo | 35 |
|  | Vista De Santa Barbara | Santa Barbara | 40 |
| Total August | 3 |  | 88 |
| Total PTD | 148 |  | 3,667 |

| Month | Mobile Home Park | City | Number Attending |
| --- | --- | --- | --- |
| September | Cedar | Bloomington | 25 |
|  | Villa Magnolia | Westminster | 35 |
|  | Villa Nova | Pico Rivera | 75 |
|  | Yucca Valley Trailer | Yucca Valley | 30 |
|  | Alto Camino | Loma Linda | 20 |
|  | Bolsa Verde | Westminster | 5 |
|  | Cedar | Bloomington | 25 |
|  | Romona | Chino | 5 |
|  | Town & Country | Santa Ana | 5 |
|  | Warren Park | Santa Ana | 5 |
| Total Sept | 10 |  | 230 |
| Total PTD | 158 |  | 3,897 |

- Direct Implementation Activities
Synergy continues to monitor ways to improve direct implementation processes and procedures and is pleased that production levels are on track and ahead of schedule.

- Program Performance/Program Status
(	Program is on target
(	Program is exceeding expectations
(	Program is falling short of expectations

- Program Achievements (Non-Resource Programs Only)
Not applicable.  This is a resource program

- Changes in program emphasis, if any, from previous quarter (new program elements, less or more emphasis on a particular delivery strategy, program elements discontinued, measures discontinued, budget changes, etc.).
None, other than working to increase production and complete all work, where possible in 2007.  We will then work with the program manager to explore supplemental funding for 2008 to gain additional energy savings.

- Discussion of near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation, etc.).
Synergy has added additional technicians and crews to increase production throughout the summer months. Not only have these individuals assisted during the summer period, but will continue to do so throughout the reminder of 2007 and the fourth quarter.

- Changes to staffing and staff responsibilities, if any.
None

- Changes to contracts, if any.
None

- Changes to contractors and contractor responsibilities, if any.
None

- Number of customer complaints received.
During the third quarter of 2007 there were 27 customer complaints, all of which have been successfully resolved to the customers’ satisfaction. A supervisor was sent to each site immediately after each call to diagnose and personally address the issue. We appreciate this feedback and in order to improve our customer service, are working closely with our technicians to make sure that all measures are working properly when leaving the installation site, to use proper business etiquette when on site, to ensure they have the appropriate supplies at each site and we have also worked with the office staff and technicians to address all scheduling concerns, including the timeliness of the technicians for appointments. We are working with the technicians to follow-through carefully with each customer and confirm that each measure is properly functioning before leaving the site and to be more social and communicative.

Synergy received 600 complimentary customer satisfaction calls and cards in the third quarter of 2007 and 3,024 program-to-date. Customers are very satisfied for the services rendered and for the program in general.

- Revisions to program theory and logic model, if any.
None. Provided in February 1, 2006 concept paper.