| Program Name: | Bakersfield Kern County Energy Watch |
| --- | --- |
| Program Number: | SCG3523 |
| Quarter: | Fourth Quarter 2007 |

- Program description

The Bakersfield and Kern County Energy Watch (BKCEW) has built on the success of the 2004-2005 partnership.  This partnership is a unique cooperative effort of Pacific Gas and Electric Company (PG&E), Southern California Edison (SCE) and Southern California Gas Company (SCG).  Partnership offerings are available to residents, businesses and municipalities of the City of Bakersfield and Kern County.  The Partnership is reducing energy use by providing energy efficiency information and direct installation of energy-efficient equipment to homeowners and small businesses in targeted areas, while continuing to retrofit municipal properties.  The 2006-2008 BKCEW has been enhanced by a new component that offers training to city building inspectors.

- Administrative activities

- Program Manager and/or PG&E Government Relations Representative met with the City Managers of Arvin, Shafter and Taft and the Finance Director and Public Works Director of the City of Wasco to discuss the partnership and to seek their support of City energy efficiency projects.

- Monthly partnership meetings were held with City, County, IOU and Staples Marketing representatives.

- Meetings were held with the appropriate IOU and Staples Marketing to discuss budget and program implementation issues.

- Marketing activities

- The partnership had a booth at the Bakersfield Fall Home Show held October 19 – 21 at the Kern County Fairgrounds.

- Staples Marketing made a presentation on energy saving during a community meeting of the Dolores Huerta Foundation in Lamont on October 25.

- The partnership was represented at the Greater Bakersfield Chamber of Commerce Business & Tech Expo held on October 30.

- Direct implementation activities

- The small business and residential direct install components are successfully

meeting goals.

- Program performance/program status

X   Program is on target

Program is exceeding expectations

Program is falling short of expectations (explain)

- Program achievements (non-resource programs only)

- The following Seminars were held during the Fourth Quarter:

October 17, Overview of ACCA Quality Installation Standards

November 1, Equipment Sizing and Selection Using ACCA Manual J

December 6, Zoning Design and Beyond

December 13, Advanced ACCA Manual D

- Changes in program emphasis, if any, from previous quarter (new program elements, less or more emphasis on a particular delivery strategy, program elements discontinued, measure discontinued, budget changes).

- Greater emphasis was placed on working with the City of Bakersfield and Kern County and associated departments to inform them about the incentive component of the Energy Watch program and to discuss potential municipal facility projects

- Discuss near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation).

- In addition to working with the City of Bakersfield and Kern County increased emphasis will be placed on working with outlying cities within Kern County to promote the Energy Watch program and the incentive component for municipal retrofits.

- Changes to staffing and staff responsibilities, if any

- None

- Changes to contracts, if any

- None

- Changes to contractors and contractor responsibilities, if any

- Staples Marketing has begun their role as an implementer for the partnership.

- Number of customer complaints received

One customer complaint was received regarding a concern about whether or not their electric bill had increased since having energy saving devices installed in the motel they own.  Upon researching the issue, it was discovered that the customer’s bill has actually decreased 23% since having the devices installed compared to the same period last year.  The customer was satisfied with the response and information provided.

- Revisions to program theory and logic model, if any

None