| Program Name: | SCE/SCG/County of Los Angeles Partnership |
| --- | --- |
| Program Number: | SCG3527 |
| Quarter: | Fourth Quarter 2007 |

- Program Description:

The 2006-08 SCE/SCG/County of Los Angeles Energy Efficiency Partnership is a continuation of the successful partnership implemented in 2004-2005.  The partnership team consists of the County of Los Angeles Internal Services Division (LAC/ISD) and the Investor Owned Utilities (IOUs): Southern California Edison (SCE) and Southern California Gas Company (SCG).  The partners will apply the lessons learned from its previous project implementation experience, as well as from other existing, successful partnership programs.  This scope of this program will focus on retro-commissioning and retrofit activities in County facilities, will apply some of the recommendations from the Public Agency Collaboration study and will explore opportunities to expand the partnership to include retrofit and retro-commissioning activities in other county affiliated agencies.  These agencies may include the Los Angeles County Office of Education (LACOE), the Los Angeles Unified School District (LAUSD), and the Los Angeles County Metropolitan Transportation Authority (LACMTA).  The Investor Owned Utilities (IOUs) will collaborate with LA County’s Internal Services Division to continue.

The management structure of this partnership will remain the same with projects managed by a management team which consists of representatives from each party (SCE, SCG, and County of LA). Each program element will be coordinated through specific project teams for Retro-commissioning (RCx) and Retrofit activities.

- Administrative Activities:

- Acquired additional resources necessary to integrate project process into SMART reporting system to update and track project performance and other non-energy savings activities.

- Continuing discussions to connect Savings By Design program group with County’s regional planning office to collaborate on current energy policy initiative for sustainable communities as well as new construction projects.  This will ensure that SCE and SCG is on board with any proposed future new construction and codes and standards activities.

- Worked with M&V to commence feasibility for reporting savings based on influence in development of County’s Green purchasing strategies.

- Draft partnership project identification, review and implementation process to streamline project administration and engineering review and establish pool of projects with EE opportunities.

- Partnership team completed evaluation of bids for Phase 3 RCx projects.  Two contractors were chosen to support this effort.

- Working with LA County EE Subcommittees to identify project opportunities.  The process will help to centralize the identification and assessment of projects for all County departments and will increase opportunities for the partnership to encourage the implementation of more energy efficient technologies that are beyond code requirements.  Recycled water initiatives were also discussed. This will relate to pumping efficiency and ability to capture energy savings for saving water. Still pending CPUC decision.

- In addition to RCx projects, the partnership team is actively seeking opportunities for new retrofit projects. Completed assessment for the following project:

  - East LA Chiller Project – Engineering Analysis Completed. Project estimated completion date is June 2008.

- Marketing Activities:

The County’s Internal Service Department will perform the outreach task to increase interest and solicit projects from targeted County departments similar to the PY04-05 program.  Southern California Edison has participated in assisting with the County’s EE policy and will be coordinating projects with other departments within the County.

- Direct Implementation Activities:

- Phase One Project Status:

- Alhambra Courthouse:  Final Report and Training.  Complete.

- West Covina Courthouse:  EEMs implemented.   FPT performed, Final Report and Training.  Complete.

- Torrance Courthouse:  Implementation, EEMs implemented.  FPT in process. Expect completion January 2008.

- Inglewood Juvenile Final Report and Training Scheduled for January.

- Inglewood Courthouse:  Implementation, EEMs implemented. FPT was performed.  Final Report and Training Scheduled for January 2008.

- Santa Clarita:  Implementation, EEMs implemented.  FPT in process.    Expect completion January 2008.

- Pomona South: Final Report and Training  Scheduled for January 2008.

- Pomona North: Final Report and Training Scheduled for January 2008.

- Norwalk:  EEMs implemented.  Final Report and Training Scheduled for January 2008.

- Registrar Recorder:  EEMs implemented.  FPT Complete.  Final Report and Training Scheduled for January 2008.

- Phase Two Project Status:

- Ferguson Administration:  Planning in process.

- Michael Antonovich CH:  Planning Report submitted, Investigation in process.

- ISD Headquarters:  Planning in process.

- Edelman Children’s Court: Planning in process.

- Airport CH:  Planning in process.

- Ferguson Health:  Planning in process.

- Sherman Block Sheriff’s: Planning in process.

- Long Beach CH:  Planning Approved, Investigation in process.

- Tidemanson:  Planning in process. Removed from Phase 2 PO.

- Dorthy Kirby:  Removed from Phase 2 PO.  Potential for revised scope.

- Los Padrinos:  Removed from Phase 2 PO.  Potential for revised scope.

- Harbor Hospital:  Removed from Phase 2 PO.  LA County to add this to county managed solicitation for RCx.

- Phase Three Project Status:

- Cudahy DPSS: Planning in process.

- DHS Roybal:  Planning in process.

- DCFS Region 2: Planning in process.

- AV Civic:  Planning in process.

- AV Service Center: Planning in process.

- Lancaster Library:  Planning in process.

- DPSS Pomona:  Planning in process.

- In addition to RCx projects, the partnership team is actively seeking opportunities for new retrofit projects. Completed assessment for the following projects.

  - Modifying domestic hot water system at Norwalk Courthouse to improve energy efficiency of boiler system.

- Program Performance/Program Status:

( Program is on target

⁬ Program is exceeding expectations

⁬ Program is falling short of expectations

- Program Achievements (non-resource programs only):

Not Applicable

- Changes in program emphasis, if any, from previous quarter (new program elements, less or more emphasis on a particular delivery strategy, program elements discontinued, measure discontinued, budget changes, etc.).

None for 4th Quarter 2007.  However, as noted above under administrative section, there may be potential opportunities to enhance the partnership program due to the adoption of County of Los Angeles energy policy.  In the event that the policy requires the partnership to collaborate with the County’s overall energy policy efforts, the partnership will identify the opportunities and will propose a modification to the current program plan.

- Discussion of near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation, etc.)

None

- Changes to staffing and staff responsibilities, if any

None

- Changes to contracts, if any

In the course of managing the implementation activities and contracts for the RCx projects noted above, the partnership have had some difficulty with the performance of one of the contractors.  This affected six buildings of the Phase 2 building group.  As such, the partners had to reduce the scope of work for this contractor to 2 buildings.  The other 4 buildings will be assigned to another contractor, when feasible.  This contractor issue has impacted the implementation schedule.

- Changes to contractors and contractor responsibilities, if any

Yes, Please see 10 above.

- Number of customer complaints received

None

- Revisions to program theory and logic model, if any

The County ISD was successful in garnering the support of County Supervisors to support a contracting approach where the County create a pool of qualified engineering and contractors to support future retrofit and retro-commissioning efforts.  This will allow the County to Contract directly with the agents to assess and implement energy projects.