| Program Name: | Alliance Partners Program (a.k.a.) California Sustainability Alliance |
| --- | --- |
| Program Number: | SCG3533 |
| Quarter: | Fourth Quarter 2007 |

- Program description

The Alliance Partners Programs, also known as the California Sustainability Alliance Program, is designed to increase and accelerate adoption of energy efficiency by packaging it with complementary "sustainability" measures (i.e., energy and water use efficiency, renewable energy, waste management, and transportation management).  In this manner, energy efficiency can be achieved more effectively and cost effectively, increasing net societal benefits and maximizing benefits to California ratepayers.  The scope will include multiple projects and programs, all dedicated towards (1) advancing and promulgating the body of sustainability best practices, tools and techniques; (2) leveraging the collective resources of all partners -- both public and private; local, state and federal; and (3) developing educational and outreach materials to widely disseminate the body of emerging and existing best practices.

- Administrative activities

- Conducted project management and accounting activities, including monthly budget variance reports, work planning, staffing and scheduling.

- Performed monthly billing and reporting, including updating Sempra Utilities’ DBE (Diverse Business Enterprises) compliance reporting database.

- Maintained the SMART system.

- Marketing activities

- Continued development of communications and graphics strategy and website design.  Phase 1 of the Alliance website was launched on October 15, 2007:

http://sustainca.org/

- Continued development of marketing and outreach plan, with focus on developing and conducting the first in a series of "Best-of-the-Best in Sustainability" Roundtables. The first event, held in Los Angeles on November 15th, 2007 focused on utilities' sustainability programs.

- Through research, the Alliance determined there were already many university competitions.  Consequently, with the consent of SCG, the Alliance's suggested university level competition was transformed into a student intern program.  Announcements were posted on the Alliance website and disseminated to California colleges and universities in December 2007.

- Commenced development of the Sustainability Showcase, with focus on identifying California market leaders in sustainability best practices from both the public and private sectors.

- Direct implementation activities

General:  Continued identifying key stakeholders, potential participants and existing programs and resources for pilot projects.

- Steering Committee & Pilot Advisory Committees -  Portfolio Manager for CalPERS and the Director of the California Dept. of Conservation, joined the Steering Committee.  A joint meeting of the Steering Committee and Green Buildings/Leases PAC was held on December 12, 2007.

- Best Practices: Sustainability Elements of General Plans – Continued building a library of model sustainability policies, goals, objectives and language for General Plans.  Commenced design of searchable database of best practices and model General Plan language.  Also commenced discussions with Governor’s Office of Planning & Research about assisting them in integrating sustainability elements into their update of the state’s General Plan Practice Manual.

Pilot Projects:

- Pilot 1, Affordable Housing – HUD HQ drafted a letter to targeted participants in its “Mark to Market” Green Initiative program, suggesting that they contact the Alliance for assistance.

- Pilot 2, New Mixed Use “Zero Carbon” Communities (ZCC) – The City of Irvine pilot project commenced with (a) documentation of lessons learned to-date at Heritage Fields, and (b) initial work related to computing the carbon impacts of the City’s 20 Year Energy Plan.  In addition, completed survey level audit of retrofit opportunities in sampling of existing multi-family residential properties owned and operated by BRE Properties.  Also commenced review and recommendation of options for increasing the level of sustainability in its new multi-family facilities being developed.

- Pilot 3, LEED – Existing [Commercial] Buildings – Completed market research and stakeholder interviews with regard to greening leased office space and completed draft “Green Leasing Toolkit” that was presented to the Steering Committee and Green Leases PAC at the joint meeting in December 2007.

- Pilot 4, Water-Energy – Continued analysis of the opportunity to achieve energy and carbon savings by increasing and accelerating development and use of recycled water in southern California.

- Pilot 5, Local Government – Commenced the City of Ontario pilot through four initial activities: (a) developing green criteria for affordable and other housing developments; (b) opportunities to incorporate sustainability elements into the City’s draft General Plan Update; (c) review of the City’s recycled water plan/program for potential energy benefits; and (d) recommendations for implementing green procurement guidelines and strategies.

- Program performance/program status

Program is on target

Program is exceeding expectations

Program is falling short of expectations

- Program achievements (non-resource programs only):

- All five pilots are underway.

- Phase 1 of the Alliance website has been launched.

- Conducted the first Sustainability Roundtable.

- Completed draft “Green Leases Toolkit”.

- Changes in program emphasis, if any, from previous quarter (new program elements, less or more emphasis on a particular delivery strategy, program elements discontinued, measure discontinued, budget changes, etc.).

- As discussed above, consistent with the Alliance’s principles of cost effectiveness and leverage, the Alliance decided not to conduct a university level sustainability competition since there were already many other such competitions already being conducted.  Instead, in consultation with SCG, the Alliance changed the university competition to a student intern program.

- Discussion of near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation, etc.)

- Continue to refine website design, content and functionality, including Showcase, Forum and Toolkit.

- Develop next Sustainability Roundtables &/or Summits.

- Hire student interns.

- Launch Sustainability Showcase.

- Continue to recruit Alliance advisors, partners and participants, and obtain commitments.

- Continue providing technical assistance to pilot participants.

- Changes to staffing and staff responsibilities, if any

- None

- Changes to contracts

- None

- Changes to contractors and contractor responsibilities, if any

- ASW Engineering, a DBE firm, was hired to assist in identifying and evaluating energy efficiency opportunities for pilot project participants.

- LUCITA, a DBE marketing consultant that specializes in corporate social responsibility issues, was hired to develop an integrated graphics, marketing and media strategy for the Alliance program.

- Number of customer complaints received

- None

- Revisions to program theory and logic model, if any

- None