| Program Name: | Statewide Residential Home Energy Efficiency Survey |
| --- | --- |
| Program Number: | SCG3509 |
| Quarter: | 1st Quarter 2008 |

- Program description:

The Southern California Gas Company (SoCalGas) Home Energy Efficiency Survey (HEES) program is a statewide residential audit program that provides residential customers the opportunity to participate in a Mail-In, Online, and

In-Home energy analysis of their home.  The primary intent of the program is to increase customer awareness of energy efficiency opportunities and prompt participation and greater crossover within other energy efficiency rebate programs.

- Administrative activities:

Routine monthly administrative activities include but are not limited to the following activities:  manage and track current survey program in production, manage and develop new survey program enhancements, contract management, respond to customer inquiries and concerns, plan future marketing events, and manage program budgets and expenditures.

Additional administrative activities for the first quarter included:

- Sponsored an auditor one-day training seminar to provide an update on new residential program developments.

- Continued to refine the customer participation process for all survey types.

- SoCalGas, in partnership with Southern California Edison (SCE), contacted Metropolitan Water District to solicit an opportunity to discuss the possibility of a multiple-utility collaboration effort in delivering surveys that will maximize funds amongst the electric, gas, and water agencies in order reach more customers with more customized surveys and to achieve program goals.

- Started dialogue with SCE to broaden the scope of the survey tool to address the special needs of renters and multi-family complexes, including the common facilities associated with these dwelling types.

- Started dialogue with SCE to enhance the HEES tool with “carbon footprint” calculation capability.

- Marketing activities:

- Continued efforts between Single Family Rebate (SFR) Program and HEES.  HEES continuing to leverage SFR low-flow showerheads and faucet aerators as Home Energy Efficiency Kit (EE Kit) gifts to Online, In-Home, and Mail-In HEES participants.

- Started 2009-2011 joint-utility marketing strategy discussions with Edison.

- Coordinated efforts with Edison to create a more colorful five minute paper survey in multiple languages for outreach events.

- Working to enhance in-language HEES accessibility directly from the SoCalGas website by providing “other language” options on the SoCalGas website landing page.  This will provide a direct link to the customer-selected in-language survey site.  These efforts will facilitate the ease at which customers, whose primary language is not English, can access the survey.  The language options include Spanish, Korean, Chinese, and Vietnamese.

- Direct implementation activities:

- The Online HEES continues to be the most cost-effective delivery channel in the joint marketing of our energy efficiency resources to SoCalGas and SCE customers.

- All In-Language survey websites (Spanish, Korean, Chinese, and Vietnamese) are currently in development expected to be available on the KEMA Gateway website by the second quarter 2008.

- The MyAccount/HEES Integration development project is in process.  Its aim is to enhance the user experience by foregoing an extra login at the point the user jumps site, and takes the Home Energy Survey.  Led by Customer Care South, the project has completed the Requirements, System Design, and Detail Design phases.  The construct/build phase is about to begin, with a projected release date of August 31, 2008.

- KEMA auditors have started giving EE Kits to customers following their completion of an In-Home survey.  When agreed upon by the customer, KEMA is providing “direct installation” of the showerheads and aerators.

- For the first quarter of 2008, the fulfillment contractor for joint SoCalGas/SCE customer surveys has assembled, packaged, and mailed out 9,626 EE Kits to Online and Mail-In HEES participants.

- For the first quarter of 2008, In-Home auditors have either directly installed or hand delivered 1,684 EE Kits as an incentive for their participation in the HEES program.

- Program performance/program status:

Program is on target

Program is exceeding expectations

Program is falling short of expectations

Explain:

- SoCalGas new Online HEES is continuing to perform exceptionally strong.  It has exceeded its three-year goal.

- The Mail-In HEES has reached 96% of its three-year goal.

- The In-Home HEES has reached 91% of its three-year goal.

- Program achievements (non-resource programs only):

- 30,493 SoCalGas Online HEES completed.  (Met three year goal.)

- 5,461 SoCalGas In-Home HEES completed.

- 23,024 SoCalGas Mail-In HEES completed.

- Changes in program emphasis, if any, from previous quarter (new program elements, less or more emphasis on a particular delivery strategy, program elements discontinued, measure discontinued, budget changes, etc.):

- The Direct Installation Agreement has been printed and is currently being used by In-Home auditors for acknowledgement of customer approval prior to the direct installation of showerheads and aerators.

- In-Home training of Korean, Chinese, and Vietnamese speaking auditors was completed in January 2008.  Global Energy Services (vendor for In-Language auditors) has begun to have auditors deliver EE kits to their customers following their completion of an In-Home In-Language survey.  The response rate in these “hard-to-reach” communities has been very positive.

- Discussion of near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation, etc.):

- Working with SCE and KEMA (vendor) to implement the 2008 Mail-In Survey marketing strategy and mailing schedule.

- All Asian-Language websites will be available for customer use except the Chinese.  It is in its final stages of translation and will be available by second quarter 2008.

- Changes to staffing and staff responsibilities, if any:

None

- Changes to contracts:

A change order to the contract with the HEES vendor has been executed to include the direct installation of EE kits during the In-Home surveys.  The change order also included updates to some of the fees charged for the surveys based upon an increase in the Consumer Price Index (CPI).

- Changes to contractors and contractor responsibilities, if any:

None.

- Number of customer complaints received:

None.

- Revisions to program theory and logic model, if any:

None.